## Consolidated timetable
ZULULAND DISTRICT MUNICIPALITY
2027/2028 MTREF : Schedule of key deadlines and Budget time table
| DETAILS | LEGISLATION |  | RESPONSIBILITY |  | OUTPUT | ACTIONS | date
|  |  | ACTIVITY | OFFICIAL | COUNCILLOR
July --2026
BUDGET PROCESS
July 2026 | Mayor begins planning for next three-year budget in accordance with co-ordination role of budget process. Planning includes review of the previous years budget process and completion of the Budget Evaluation Checklist Formation of budget Steering Committee (Section 4, subsection 1) Mayor establishes committees and consultation forums for the budget process Mayor establishes committees and consultation forums for the budget process | MFMA 53,68,MSAs76-81 | Accounting officers and senior officials of municipality and entities begin planning for next three-year budget Accounting officers and senior officials of municipality and entities review options and contracts for service delivery Approve and announce new budget schedule and set up committees and forums. Consultation on performance and changing needs. | Chief Financial Officer, | His Worship The Mayor
AUGUST -- 2026
BUDGET PROCESS
2026-08-01 | Mayor tables in Council a time schedule outlining key deadlines for: preparing, tabling and approving the budget; reviewing the IDP (as per s 34 of MSA) and budget related policies and consultation processes at least 10 months before the start of the budget year. The Mayor tables the budget timetable for approval Mayor establishes committees and consultation forums for the budget process | MFMA s 21,22, 23;MSA s 34, Ch 4 as amended | • MM to give notice to the community of the process to be followed (advertise)MSA s28(3) • The budget team co ordinate the budget time table | HOD Planning & Chief financial officer | His Worship The Mayor
SEPTEMBER -- 2026
BUDGET PROCESS
2026-09-01 | Council through the IDP review process determines strategic objectives for service delivery and development for next three-year budgets including review of provincial and national government sector and strategic plans. Budget Steering Committee |  | Budget offices of municipality and entities determine revenue projections and proposed rate and service charges and drafts initial allocations to functions and departments for the next financial year after taking into account strategic objectives Engages with Provincial and National sector departments on sector specific programmes for alignment with municipalities plans (schools, libraries, clinics, water, electricity, roads, etc). The Issue Budget Preparation Circular and Budget Instructions. Departments submit budget proposals and operational plans | HODs,Deputy CFO Revenue and Budget manager CFO HODs
OCTOBER -- 2026
BUDGET PROCESS
2026-10-01 | •Review of Service Delivery & Budget Implementation Plan | MFMA s 35, 36, 42; MTBPS | Accounting officer does initial review of national policies and budget plans and potential price increases of bulk resources with function and department officials. Review revenue assumptions, tariffs and funding Prepare draft Capital Programme | Budget office PMU
NOVEMBER -- 2026
BUDGET PROCESS
2026-11-30 | Budget preparation process proceed Management budget review sessions | MSA s 34 | Accounting officer reviews and drafts initial changes to IDP The budget input from department to be submitted Budget, liaises with departments. | Municipal Manager / CFO / HODs
DECEMBER -- 2026
BUDGET PROCESS
December 2026 | First Draft MTREF prepared Council finalises tariff (rates and service charges) policies for next financial year | MSA s 74, 75 | The draft budget be submitted to CFO for review Accounting officer and senior officials consolidate and prepare proposed budget and plans for next financial year taking into account previous years performance as per audited financial statements | Budget office Municipal Manager
December 2026 | Finalise inputs from bulk resource providers (and NERSA) and agree on proposed price increase | MFMA guidance | Council finalises tariff (service charges) policies for next financial year. | Chief Financial Officer
JANUARY --2027
BUDGET PROCESS
January 2027 | Note the President's State of the Nation Address for further budget priorities | MFMA guidance | Accounting officer reviews proposed national and provincial allocations to municipality for incorporation into the draft budget for tabling. (Proposed national and provincial allocations for three years must be available by January) Review funding compliance and budget assumptions Prepare detailed budgets and plans for the next three years. Review of mid-year budget and annual report. EXCO - Approval of mid-year budget and annual report. Review of Mid-Year Budget & Performance Assessment. Mayor to table annual report to Council. Contents of report in accordance with Sect. 127 (3) MM reviews proposed national and provincial allocations to municipality for incorporation into the draft budget for tabling. Submit a report of the mid-year budget and performance assessment to NT and PT. Engage PT on mid-year assessment feedback Departmental Managers Review and Approve provisional 3-year budget. | Municipal Manager | His Worship The Mayor
January 2027 | Entity board of directors must approve and submit proposed budget and plans for next three-year budgets to parent municipality at least 150 days before the start of the budget year | MFMA s 87(1), MFMA s 36 |  | Municipal Manager
January 2027 | Review whether comments from National Treasury and SALGA have been received on proposed price increases of bulk resources. | MFMA guidance |  | Chief Financial Officer
January 2027 | •Identify adjustment budget issues and parameters for discussion with Treasury.
January 2027 | Second draft of the Draft Estimate Report | MFMA guidance
January 2027 | To table the Mid year assessment to Budget steering committee | MFMA 8 Section 72 |  | Chief Financial Officer
January 2027 | Adoption of amended budget related policies and update Council on the status of the budget | MFMA guidance
FEBRUARY -- 2027
BUDGET PROCESS
February 2027 | Note National budget for provincial and national allocations to municipalities for incorporation into budget | MFMA guidance | Municipality engages Provincial KZN Treasury regarding Mid-Year Budget Performance Assessment. Prepare the adjustment budget documents MFMA section 28. Accounting officer finalises and submits to Mayor proposed budgets and plans for next three-year budgets taking into account the recent mid-year review and any corrective measures proposed as part of the oversight report for the previous years audited financial statements and annual report Budget steering committee Tabled the Adjustments Budget to EXCO Approval of Adjustments Budget - Tabled at Council Accounting officer to notify relevant municipalities of projected allocations for next three budget years 120 days prior to start of budget year Update the Draft Estimate Report Management workshop to give detail of funding and budget inputs. | Chief Financial Officer | His Worship the Mayor
February 2027 | Council considers municipal entity proposed budget and service delivery plan and accepts or makes recommendations to the entity | MFMA s 87(2), MFMA s 37(2)
Management Budget Workshop
Municipal Manager
|  | MFMA guidance |  | Chief Financial Officer
MARCH -- 2027
BUDGET PROCESS
March 2027 | Entity board of directors considers recommendations of parent municipality and submit revised budget by 22nd of month | MFMA s 87(2), MFMA s 22 & 37; MSA Ch 4 as amended | Place the Adjustments budget on the municipal website Engage PT on adjustment budget feedback MANCO - final draft budget for next year MM reviews any changes in prices for bulk resources as communicated by the 15th of March. Review of final draft budget / IDP to Finance Portfolio Approval of final draft Budget,SDBIP & IDP by Council - Mayor must table annual budget 90 days before start of budget year. Draft Tabled Budget submission to National Treasury & Provincial Treasuries Accounting officer publishes tabled budget, plans, and proposed revisions to IDP, invites local community comment and submits to NT, PT and others as prescribed. Accounting officer reviews any changes in prices for bulk resources as communicated by 15 March Receive notification of any transfers that will be made to the municipality from other municipalities in each of the next three financial years Table Annual Budgets - BSC Table Annual Budgets - Exco. Table Annual Budgets - Council | Budget office CFO / Deputy Director Research &Policy Municipality Manager | His Worship The Mayor
March 2027 | Mayor tables municipality budget, budgets of entities, resolutions, plans, and proposed revisions to IDP at least 90 days before start of budget year | MFMA s 16, 22, 23, 87; MSA s 34, MFMA s 42
March 2027 | Provide notification of any transfers that will be made by the municipality to other municipalities in each of the next three financial years | MFMA 37(2)
March 2027 | Table Draft MTREF, IDP and Budget-related Policies before Council | MFMA 16(2)
APRIL -- 2027
BUDGET PROCESS
April 2027 | Consultation with national and provincial treasuries and finalise sector plans for water, sanitation, electricity etc | MFMA 23, MFMA guidance | Place approved annual budget and policies on the municipal website Accounting Officer to Publish draft budget for comments/invite communities for comments. Engage PT on Tabled budget feedback Consultation with National and Provincial Treasuries Public hearings on the Budget, Council Debate on Budget and Plans. Revision of budget and IDP after input from National Treasury, Provincial, other Municipalities and public have been received Confirm National and Provincial budget allocations Accounting officer assists the Mayor in revising budget documentation in accordance with consultative processes and taking into account the results from the third quarterly review of the current year Revise budget documents (DER) incorporating comments from National and Provincial Treasury and stakeholders Print and distribute all budget documents including draft SDBIP | Budget office Chief financial officer Municipality Manager
April 2027 | Municipal hearings to be held on the Budgets | MFMA guidance
His Worship The Mayor
MAY -- 2027
BUDGET PROCESS
May 2027 | Budget steering committee |  | Table the propossed amendments as per budget consultation at the budget steering committee. Public hearings on the Budget, Council Debate on Budget, and Plans. Engage Provincial Treasury on tabled draft budget assessment Council adopts budget, resolutions, capital implementation plans, objectives, and changes in IDP. Revised budget and IDP tabled to Financial Portfolio Final approval of Budget & IDP by Council - Council to consider approval of budget and plans (at least 30 days before start of budget year) Accounting officer assists the Mayor in preparing the final budget documentation for consideration for approval at least 30 days before the start of the budget year taking into account consultative processes and any other new information of a material nature | Budget office Chief financial officer Municipality Manager | His Worship the Mayor
May 2027 | Public hearings on the budget, and council debate. Council consider views of the local community, NT, PT, other provincial and national organs of state and municipalities. Mayor to be provided with an opportunity to respond to submissions during consultation and table amendments for council consideration. Council to consider approval of budget and plans at least 30 days before start of budget year | MFMA s 23, 24; MSA Ch 4 as amended
May 2027 | Entity board of directors to approve the budget of the entity not later than 30 days before the start of the financial year, taking into account any hearings or recommendations of the council of the parent municipality | MFMA s 87
May 2027 | Fourth draft 2026/27 IDP review to be completed | MSA 25(1)
May 2027 | Council must approve annual budget by resolution, setting taxes and tariffs, approving changes to IDP and budget related policies, approving measurable performance objectives for revenue by source and expenditure by vote before start of budget year | MFMA s 16, 24, 26, 53
JUNE -- 2027
BUDGET PROCESS
June 2027 | Submit approved annual budget to provincial and National Treasury Mayor must approve SDBIP within 28 days after approval of the budget and ensure that annual performance contracts are concluded in accordance with s 57(2) of the MSA. Mayor to ensure that the annual performance agreements are linked to the measurable performance objectives approved with the budget and SDBIP. The mayor submits the approved SDBIP and performance agreements to council, MEC for local government and makes public within 14 days after approval | MFMA s 53; MSA s 38-45, 57(2) | Publish budget and tariffs. SDBIP to Mayor (14 days after approval of budget) SDBIP approval by Mayor - 28-day deadline after approval of the budget Workshoping the budget to management. | Chief Financial Officer
June 2027 | Council must approve annual budget by resolution, setting taxes and tariffs, approving changes to IDP and budget related policies, approving measurable performance objectives for revenue by source and expenditure by vote before start of budget year | MFMA s 16, 24, 26, 53