## Organizational SDBIP
ZULULAND DISTRICT MUNICIPALITY 2021/2022
KPA 01 - BASIC SERVICE DELIVERY AND INFRASTRUCTURE
Strategic Objective(SO) | KPI No. | Key Performance Indicator | Unit of Measure | Formula | IDP Strategic Objective Ref No. | Baseline | QUARTERLY TARGETS | [13 empty] | target date / reporting frequency | Budget Allocated (2020/21) | Vote No. | Responsible Department | STATUS | REASON FOR VIARIANCE | MEASURES TAKEN TO IMPROVE PERFORMANCE | Portfolio of Evidence
[7 empty] | Target Q1 30 Sep 2021 | Actual Q 1 30 Sep 2021 | POE | Target Q2 31 Dec 2021 | Actual Q2 31 Dec 2021 | POE | Target Q3 31 Mar 2022 | Actual Q3 31 Mar 2022 | POE | Target Q4 30 June 2022 | Actual Q4 30 June 2022 | POE | Annual Target 01 July 2021 - 30 June 2022 | Actual Annual 01 July 2021 - 30 June 2022
Continuously managing all developed infrastructure capital assets to minimize the total cost of owning and operating these assets while delivering the desired service levels & protecting the natural environment ( Effective Asset Management, internal&community capacity building, collecting revenue, tariffs, monitoring & evaluation, environmental management)
Continuously managing all existing infrastructure capital assets to minimize the total cost of owning and operating these assets. (Effective Asset Management, internal & community capacity building, collecting revenue, tariffs, monitoring & evaluation, environmental management) | 1 | Number of lightning conductors installed in identified rural households within ZDM per quarter | Number | N/A | SO 1.1.1 | TBT | 25 lightning conductors installed in identified rural households per quarter within ZDM | 44 |  | 25 lightning conductors installed in identified rural households per quarter within ZDM |  |  | 25 lightning conductors installed in identified rural households per quarter within ZDM |  |  | 25 lightning conductors installed in identified rural households per quarter within ZDM |  |  | 100 lightning conductors installed in identified rural households per quarter within ZDM by 30 June 2022 |  | Quarterly |  |  | Corporate Services | Achieved |  |  | Certificate of completion
| 2 | Date verification on ZDM infrastructure assets performed | Date | N/A |  |  | N/A | Q4 |  | N/A |  |  | N/A |  |  | Verification on ZDM infrastructure assets performed by 30 June 2022 |  |  | Verification on ZDM infrastructure assets performed by 30 June 2022 |  | 30-Jun-22 |  |  | Budget & Treasury | Q4 |  |  | Engineers certificate
[6 empty] | To be confirmed | [17 empty] | To be confirmed
| 3 | Number of ZDM water contracts under construction per quarter | Number | N/A |  |  | 24 ZDM water contracts under construction per quarter | Q2 |  | 22 ZDM water contracts under construction per quarter |  |  | 26 ZDM water contracts under construction per quarter |  |  | 23 ZDM water contracts under construction per quarter |  |  | 18 ZDM water contracts under construction by 30 June 2022 |  | Quarterly |  |  | Planning services | Q2 |  |  | Contracts List and Appointment letters of service providers
| 4 | Number of ZDM sanitation contracts under construction per quarter | Number | N/A |  |  | 2 ZDM sanitation contracts under construction per quarter | 2 |  | 2 ZDM sanitation contracts under construction per quarter |  |  | 2 ZDM sanitation contracts under construction per quarter |  |  | 3 ZDM sanitation contracts under construction per quarter |  |  | 2 ZDM sanitation contracts under construction by 30 June 2022 |  | Quarterly |  |  | Planning services | Achieved |  |  | Contracts list or Progress reports and Appointment letters for service providers
| 5 | Number of ZDM water contracts completed per quarter | Number | N/A |  |  | 4 ZDM water contracts completed per quarter | Q4 |  | 1 ZDM water contract completed per quarter |  |  | 5 ZDM water contracts completed per quarter |  |  | 5 ZDM water contracts completed per quarter |  |  | 15 ZDM water contracts completed by 30 June 2022 |  | Quarterly |  |  | Planning services | Q4 |  |  | Certificate of completion
| 6 | Percentage of ZDM Water determinants that pass laboratory tests per quarter | Percentage | N/A |  |  | 85% ZDM Water determinants that pass laboratory tests per quarter | 97% |  | 85% ZDM Water determinants that pass laboratory tests per quarter |  |  | 85% ZDM Water determinants that pass laboratory tests per quarter |  |  | 85% ZDM Water determinants that pass laboratory tests per quarter |  |  | 85% ZDM Water determinants that pass laboratory tests by 30 June 2022 |  | Quarterly |  |  | Technical Services | Achieved |  |  | Lab results
| 7 | The average time taken to fix spillages per quarter | Hours | N/A |  |  | 48Hrs average time taken to fix spillages per quarter | 31Hrs |  | 48Hrs average time taken to fix spillages per quarter |  |  | 48Hrs average time taken to fix spillages per quarter |  |  | 48Hrs average time taken to fix spillages per quarter |  |  | 48Hrs average time taken to fix spillages by 30 June 2022 |  | Quarterly |  |  | Technical Services | Not Achieved |  |  | Job card summary report
Establishing and maintaining partnerships with government and private sector to accelerate provision of universal, equitable & consistent access to the municipal services that local communities are entitled to. | 8 | Number of households within ZDM to be provided with access to water within RDP standard | Number | N/A | SO 1.2.1 |  | N/A | 0 | Appointment letters | N/A |  |  | 600 households within ZDM to be provided with access to water within RDP standard |  |  | 300 households within ZDM to be provided with access to water within RDP standard |  |  | 900 households within ZDM to be provided with access to water within RDP standard by 30 June 2022 |  | 30 Jun 22 |  |  | Planning Services | Not Achieved | Finalization of SCM processes |  | List of beneficiaries and GPS co-ordinates
| 9 | Number of households within ZDM to be provided with sanitation facilities within RDP standard per quarter | Number | N/A |  |  | 538 households within ZDM to be provided with sanitation facilities within RDP standard per quarter | 796 |  | 900 households within ZDM to be provided with sanitation facilities within RDP standard per quarter |  |  | 346 households within ZDM to be provided with sanitation facilities within RDP standard per quarter |  |  | 485 households within ZDM to be provided with sanitation facilities within RDP standard per quarter |  |  | 1537 households within ZDM to be provided with sanitation facilities within RDP standard by 30 June 2022 |  | Quarterly |  |  | Planning Services | Achieved |  |  | List of beneficiaries and GPS co-ordinates
| 10 | Number of report on evaluation of ZDM water service provider (consultants) performed and submitted to General Manager: Planning Services per quarter | Number | N/A |  |  | 1 report on evaluation of ZDM water service provider (consultants) performed and submitted to General Manager: Planning Services per quarter | 1 |  | 1 report on evaluation of ZDM water service provider (consultants) performed and submitted to General Manager: Planning Services per quarter |  |  | 1 report on evaluation of ZDM water service provider (consultants) performed and submitted to General Manager: Planning Services per quarter |  |  | 1 report on evaluation of ZDM water service provider (consultants) performed and submitted to General Manager: Planning Services per quarter |  |  | 4 report on evaluation of ZDM water service provider (consultants) performed and submitted to General Manager: Planning Services by 30 Jun 2022 |  | Quarterly | Internal | Achieved | Evaluation report and Proof of submission |  | Evaluation report and Proof of submission
| 14 | The average time taken to fix pipeline blockages within ZDM per quarter |  | N/A |  |  | 24 hrs average time taken to fix pipeline blockages within ZDM per quarter | 3Hrs |  | 24 hrs average time taken to fix pipeline blockages within ZDM per quarter |  |  | 24 hrs average time taken to fix pipeline blockages within ZDM per quarter |  |  | 24 hrs average time taken to fix pipeline blockages within ZDM per quarter |  |  | 24 hrs average time taken to fix pipeline blockages within ZDM per quarter |  | Quarterly |  |  | Technical Services | Achieved |  |  | Job cards summary report
KPA 02 - MUNICIPAL TRANSFORMATION AND ORGANIZATIONAL DEVELOPMENT
Strategic Objective(SO) | KPI No. | Key Performance Indicator | Unit of Measure | Formula | IDP Strategic Objective Ref No. | Baseline | Target Q1 30 Sep 2021 | Actual Q 1 30 Sep 2021 | POE | Target Q2 31 Dec 2021 | Actual Q2 31 Dec 2021 | POE | Target Q3 31 Mar 2022 | Actual Q3 31 Mar 2022 | POE | Target Q4 30 JUNE 2022 | Actual Q4 | POE | Annual Target 01 July 2021 - 30 June 2022 | Actual Annual 01 July 2021 - 30 June 2022 | target date / reporting frequency |  |  | Responsible Department | STATUS | REASON FOR VIARIANCE | MEASURES TAKEN TO IMPROVE PERFORMANCE | Portfolio of Evidence
Investing in a workforce to meet service delivery demand through implementing a culture of continuous learning and improvement | 11 | Number of students trained in music within ZDM annually | Number | N/A | SO 5.1.1 |  | N/A | Q 4 |  | N/A |  |  | N/A |  |  | 8 Students trained in music within ZDM by 30 June 2022 |  |  | 8 Students trained in music within ZDM by 30 June 2022 |  | 30-Jun-22 |  |  | Community Services | Q 4 |  |  | Graduation ceremony list
Monitor, review and progressively improve service delivery performance through improvement of business processes and systems, performance auditing, risk management and oversight | 12 | Date ZDM Local Economic Development strategy is adopted by the council by 30 June 2022 | Date | N/A | SO 5.1.4 |  | N/A | Q4 |  | N/A |  |  | N/A |  |  | ZDM Local Economic Development strategy is adopted by 30 June 2022 |  |  | ZDM Local Economic Development strategy is adopted by 30 June 2022 |  | 30-Jun-22 |  |  | Community Services | Q 4 |  |  | Council Resolution and LED Strategy
| 13 | Number of MRRT meetings conducted per quarter | Number | N/A |  |  | 1 MRRT meeting conducted per quarter | 0 |  | 1 MRRT meeting conducted per quarter |  |  | 1 MRRT meeting conducted per quarter |  |  | 1 MRRT meeting conducted per quarter |  |  | 4 MRRT meetings conducted by 30 June 2022 |  | Quarterly |  |  | Community Services | Not Achieved | The meeting did not sit due to network problem | We will arrange physical meeting in the next quarter | Notice, Agenda, Minutes and attendance register
| 14 | Date Indonsa Arts & Craft Centre business strategy is adopted by the council | Date | N/A |  |  | N/A | Q 4 |  | N/A |  |  | N/A |  |  | Indonsa Arts & craft centre business strategy is adopted by 30 June 2022 |  |  | Indonsa Arts & craft centre business strategy is adopted by 30 June 2022 |  | 30-Jun-22 |  |  | Community Services | Q 4 |  |  | Council Resolution and Indonsa Arts and craft centre business strategy
| 15 | Date revised ZDM internal audit charter adopted by Audit committee | Date | N/A |  |  | N/A | 2021-08-20 |  | N/A |  |  | N/A |  |  | Revised ZDM internal audit charter adopted by Audit committee by 30 June 2022 |  |  | Revised ZDM internal audit charter adopted by Audit committee by 30 June 2022 |  | 30 Jun 22 |  |  | OMM | Achieved |  |  | Copy of Internal Audit Charter and Audit Committee minutes
| 16 | Number of Quarterly SDBIP reports submitted to Internal Audit per quarter | Number | N/A |  |  | 1 Quarterly SDBIP report submitted to Internal Audit per quarter | 08 Jun 21 |  | 1 Quarterly SDBIP report submitted to Internal Audit per quarter |  |  | 1 Quarterly SDBIP report submitted to Internal Audit per quarter |  |  | 1 Quarterly SDBIP report submitted to Internal Audit per quarter |  |  | 4 Quarterly SDBIP reports submitted to Internal Audit by 30 June 2022 |  | Quarterly |  |  | OMM | Achieved |  |  | Attendance Register; Assessment report and signed scoring sheets
Investing in a workforce to meet service delivery demand through implementing a culture of continuous learning and improvement | 17 | Number of students within ZDM trained in visual art annually | Number | N/A | SO 5.1.1 |  | N/A | Q4 |  | N/A |  |  | N/A |  |  | 10 students within ZDM trained in visual art by 30 June 2022 |  |  | 10 students within ZDM trained in visual art by 30 June 2022 |  | 2022-06-30 |  |  | Community Services | Q4 |  |  | Graduation ceremony list
| 18 | Number of students within ZDM trained in fashion design annually | Number | N/A |  |  | N/A | Q4 |  | N/A |  |  | N/A |  |  | 15 students within ZDM trained in fashion design by 30 June 2022 |  |  | 15 students within ZDM trained in fashion design by 30 June 2022 |  | 2022-06-30 |  |  | Community Services | Q4 |  |  | Graduation ceremony list
Optimise workforce productivity by enforcing a sound organizational culture | 19 | Date Internal Audit Plan 2021/2022 submitted to Audit Committee for adoption | Date | N/A | SO 5.1.3 | NEW KPI | Internal Audit Plan 2021/2022 submitted to Audit Committee for adoption by 30 Sept 2022 | 2021-08-20 |  | N/A |  |  | N/A |  |  | N/A |  |  | Internal Audit Plan 2021/2022 submitted to Audit Committee for adoption by 30 Sept 2022 |  | 31-Dec-21 |  |  | OMM | Achieved |  |  | Internal Audit Plan and Audit Committee minutes
| 20 | Number of Internal Audit reports submitted to the Audit committee per quarter | Number | N/A |  |  | 1 Internal Audit reports submitted to the Audit committee per quarter | 3 |  | 1 Internal Audit reports submitted to the Audit committee per quarter |  |  | 1 Internal Audit reports submitted to the Audit committee per quarter |  |  | 1 Internal Audit reports submitted to the Audit committee per quarter |  |  | 4 Internal Audit reports submitted to the Audit committee by 30 June 2022 |  | Quarterly |  |  | OMM | Achieved |  |  | IA reports and Audit Committee minutes
| 21 | Date ZDM Service Delivery Charter adopted by council | Date | N/A |  | To be confirmed | N/A | Q4 |  | N/A |  |  | N/A |  |  | ZDM Service Delivery Charter adopted council by 30 June 2022 |  |  | ZDM Service Delivery Charter adopted council by 30 June 2022 |  | 2022-06-30 |  |  | Corporate Service | Q4 |  |  | Council resolution and Copy of Service delivery Charter
| 22 | Number of Audit Committee meetings coordinated per quarter | Number | N/A |  |  | 1 Audit committee meetings coordinated per quarter | 3 |  | 1 Audit committee meetings coordinated per quarter |  |  | 1 Audit committee meetings coordinated per quarter |  |  | 1 Audit committee meetings coordinated per quarter |  |  | 4 Audit committee meetings coordinated by 30 June 2022 |  | Quarterly |  |  | OMM | Achieved |  |  | Notice, Agenda, Minutes and attendance register
Monitor, review and progressively improve service delivery performance through improvement of business processes and systems, performance auditing, risk management and oversight | 23 | Date employment equity plan reports submitted to Department of Labour | Date | N/A | SO 5.1.4 |  | N/A | Q3 |  | N/A |  |  | Employment equity plan reports submitted to Department of Labour by 15 Jan 2022 |  |  | N/A |  |  | Employment equity plan reports submitted to Department of Labour by 15 Jan 2022 |  | 2022-01-15 |  |  | Corporate Services | Q3 |  |  | Proof of submission and copy of employment equity plan report
| 24 | Number of policy workshops conducted for ZDM employees per quarter | Number | N/A |  |  | 1 policy workshops conducted for ZDM employees per quarter | 1 |  | 1 policy workshops conducted for ZDM employees per quarter |  |  | 1 policy workshops conducted for ZDM employees per quarter |  |  | 1 policy workshops conducted for ZDM employees per quarter |  |  | 4 policy workshops conducted for ZDM employees by 30 June 2022 |  | Quarterly |  |  | Corporate Services | Achieved |  |  | Notice, Attendance Register and copy of presentations made
| 25 | Number of ZDM employees trained on Batho Pele principles per quarter | Number | N/A |  | To be confirmed | 30 ZDM employees trained on Batho Pele principles per quarter | 126 |  | 30 ZDM employees trained on Batho Pele principles per quarter |  |  | 30 ZDM employees trained on Batho Pele principles per quarter |  |  | 30 ZDM employees trained on Batho Pele principles per quarter |  |  | 120 ZDM employees trained on Batho Pele principles by 30 June 2022 |  | Quarterly |  |  | Corporate services | Achieved |  |  | Notice, Attendance Register and copy of presentations made
| 26 | Date employment equity plan reports submitted to Council | Date | N/A |  |  | N/A | Q2 |  | 1 employment equity report submitted to council by 31 Dec 2021 |  |  | N/A |  |  | N/A |  |  | 1 employment equity report submitted to council by 31 Dec 2021 |  | 2021-12-31 |  |  | Corporate Services | Q2 |  |  | Council resolution and Employment equity Plan
| 27 | Number workshops conducted on labour relations matters to ZDM employees per quarter | Number | N/A |  |  | 1 workshops conducted on labour relations matters to ZDM employees per quarter | 1 |  | 1 workshops conducted on labour relations matters to ZDM employees per quarter |  |  | 1 workshops conducted on labour relations matters to ZDM employees per quarter |  |  | 1 workshops conducted on labour relations matters to ZDM employees per quarter |  |  | 4 workshops conducted on labour relations matters to ZDM employees by 30 June 2022 |  | Quarterly |  |  | Corporate Services | Achieved |  |  | Notice, Attendance Register and copy of presentations made
| 28 | Date 2022/2023 ZDM organogram approved by council | Date | N/A |  |  | N/A | Q4 |  | N/A |  |  | N/A |  |  | 2022/2023 ZDM organogram approved by council by 30 June 2022 |  |  | 2022/2023 ZDM organogram approved by council by 30 June 2022 |  | 2022-06-30 |  |  | Corporate Services | Q4 |  |  | Council Resolution and organogram
KPA 03 - MUNICIPAL FINANCIAL VIABILITY AND MANAGEMENT
Strategic Objective(SO) | KPI No. | Key Performance Indicator | Unit of Measure | Formula | Responsible Department | Baseline | Target Q1 30 Sep 2021 | Actual Q 1 30 Sep 2021 | POE | Target Q2 31 Dec 2021 | Actual Q2 31 Dec 2021 | POE | Target Q3 31 Mar 2022 | Actual Q3 31 Mar 2022 | POE | Target Q4 30 June 2022 | Actual Q4 30 June 2022 | POE | Annual Target 01 July 2021 - 30 June 2022 | Actual Annual 01 July 2021 - 30 June 2022 | target date / reporting frequency |  |  | Responsible Department | STATUS | REASON FOR VIARIANCE | MEASURES TAKEN TO IMPROVE PERFORMANCE | Portfolio of Evidence
Establish and maintain a sound and sustainable management of the fiscal and financial affairs of the municipality and its entities. | 29 | Date Submission of Sec 54 (f) Mid Year Budget & Performance Assessment to the Council | Date | N/A | SO 3.1.1 |  | N/A | Q3 |  | N/A |  |  | Submission of Sec 54(f) Mid Year Budget & Performance Assessment to the Council by 31 January 2022 |  |  | N/A |  |  | Submission of Sec 54(f) Mid Year Budget &Performance Assessment to the Council by 31 January 2022 |  | 2022-01-31 |  |  | All | Q3 |  |  | Council resolution and Copy of Sec 54 Mid Year Budget & Performance Assessment
| 30 | Percentage of disconnections implemented to identified non-paying ZDM customers per quarter | Percentage | N/A |  |  | 100% disconnections implemented to identified non-paying ZDM customers per quarter | 63% |  | 100% disconnections implemented to identified non-paying ZDM customers per quarter |  |  | 100% disconnections implemented to identified non-paying ZDM customers per quarter |  |  | 100% disconnections implemented to identified non-paying ZDM customers per quarter |  |  | 100% disconnections implemented to identified non-paying ZDM customers by 30 June 2022 |  | Quarterly |  |  | Budget & Treasury | Not achieved |  |  | Disconnection report and debtors age analysis report
| 31 | Date adjustment Budget submitted to council | Date | N/A |  |  | N/A | Q3 |  | N/A |  |  | Adjustment Budget submitted to council by 28 Feb 2022 |  |  | N/A |  |  | Adjustment Budget submitted to council by 28 February 2022 |  | 28-Feb-2022 |  |  | Budget & Treasury | Q3 |  |  | Council Resolution and copy of adjustment Budget
| 38 | Date MFMA 54(1) Submission of Sec 72 Mid Year Performance Assessment to Council | Date | N/A |  |  | N/A | Q3 |  | N/A |  |  | MFMA 54(1) Submission of Sec 72 Mid Year Performance Assessment to Council by 31 Jan 2022 |  |  | N/A |  |  | MFMA 54(1) Submission of Sec 72 Mid Year Performance Assessment to Council by 31 Jan 2022 |  | 31-Jan-22 |  |  | Budget & Treasury | Q3 |  |  | Council Resolution and Copy of Sec 72 Report
| 32 | Number of reports on Irregular Expenditure submitted to council per quarter | Number | N/A |  |  | 1 report on Irregular Expenditure submitted to council per quarter | 0 |  | 1 report on Irregular Expenditure submitted to council per quarter |  |  | 1 report on Irregular Expenditure submitted to council per quarter |  |  | 1 report on Irregular Expenditure submitted to council per quarter |  |  | 4 reports on Irregular Expenditure submitted to council by 30 June 2022 |  | Quarterly |  |  | Budget & Treasury | Not achieved |  |  | Council resolution and Copy of Irregular Expenditure Report
| 33 | Date consolidated procurement plan submitted to MANCO | Date | N/A |  |  | Consolidated procurement plan submitted to MANCO by 31 Aug 2021 | 0 |  | N/A |  |  | N/A |  |  | N/A |  |  | Consolidated procurement plan submitted to MANCO by 31 Aug 2021 |  | 31-Aug-21 |  |  | Budget & Treasury | Not achieved |  |  | Copy of consolidated procurement plan and proof of submission
Refine procurement systems and processes to respond to the demand for services | 34 | Number of SCM quarterly reports submitted to EXCO per quarter | Number | N/A | SO 3.1.4 |  | 1 SCM quarterly report submitted to EXCO per quarter |  |  | 1 SCM quarterly report submitted to EXCO per quarter |  |  | 1 SCM quarterly report submitted to EXCO per quarter |  |  | 1 SCM quarterly report submitted to EXCO per quarter |  |  | 4 SCM quarterly reports submitted to EXCO by 30 June 2022 |  | Quarterly |  |  | Budget & Treasury | Not achieved |  |  | Proof of submission and Copy of SCM Quarterly reports
Manage, monitor and review existing financial systems to support accurate and credible reporting, budget monitoring and compliance | 35 | Date verification report on ZDM movable assets submitted to Finance Portfolio committee | Date | N/A | SO 3.1.3 |  | N/A | 0 |  | N/A |  |  | N/A |  |  | Verification reports on ZDM movable assets conducted by 30 June 2022 |  |  | Verification reports on ZDM movable assets conducted by 30 June 2022 |  | 30 Jun 2022 |  |  | Budget & Treasury | Not achieved |  |  | Copy of Verification report on ZDM movable assets
| 36 | Date updates performed on the ZDM municipal fixed assets register | Date | N/A |  |  | N/A | 0 |  | N/A |  |  | N/A |  |  | Updates performed on the ZDM municipal fixed assets register by 30 June 2022 |  |  | Updates performed on the ZDM municipal fixed assets register by 30 June 2022 |  | 30 Jun 2022 |  |  | Budget & Treasury | Not achieved |  |  | Updated FAR
| 37 | Percentage of expenditure on conditional grants per quarter | Percentage | N/A |  |  | 25% expenditure on conditional grants per quarter | Q4 |  | 25% expenditure on conditional grants per quarter |  |  | 25% expenditure on conditional grants per quarter |  |  | 25% expenditure on conditional grants per quarter |  |  | 100% expenditure on conditional grants by 30 June 2022 |  | Quarterly |  |  | Budget & Treasury | Q4 |  |  | Copy of Expenditure report and copy of grant register
| 38 | Percentage of Collection Rate achieved per quarter | Percentage | N/A |  |  | 90% Collection Rate achieved per quarter | 58% |  | 90% Collection Rate achieved per quarter |  |  | 90% Collection Rate achieved per quarter |  |  | 90% Collection Rate achieved per quarter |  |  | 90% Collection Rate achieved by 30 June 2022 |  | Quarterly |  |  | Budget & Treasury | Not achieved |  |  | Copy of Collection Report
KPA 04 - GOOD GOVERNANCE AND PUBLIC PARTICIPATION
Strategic Objective(SO) | KPI No. | Key Performance Indicator | Unit of Measure | Formula | Responsible Department | Baseline | Target Q1 30 Sep 2021 | Actual Q 1 30 Sep 2021 | POE | Target Q2 31 Dec 2021 | Actual Q2 31 Dec 2021 | POE | Target Q3 31 Mar 2022 | Actual Q3 31 Mar 2022 | POE | Target Q4 30 June 2022 | Actual Q4 30 June 2022 | POE | Annual Target 01 July 2021 - 30 June 2022 | Actual Annual 01 July 2021 - 30 June 2022 | target date / reporting frequency |  |  | Responsible Department | STATUS | REASON FOR VIARIANCE | MEASURES TAKEN TO IMPROVE PERFORMANCE | Portfolio of Evidence
Promoting transparent and accountable governance through regular community engagements and effective administration. | 39 | Number of LED awareness events held to market ZDM municipal programmes per quarter | Number | N/A | SO 4.1.2 |  | 1 LED awareness event held to market ZDM municipal programmes per quarter | 1 |  | 1 LED awareness event held to market ZDM municipal programmes per quarter |  |  | 1 LED awareness event held to market ZDM municipal programmes per quarter |  |  | 1 LED awareness event held to market ZDM municipal programmes per quarter |  |  | 4 LED awareness events held to market ZDM municipal programmes by 30 June 2022 |  | Quarterly |  |  | Community Services | Achieved |  |  | OOP and Attendance Register
| 40 | Number of ZDM Municipal Health awareness campaigns conducted per quarter | Number | N/A |  |  | 1 ZDM Municipal Health awareness campaign conducted per quarter | 2 |  | 1 ZDM Municipal Health awareness campaign conducted per quarter |  |  | 1 ZDM Municipal Health awareness campaign conducted per quarter |  |  | 1 ZDM Municipal Health awareness campaign conducted per quarter |  |  | 4 ZDM Municipal Health awareness campaigns conducted by 30 June 2022 |  | Quarterly |  |  | Community Services | Achieved |  |  | OOP and Attendance Register
| 41 | Number of ZDM disaster awareness campaigns held | Number | N/A |  |  | 1 ZDM disaster awareness campaign held per quarter | 1 |  | 1 ZDM disaster awareness campaign held per quarter |  |  | 1 ZDM disaster awareness campaign held per quarter |  |  | 1 ZDM disaster awareness campaign held per quarter |  |  | 4 ZDM disaster awareness campaigns held by 30 June 2022 |  | Quarterly |  |  | Corporate Services | Achieved |  |  | OOP and Attendance Register
| 42 | Number of funeral parlours inspected within ZDM per quarter | Number | N/A |  |  | 12 funeral parlours inspected within ZDM per quarter | 18 |  | 12 funeral parlours inspected within ZDM per quarter |  |  | 12 funeral parlours inspected within ZDM per quarter |  |  | 12 funeral parlours inspected within ZDM per quarter |  |  | 48 funeral parlours inspected within ZDM by 30 June 2022 |  | Quarterly |  |  | Community Services | Achieved |  |  | Summary of Inspection Register
| 43 | Number of water samples within ZDM collected for independent laboratory testing per quarter | Number | N/A |  |  | 15 water samples within ZDM collected for independent laboratory testing per quarter | 18 |  | 15 water samples within ZDM collected for independent laboratory testing per quarter |  |  | 15 water samples within ZDM collected for independent laboratory testing per quarter |  |  | 15 water samples within ZDM collected for independent laboratory testing per quarter |  |  | 60 water samples within ZDM collected for independent laboratory testing by 30 June 2022 |  | Quarterly |  |  | Community Service | Achieved |  |  | Copy of Lab results
| 44 | Number of food premises inspected within ZDM per quarter | Number | N/A |  |  | 45 food premises inspected within ZDM per quarter | 61 |  | 45 food premises inspected within ZDM per quarter |  |  | 45 food premises inspected within ZDM per quarter |  |  | 45 food premises inspected within ZDM per quarter |  |  | 180 food premises inspected within ZDM by 30 June 2022 |  | Quarterly |  |  | Community Services | Achieved |  |  | Summary of Inspection Register
| 45 | Number of food samples within ZDM collected for independent laboratory testing per quarter | Number |  |  |  | 15 food samples within ZDM collected for independent laboratory testing per quarter | 14 |  | 15 food samples within ZDM collected for independent laboratory testing per quarter |  |  | 15 food samples within ZDM collected for independent laboratory testing per quarter |  |  | 15 food samples within ZDM collected for independent laboratory testing per quarter |  |  | 60 food samples within ZDM collected for independent laboratory testing by 30 June 2022 |  | Quarterly |  |  | Community Services | Not Achieved |  |  | Copy of Lab Results
| 46 | Number of District monthly statistics reports submitted to Provincial Department of Health per quarter | Number | N/A |  |  | 3 District monthly statistics reports submitted to Provincial Department of Health per quarter | 9 |  | 3 District monthly statistics reports submitted to Provincial Department of Health per quarter |  |  | 3 District monthly statistics reports submitted to Provincial Department of Health per quarter |  |  | 3 District monthly statistics reports submitted to Provincial Department of Health per quarter |  |  | 12 District monthly statistics reports submitted to Provincial Department of Health by 30 June 2022 |  | Quarterly |  |  | Community Services | Achieved | DoH requires these reports monthly per LM within DM, KPI will be amended during adjustment period |  | Proof of Submission and soft copy of district monthly statistics report
Systematic development and or review and monitoring implementation of all municipal policies, bylaws, strategies, plans and frameworks in line with any applicable legislation | 47 | Date 2021/2022 IDP Process Plan including Budget time table submitted to Council | Date | N/A | SO 4.1.4 |  | 2021/2022 IDP Process Plan including Budget time table submitted Council by 31-Aug-22 | 2021-08-25 |  | N/A |  |  | N/A |  |  | N/A |  |  | 2021/2022 IDP Process Plan including Budget time table submitted Council by 31-Aug-22 |  | 31-Aug-22 |  |  | Budget & Treasury and Planning Services | Achieved |  |  | Council Resolution and copy of IDP Process Plan including Budget time table
| 48 | Date Final Budget approved by Council | Date | N/A |  |  | N/A | Q4 |  | N/A |  |  | N/A |  |  | Final Budget approved by Council by 31 May 2022 |  |  | Final Budget approved by Council by 31 May 2022 |  | 31-May-22 |  |  | Budget & Treasury | Q4 |  |  | Council Resolution and copy of approved budget
| 49 | Number of integrated grant expenditure reports submitted to the Department of Public Works per quarter | Number | N/A |  |  | 3 integrated grant expenditure reports submitted to the Department of Public Works per quarter | 3 |  | 3 integrated grant expenditure reports submitted to the Department of Public Works per quarter |  |  | 3 integrated grant expenditure reports submitted to the Department of Public Works per quarter |  |  | 3 integrated grant expenditure reports submitted to the Department of Public Works per quarter |  |  | 12 integrated grant expenditure reports submitted to the Department of Public Works by 30 June 2022 |  | Quarterly |  |  | Community service | Achieved |  |  | Acknowledgment of receipts and copies of expenditure reports
| 50 | Date WSP report submitted to LGSETA | Date | N/A |  | new KPI | N/A | Q4 |  | N/A |  |  | N/A |  |  | WSP report submitted to LGSETA by 30 June 2022 |  |  | WSP report submitted to LGSETA by 30 June 2022 |  | 2022-06-30 |  |  | Corporate services | Q4 |  |  | Copy of WSP Report and Proof of submission
| 51 | Date of Submission of Sec 72 Mid - Year Budget & Performance Assessment to the Mayor & Provincial Treasury | Date | N/A |  |  | N/A | Q3 |  | N/A |  |  | Submission of Sec 72 Mid - Year Budget & Performance Assessment to the Mayor & Provincial Treasury by 25 January 2022 |  |  | N/A |  |  | Submission of Sec 72 Mid - Year Budget & Performance Assessment to the Mayor & Provincial Treasury by 25 January 2022 |  | 2022-01-25 |  |  | Budget & Treasury | Q3 |  |  | Proof of submission and copy of Sec72 Mid - Year Budget & Performance Assessment
Promoting transparent and accountable governance through regular community engagements | 52 | Number of ZDM District Civil Society Forum held per quarter | Number | N/A | SO 4.1.2 | new KPI | 1 ZDM District Civil Society Forum held per quarter | 1 |  | 1 ZDM District Civil Society Forum held per quarter |  |  | 1 ZDM District Civil Society Forum held per quarter |  |  | 1 ZDM District Civil Society Forum held per quarter |  |  | 4 ZDM District Civil Society Forum held by 30 June 2022 |  | Quarterly |  |  | Community Services | Achieved |  |  | Notice, Agenda, Minutes and attendance register
| 53 | Number of monthly budget statements (Sec 71 reports) submitted to Mayor and Provincial Treasury per quarter | Number | N/A |  |  | 3 monthly budget statements (Sec 71 reports) submitted to Mayor and Provincial Treasury per quarter | 3 |  | 3 monthly budget statements (Sec 71 reports) submitted to Mayor and Provincial Treasury per quarter |  |  | 3 monthly budget statements (Sec 71 reports) submitted to Mayor and Provincial Treasury per quarter |  |  | 3 monthly budget statements (Sec 71 reports) submitted to Mayor and Provincial Treasury per quarter |  |  | 12 monthly budget statements (Sec 71 reports) submitted to Mayor and Provincial Treasury by 30 June 2022 |  | Quarterly |  |  | Budget & Treasury | Achieved |  |  | Proof of submission and soft copy of Sec 71 report
| 54 | Date AFS submitted to AG | Date | N/A |  |  | AFS submitted to AG by 31 Aug 2021 | 2021-08-31 |  | N/A |  |  | N/A |  |  | N/A |  |  | AFS submitted to AG by 31 Aug 2021 |  | 2021-08-31 |  |  | Budget & Treasury | Achieved |  |  | Proof of submission and copy of AFS
| 55 | Number of MSCOA data strings uploaded to Local Government portal per quarter | Number | N/A |  |  | 3 MSCOA data strings uploaded to Local Government portal per quarter | 3 |  | 3 MSCOA data strings uploaded to Local Government portal per quarter |  |  | 3 MSCOA data strings uploaded to Local Government portal per quarter |  |  | 3 MSCOA data strings uploaded to Local Government portal per quarter |  |  | 12 MSCOA data strings uploaded to Local Government portal by 30 June 2022 |  | Quarterly |  |  | Budget & Treasury | Achieved |  |  | Print screen of system upload and copy of data strings
| 56 | Number of Sec 52 reports submitted to Council per quarter | Number | N/A |  |  | 1 Sec 52 report submitted to Council per quarter (previous quarter) | 0 |  | 1 Sec 52 report submitted to Council per quarter (previous quarter) |  |  | 1 Sec 52 report submitted to Council per quarter (previous quarter) |  |  | 1 Sec 52 report submitted to Council per quarter (previous quarter) |  |  | 4 Sec 52 reports submitted to Council by 30 June 2022 |  | Quarterly |  |  | Budget & Treasury | Not Achieved |  |  | Proof of submission and copy of Sec 52 report
| 57 | Number of Sec 66 reports submitted to Council per quarter | Number | N/A |  |  | 3 Sec 66 reports submitted to Council per quarter (previous quarter) | Refer to Sec 71 |  | 3 Sec 66 reports submitted to Council per quarter (previous quarter) |  |  | 3 Sec 66 reports submitted to Council per quarter (previous quarter) |  |  | 3 Sec 66 reports submitted to Council per quarter (previous quarter) |  |  | 12 Sec 66 reports submitted to Council by 30 June 2022 |  | Quarterly |  |  | Budget & Treasury | Not Achieved |  |  | Proof of submission and copy of Sec 66 report
| 58 | Number of Municipal Manager Technical IGR/DDM meetings coordinated per quarter | Number | N/A |  | NEW KPI | 1 Municipal Manager Technical IGR/DDM meetings coordinated per quarter | 3 |  | 1 Municipal Manager Technical IGR/DDM meetings coordinated per quarter |  |  | 1 Municipal Manager Technical IGR/DDM meetings coordinated per quarter |  |  | 1 Municipal Manager Technical IGR/DDM meetings coordinated per quarter |  |  | 4 Municipal Manager Technical IGR/DDM meetings coordinated by 30 June 2022 |  | Quarterly |  |  | OMM | Achieved |  |  | Notice, Agenda, Minutes and Attendance Register
| 59 | Date WSIG and RBIG Annual Implementation Plan submitted to Department of Water and Sanitation | Date |  |  |  | N/A | 2021-07-28 |  | N/A |  |  | N/A |  |  | WSIG and RBIG Annual Implementation Plan submitted to Department of Water and Sanitation by 15 Jun 2022 |  |  | WSIG and RBIG Annual Implementation Plan submitted to Department of Water and Sanitation by 15 Jun 2022 |  | 2022-06-15 | Internal |  | Planning Services | Achieved | Due in Q4, over achieved |  | Proof of Submission and copy of WSIG and RBIG Annual Implementation Plan report
| 60 | Date PMU Business Plan submitted to KZN-COGTA | Date |  |  |  | N/A | 2021-08-03 |  | N/A |  |  | N/A |  |  | PMU Business Plan submitted to KZN-COGTA by 30 April 2022 |  |  | PMU Business Plan submitted to KZN-COGTA by 30 April 2022 |  | 2022-04-30 | Internal |  | Planning Services | Achieved |  |  | Proof of Submission and copy of PMU Business Plan report
| 61 | Date Three Year Proforma Implementation Plan submitted to KZN-COGTA | Date |  |  |  | N/A | Q3 |  | N/A |  |  | Three Year Proforma Implementation Plan submitted to KZN-COGTA by 30 January 2022 |  |  | N/A |  |  | Three Year Proforma Implementation Plan submitted to KZN-COGTA by 30 January 2022 |  | 2022-01-30 | Internal |  | Planning Services | Q3 |  |  | Proof of Submission and copy of three year proforma Implementation plan
| 62 | Number of MIG Claims uploads onto MIG MIS and submission of the MIG Expenditure and Commitments Schedule [MECS] to KZN-COGTA per quarter | Number |  |  |  | 3 MIG Claims uploads onto MIG MIS and submission of the MIG Expenditure and Commitments Schedule [MECS] to KZN-COGTA per quarter | 3 |  | 3 MIG Claims uploads onto MIG MIS and submission of the MIG Expenditure and Commitments Schedule [MECS] to KZN-COGTA per quarter |  |  | 3 MIG Claims uploads onto MIG MIS and submission of the MIG Expenditure and Commitments Schedule [MECS] to KZN-COGTA per quarter |  |  | 3 MIG Claims uploads onto MIG MIS and submission of the MIG Expenditure and Commitments Schedule [MECS] to KZN-COGTA per quarter |  |  | 12 MIG Claims uploads onto MIG MIS and submission of the MIG Expenditure and Commitments Schedule [MECS] to KZN-COGTA by 30 June 2022 |  | Quarterly |  |  | Planning Services | Achieved |  |  | Print screen of system upload
| 63 | Number of WSIG and RBIG QPE Reports submitted to Department of Water & Sanitation per quarter | Number |  |  |  | 1 WSIG and RBIG QPE Report submitted to DWS per quarter | 1 |  | 1 WSIG and RBIG QPE Report submitted to DWS per quarter |  |  | 1 WSIG and RBIG QPE Report submitted to DWS per quarter |  |  | 1 WSIG and RBIG QPE Report submitted to DWS per quarter |  |  | 4 WSIG and RBIG QPE Reports submitted to DWS by 30 June 2022 |  | Quarterly |  |  | Planning Services | Achieved |  |  | Proof of Submission and copy of report
| 64 | Date MIG Annual Performance Evaluation Report submitted to KZN-COGTA | Date |  |  |  | MIG Annual Performance Evaluation Report submitted to KZN-COGTA by 25 Sept 2021 | 2021-10-08 |  | N/A |  |  | N/A |  |  | N/A |  |  | MIG Annual Performance Evaluation Report submitted to COGTA by 25 Sept 2021 |  | 2021-09-25 |  |  | Planning Services | Not Achieved |  |  | Proof of Submission and copy of MIG Annual Performance Evaluation Report
| 65 | Number of MIG Expenditure Proof of Payments to KZN-COGTA on MIG MIS per quarter | Number |  |  |  | 3 MIG Expenditure Proof of Payments to KZN-COGTA on MIG MIS per quarter | 1 |  | 3 MIG Expenditure Proof of Payments to KZN-COGTA on MIG MIS per quarter |  |  | 3 MIG Expenditure Proof of Payments to KZN-COGTA on MIG MIS per quarter |  |  | 3 MIG Expenditure Proof of Payments to KZN-COGTA on MIG MIS per quarter |  |  | 12 MIG Expenditure Proof of Payments to KZN-COGTA on MIG MIS by 30 June 2022 |  | Quarterly |  |  | Planning Services | Not Achieved |  |  | Proof of Submission and proof of payments
| 66 | Number of WSIG and RBIG Monthly Reports (5B) submitted to Department of Water & Sanitation per quarter | Number |  |  |  | 3 WSIG and RBIG Monthly Reports (5B) submitted to Department of Water & Sanitation per quarter | 0 |  | 3 WSIG and RBIG Monthly Reports (5B) submitted to Department of Water & Sanitation per quarter |  |  | 3 WSIG and RBIG Monthly Reports (5B) submitted to Department of Water & Sanitation per quarter |  |  | 3 WSIG and RBIG Monthly Reports (5B) submitted to Department of Water & Sanitation per quarter |  |  | 12 WSIG and RBIG Monthly Reports (5B) submitted to Department of Water & Sanitation per quarter |  | Quarterly |  |  | Planning Services | October |  |  | Proof of Submission and copy WSIG and RBIG monthly report
| 67 | Number of Provincial Council for AIDS (PCA) presentations generated for submission to Office the Premier by ZDM per quarter | Number |  |  |  | 1 Provincial Council for AIDS (PCA) presentation generated for submission to Office the Premier by ZDM per quarter | 1 |  | 1 Provincial Council for AIDS (PCA) presentation generated for submission to Office the Premier by ZDM per quarter |  |  | 1 Provincial Council for AIDS (PCA) presentation generated for submission to Office the Premier by ZDM per quarter |  |  | 1 Provincial Council for AIDS (PCA) presentation generated for submission to Office the Premier by ZDM per quarter |  |  | 4 Provincial Council for AIDS (PCA) presentations generated for submission to Office of Premier by ZDM by 30 June 2022 |  | Quarterly |  |  | Community Services | Achieved |  |  | Copy of PCA presentations and proof submission
| 68 | Number of ZDM EPWP forums conducted per quarter | Number | N/A |  |  | 1 ZDM EPWP forum conducted per quarter | 0 |  | 1 ZDM EPWP forum conducted per quarter |  |  | 1 ZDM EPWP forum conducted per quarter |  |  | 1 ZDM EPWP forum conducted per quarter |  |  | 4 ZDM EPWP forums conducted by 30 June 2022 |  | Quarterly |  |  | Community Services | Not Achieved | The meeting did not sit due to technical issues of the network | Will arrange physical forum meetings | Notice, Agenda, Attendance register and minutes
| 69 | Date of submission of narrative 2020/2021 Annual Report on EPWP to Department of Public Works | Date | N/A |  |  | Submission on narrative 2020/2021 Annual Report on EPWP to Department of Public Works by 15 July 2021 | Q4 |  | N/A |  |  | N/A |  |  | N/A |  |  | Submission on narrative 2020/2021 Annual Report on EPWP to Department of Public Works by 15 July 2021 |  | 15-Jul-21 |  |  | Community Services | Q4 |  |  | Proof of submission and copy of report
| 70 | Date Annual Report adopted by Council | Date | N/A |  |  | N/A | Q3 |  | N/A |  |  | Annual Report adopted by Council by 31 Jan 2022 |  |  | N/A |  |  | Annual Report adopted by Council by 31 Jan 2022 |  | 31-Jan-22 |  |  | Planning Services | Q3 |  |  | Council Resolution and copy of annual report
| 71 | Date final SDBIP 2022/2023 submitted to the Mayor | Date | N/A |  |  | N/A | Q4 |  | N/A |  |  | N/A |  |  | Final SDBIP 2022/2023 submitted to the Mayor by 28 June 2022 |  |  | Final SDBIP 2022/2023 submitted to the Mayor by 28 June 2022 |  | 28-Jun-2022 |  |  | OMM | Q4 |  |  | Proof of Submission and signed SDBIP by Mayor 2022/2023 by the Mayor
Systematic development and or review and monitoring implementation of all municipal policies, bylaws, strategies, plans and frameworks in line with any applicable legislation | 72 | Date Performance Agreements for ZDM Senior Managers submitted to KZN-COGTA | Date | N/A | SO 4.1.4 | NEW KPI | Performance Agreements for ZDM Senior Managers submitted to KZN-COGTA by 14 Aug 2021 | 2021-08-13 |  | N/A |  |  | N/A |  |  | N/A |  |  | Performance Agreements for ZDM Senior Managers submitted to KZN-COGTA by 14 Aug 2021 |  | 2021-08-14 |  |  | OMM | Achieved |  |  | Proof of submission and signed performance agreements
| 73 | Date Performance Agreements for ZDM Senior managers published in print and electronic platforms | Date | N/A |  |  | Performance Agreements for ZDM Senior managers published in print and electronic platforms by 30 August 2021 | 19 & 20 Aug 21 |  | N/A |  |  | N/A |  |  | N/A |  |  | Performance Agreements for ZDM Senior managers published in print and electronic platforms by 30 August 2021 |  | 2021-08-30 |  |  | OMM | Achieved |  |  | Copy of advert and print screen of ZDM website
Promoting transparent and accountable governance through regular community engagements and effective administration | 74 | Date ZDM Annual Performance Report submitted to AG | Date | N/A | SO 4.1.2 |  | ZDM Annual Performance Report submitted to AG by 31 August 2021 | 2021-08-31 |  |  |  |  | N/A |  |  | N/A |  |  | ZDM Annual Performance Report submitted to AG by 31 August 2021 |  | 2021-08-31 |  |  | OMM | Achieved |  |  | Proof of submission and copy of the APR
Systematic development and or review and monitoring implementation of all municipal policies, bylaws, strategies, plans and frameworks in line with any applicable legislation | 75 | Number of MPMR Sec 14 (2)(g) meetings in relation to Audit Committee secretariat services provided per quarter | Number | N/A | SO 4.1.4 |  | 1 MPMR Sec 14 (2)(g) meeting in relation to Audit Committee secretariat services provided held per quarter | 3 |  | 1 MPMR Sec 14 (2)(g) meeting in relation to Audit Committee secretariat services provided held per quarter |  |  | 1 MPMR Sec 14 (2)(g) meeting in relation to Audit Committee secretariat services provided held per quarter |  |  | 1 MPMR Sec 14 (2)(g) meeting in relation to Audit Committee secretariat services provided held per quarter |  |  | 4 MPMR Sec 14 (2)(g) meetings in relation to Audit Committee secretariat services provided held by 30 June 2022 |  | Quarterly |  |  | Corporate Services | Achieved |  |  | Notice, Agenda and attendance register
| 76 | Number of EXCO Meetings coordinated per quarter | Number | N/A |  |  | 1 EXCO Meeting coordinated per quarter | 1 |  | 1 EXCO Meeting coordinated per quarter |  |  | 1 EXCO Meeting coordinated per quarter |  |  | 1 EXCO Meeting coordinated per quarter |  |  | 4 EXCO Meetings coordinated by 30 June 2022 |  | Quarterly |  |  | Corporate Services | Achieved |  |  | Notice, Agenda and attendance register
| 77 | Number of MSA Sec 79 (1) Number of portfolio committee meetings coordinated per quarter | Number | N/A |  | new KPI | 4 MSA Sec 79 (1) portfolio committee meetings coordinated per quarter | 2 |  | 4 MSA Sec 79 (1) portfolio committee meetings coordinated per quarter |  |  | 4 MSA Sec 79 (1) portfolio committee meetings coordinated per quarter |  |  | 4 MSA Sec 79 (1) portfolio committee meetings coordinated per quarter |  |  | 16 MSA Sec 79 (1) portfolio committee meetings coordinated by 30 June 2022 |  | Quarterly | - | - | Corporate Services | Not Achieved | The Portfolio committees could not sit because Council was engaged with APR and AFS | The portfolio committees will sit in the next quarter | Notice, Agenda and attendance register
| 78 | Number of MPAC meetings coordinated per quarter | Number | N/A |  |  | 1 MPAC meeting coordinated per quarter | 1 |  | 1 MPAC meeting coordinated per quarter |  |  | 1 MPAC meeting coordinated per quarter |  |  | 1 MPAC meeting coordinated per quarter |  |  | 4 MPAC meetings coordinated by 30 June 2022 |  | Quarterly |  |  | Corporate Services | Achieved |  |  | Notice, Agenda and attendance register
| 79 | Number of Council Meetings coordinated per quarter | Number | N/A |  | To be confirmed | 1 Council Meeting coordinated per quarter | 1 |  | 1 Council Meeting coordinated per quarter |  |  | 1 Council Meeting coordinated per quarter |  |  | 1 Council Meeting coordinated per quarter |  |  | 4 Council Meetings coordinated by 30 June 2022 |  | Quarterly |  |  | Corporate Services | Achieved |  |  | Notice, Agenda and attendance register
| 80 | Date MSA Sec 11(3)(a) MFMA 16(1), 24(2), 53(1)( c)(i), 62(1)(f), 79(1)(c ) Policies and bylaws submitted to the Council | Date | N/A |  | To be confirmed | N/A | Q4 |  | N/A |  |  | N/A |  |  | MSA Sec 11(3)(a) MFMA 16(1), 24(2), 53(1)( c)(i), 62(1)(f), 79(1)(c ) Policies and bylaws submitted to the Council by 30 June 2022 |  |  | MSA Sec 11(3)(a) MFMA 16(1), 24(2), 53(1)( c)(i), 62(1)(f), 79(1)(c ) Policies and bylaws submitted to the Council by 30 June 2022 |  | 2022-06-30 | - | - | Corporate Services | Q4 |  |  | Council resolutions and copy of polices and bylaws
| 81 | Number of reports submitted to Office of the Premier on Civil Society Forum per quarter | Number | N/A |  |  | 1 report submitted to Office of the Premier on Civil Society Forum per quarter | 1 |  | 1 report submitted to Office of the Premier on Civil Society Forum per quarter |  |  | 1 report submitted to Office of the Premier on Civil Society Forum per quarter |  |  | 1 report submitted to Office of the Premier on Civil Society Forum per quarter |  |  | 1 report submitted to Office of the Premier on Civil Society Forum by 30 June 2022 |  | Quarterly |  |  | Community Services | Not Achieved |  |  | Proof of submission and copy of the report
| 82 | Number of ICT steering committee meetings held per quarter | Number | N/A |  |  | 1 ICT steering committee meeting held per quarter | 1 |  | 1 ICT steering committee meeting held per quarter |  |  | 1 ICT steering committee meeting held per quarter |  |  | 1 ICT steering committee meeting held per quarter |  |  | 4 ICT steering committee meetings held by 30 June 2022 |  | Quarterly |  |  | Corporate Services | Achieved |  |  | Notice, Agenda and attendance register
Promoting transparent and accountable governance through regular community engagements and effective administration | 83 | Number of Tourism Forums held within ZDM per quarter | Number | N/A | SO 4.1.2 |  | 1 Tourism Forum held within ZDM per quarter | 1 |  | 1 Tourism Forum held within ZDM per quarter |  |  | 1 Tourism Forum held within ZDM per quarter |  |  | 1 Tourism Forum held within ZDM per quarter |  |  | 4 Tourism Forums held within ZDM by 30 June 2022 |  | Quarterly |  |  | Community Services | Achieved |  |  | Notice, Agenda and Minutes
| 84 | Number of Quarterly evaluation reports on Integrated grant EPWP submitted to Department of Public Works per quarter | Number | N/A |  | new KPI | 1 Quarterly evaluation report on Integrated grant EPWP submitted to Department of Public Works per quarter | 1 |  | 1 Quarterly evaluation report on Integrated grant EPWP submitted to Department of Public Works per quarter |  |  | 1 Quarterly evaluation report on Integrated grant EPWP submitted to Department of Public Works per quarter |  |  | 1 Quarterly evaluation report on Integrated grant EPWP submitted to Department of Public Works per quarter |  |  | 4 Quarterly evaluation reports on Integrated grant EPWP submitted to Department of Public Works by 30 June 2022 |  | Quarterly |  |  | Community Services | Achieved |  |  | Proof of submission and Quarterly evaluation reports
| 85 | Date draft Budget submitted to Council | Date | N/A |  |  | N/A | Q3 |  | N/A |  |  | Draft Budget submitted to Council by 31 March 2022 |  |  | N/A |  |  | Draft Budget submitted to Council by 31 March 2022 |  | 31 March 2021 |  |  | Budget & Treasury | Q3 |  |  | Council Resolution and copy of the draft budget
| 86 | Date draft budget related policies submitted to Council | Date | N/A |  |  | N/A | Q3 |  | N/A |  |  | Draft budget related policies submitted to Council by 31 March 2022 |  |  | N/A |  |  | Draft budget related policies submitted to Council by 31 March 2022 |  | 31-Mar-22 |  |  | Budget & Treasury | Q3 |  |  | Council Resolution and copy of draft budget related policies
| 87 | Date final budget related policies submitted to Council | Date | N/A |  |  | N/A | Q4 |  | N/A |  |  | N/A |  |  | Final budget related policies submitted to Council by 30 June 2022 |  |  | Final budget related policies submitted to Council by 30 June 2022 |  | 30-Jun-22 |  |  | Budget & Treasury | Q4 |  |  | Council Resolution and copy final budget related policies
| 88 | Number of Sec 11 reports submitted to Council, Provincial Treasury and Auditor General per quarter | Number | N/A |  |  | 1 Sec 11 report submitted to Council, Provincial Treasury and Auditor General per quarter (previous quarter) | 0 |  | 1 Sec 11 report submitted to Council, Provincial Treasury and Auditor General per quarter (previous quarter) |  |  | 1 Sec 11 report submitted to Council, Provincial Treasury and Auditor General per quarter (previous quarter) |  |  | 1 Sec 11 report submitted to Council, Provincial Treasury and Auditor General per quarter (previous quarter) |  |  | 4 Sec 11 reports submitted to Council, Provincial Treasury and Auditor General per quarter (previous quarter) |  | Quarterly |  |  | Budget & Treasury | Not Achieved |  |  | Council Resolution; Proof of submission and copy of Sec 11 reports
Systematic development and or review and monitoring implementation of all municipal policies, bylaws, strategies, plans and frameworks in line with any applicable legislation | 89 | Percentage of tenders finalised within 3 months after date of advertisement per quarter | Percentage | N/A | SO 4.1.4 |  | 100% of tenders finalised within 3 months after date of advertisement per quarter | 0 |  | 100% of tenders finalised within 3 months after date of advertisement per quarter |  |  | 100% of tenders finalised within 3 months after date of advertisement per quarter |  |  | 100% of tenders finalised within 3 months after date of advertisement per quarter |  |  | 100% of tenders finalised within 3 months after date of advertisement by 30 June 2022 |  | Quarterly |  |  | Budget & Treasury | Not Achieved |  |  | Adverts and appointment letters
| 90 | Number of Revenue Steering Committee meetings conducted per quarter | Number | N/A |  |  | 1 Revenue Steering Committee meeting conducted per quarter | 0 |  | 1 Revenue Steering Committee meeting conducted per quarter |  |  | 1 Revenue Steering Committee meeting conducted per quarter |  |  | 1 Revenue Steering Committee meeting conducted per quarter |  |  | 4 Revenue Steering Committee meetings conducted by 30 June 2022 |  | Quarterly |  |  | Budget & Treasury | Not Achieved |  |  | Notice, Agenda, Minutes and Attendance Register
| 91 | Date of ZDM stock taking report performed per quarter | Date | N/A |  |  | N/A | 0 |  | N/A |  |  | N/A |  |  | ZDM stock taking report performed by 30 Jun 2022 |  |  | ZDM stock taking report performed by 30 Jun 2022 |  | 30 Jun 2022 |  |  | Budget & Treasury | Not Achieved |  |  | Copy of Stock taking reports
| 92 | Date reports on Sec 13 of the MFMA submitted to AG | Number | N/A |  |  | Reports on Sec 13 of the MFMA submitted to AG by 31 July 2021 | 0 |  | N/A |  |  | N/A |  |  | N/A |  |  | Reports on Sec 13 of the MFMA submitted to AG by 31 July 2021 |  | 31 July 2021 |  |  | Budget & Treasury | Not Achieved |  |  | Proof of submission and copy of Sec 13 reports
| 93 | Date AG corrective action plan developed | Date | N/A |  |  | N/A | Q4 |  | AG Corrective action plan developed by 31 December 2021 |  |  | N/A |  |  | N/A |  |  | AG Corrective action plan developed by 31 December 2021 |  | 31-Dec-2021 |  |  | OMM | Q4 |  |  | Copy Action Plan
| 94 | Number of reports based on updated Grants Register submitted to Finance Portfolio committee per quarter | Number | N/A |  |  | 3 reports based on updated Grants Register submitted to Finance Portfolio committee per quarter | 1 |  | 3 reports based on updated Grants Register submitted to Finance Portfolio committee per quarter |  |  | 3 reports based on updated Grants Register submitted to Finance Portfolio committee per quarter |  |  | 3 reports based on updated Grants Register submitted to Finance Portfolio committee per quarter |  |  | 12 reports based on updated Grants Register submitted to Finance Portfolio committee by 30 June 2022 |  | Quarterly |  |  | Budget & Treasury | Achieved |  |  | Updated grant register
| 95 | Date AFS unqualified "clean" audit report achieved | Date | N/A |  |  | N/A | Q2 |  | AFS unqualified "clean" audit report achieved by 31 December 2021 |  |  | N/A |  |  | N/A |  |  | AFS unqualified "clean" audit report achieved by 31 December 2021 |  | 31-Dec-2021 |  |  | Budget & Treasury | Q2 |  |  | Audit Report
| 96 | Percentage of resolved issues as per corrective action plan targets | Percentage | N/A |  |  | N/A | Q4 |  | N/A |  |  | N/A |  |  | 100% resolved issues as per corrective action plan targets by 30 June 2022 |  |  | 100% resolved issues as per corrective action plan targets by 30 June 2022 |  | 30-Jun-22 |  |  | Budget & Treasury | Q4 |  |  | Updated action plan
| 97 | Date APR unqualified audit opinion 2020/2021 achieved | Date | N/A |  |  | N/A | Q2 |  | APR unqualified audit opinion 2020/2021 achieved by 31 December 2021 |  |  | N/A |  |  | N/A |  |  | APR unqualified audit opinion 2020/2021 achieved by 31 December 2021 |  | 31-Dec-2021 |  |  | OMM | Q2 |  |  | Audit Report
Promoting transparent and accountable governance through regular community engagements and effective administration | 98 | Date Final 2022/2023 IDP submitted to Council for adoption | Date | N/A |  |  | N/A | Q4 |  | N/A |  |  | N/A |  |  | Final 2022/2023 IDP submitted to Council for adoption by 31 May 2022 |  |  | Final 2022/2023 IDP submitted to Council for adoption by 31 May 2022 |  | 2022-05-31 |  |  | Planning Services | Q4 |  |  | Council Resolution and copy of final IDP
KPA 05 - LOCAL ECONOMIC DEVELOPMENT
Strategic Objective(SO) | KPI No. | Key Performance Indicator | Unit of Measure | Formula | Responsible Department | Baseline | Target Q1 30 Sep 2021 | Actual Q 1 30 Sep 2021 | POE | Target Q2 31 Dec 2021 | Actual Q2 31 Dec 2021 | POE | Target Q3 31 Mar 2022 | Actual Q3 31 Mar 2022 | POE | Target Q4 30 June 2022 | Actual Q4 30 June 2022 | POE | Annual Target 01 July 2021 - 30 June 2022 | Actual Annual 01 July 2021 - 30 June 2022 | target date / reporting frequency |  |  | Responsible Department |  |  |  | Portfolio of Evidence
Consolidating and expanding tourism | 99 | Date Tourism & Marketing Strategy submitted to Council for adoption | Date | N/A | SO 2.2.1 |  | N/A | Q2 |  | N/A |  |  | N/A |  |  | Tourism & Marketing Strategy submitted to Council for adoption by 30 June 2022 |  |  | Tourism & Marketing Strategy submitted to Council for adoption by 30 June 2022 |  | 2022-06-30 |  |  | Community Services | Q2 |  |  | Council Resolution and copy of Tourism & Marketing Strategy
Growing agriculture | 100 | Number of ZDM Co-operatives trained per quarter | Number | N/A | SO 2.2.2 |  | 25 ZDM Co-operatives trained per quarter | 28 |  | 25 ZDM Co-operatives trained per quarter |  |  | 25 ZDM Co-operatives trained per quarter |  |  | 25 ZDM Co-operatives trained per quarter |  |  | 100 ZDM Co-operatives trained by 30 June 2022 |  | Quarterly |  |  | Community services | Not Achieved | ZDM/UKZN MOU expired, however training was conducted by ZDM officials to Coops | Amend KPI during adjustment period | List of trained Co-operatives and attendance register
Supporting the well-being of vulnerable groups through short and long term initiatives | 101 | Number of jobs created through the ZDM municipal EPWP initiatives including capital projects | Number | N/A | SO 2.2.5 |  | N/A | Q4 |  | N/A |  |  | N/A |  |  | 1370 jobs created through the ZDM municipal EPWP initiatives including capital projects by 30 June 2022 |  |  | 1370 jobs created through the ZDM municipal EPWP initiatives including capital projects by 30 June 2022 |  | 2022-06-30 |  |  | Community Services | Q4 |  |  | Report retrieved from the EPWP system
| 102 | Number of Reports on implementation of Indigent Policy submitted to Council per quarter | Number | N/A |  |  | 3 Reports on implementation of Indigent Policy submitted to Council per quarter | 0 |  | 3 Reports on implementation of Indigent Policy submitted to Council per quarter |  |  | 3 Reports on implementation of Indigent Policy submitted to Council per quarter |  |  | 3 Reports on implementation of Indigent Policy submitted to Council per quarter |  |  | 12 Reports on implementation of Indigent Policy submitted to Council by 30 June 2022 |  | Quarterly |  |  | Budget & Treasury | Not Achieved |  |  | Copy of Indigent Policy Implementation report and proof of submission
| 103 | Number of jobs maintained through ZDM EPWP integrated grant projects | Number | N/A |  |  | N/A | Q4 |  | N/A |  |  | N/A |  |  | 300 jobs maintained through ZDM EPWP integrated grant projects by 30 June 2022 |  |  | 300 jobs maintained through ZDM EPWP integrated grant projects by 30 June 2022 |  | 2022-06-30 |  |  | Community Services | Q4 |  |  | List of participants retrieved from HR system
Building the capacity of the people to engage in the economy | 104 | Date support plan of Emerging farmer and SMME tabled to Council for adoption | Date | N/A | SO 2.1.2 |  | N/A | Q2 |  | N/A |  |  | N/A |  |  | Support plan of Emerging farmer and SMME tabled to Council by 30 June 2022 |  |  | Support plan of Emerging farmer and SMME tabled to Council by 30 June 2022 |  | 2022-06-30 |  |  | Community services | Q2 |  |  | Council Resolution and copy of the support plan of Emerging farmer and SMME report
Municipal Manager _______________________________________
Note on C6: Mlungisi Ngcobo: Look at target within stds??
Note on C43: Mlungisi Ngcobo: Include: No of consumers who approached the municipality to make arrangements after disconnections
Note on C94: Mlungisi Ngcobo: Insert to all depts
Note on C98: Mlungisi Ngcobo: Insert to all depts
Note on H43: Mlungisi Ngcobo: Include: No of consumers who approached the municipality to make arrangements after disconnections
Note on H94: Mlungisi Ngcobo: Insert to all depts
Note on H98: Mlungisi Ngcobo: Insert to all depts
Note on K43: Mlungisi Ngcobo: Include: No of consumers who approached the municipality to make arrangements after disconnections
Note on K94: Mlungisi Ngcobo: Insert to all depts
Note on K98: Mlungisi Ngcobo: Insert to all depts
Note on N43: Mlungisi Ngcobo: Include: No of consumers who approached the municipality to make arrangements after disconnections
Note on N94: Mlungisi Ngcobo: Insert to all depts
Note on N98: Mlungisi Ngcobo: Insert to all depts
Note on Q43: Mlungisi Ngcobo: Include: No of consumers who approached the municipality to make arrangements after disconnections
Note on Q94: Mlungisi Ngcobo: Insert to all depts
Note on Q98: Mlungisi Ngcobo: Insert to all depts
Note on T43: Mlungisi Ngcobo: Include: No of consumers who approached the municipality to make arrangements after disconnections
Note on T94: Mlungisi Ngcobo: Insert to all depts
Note on T98: Mlungisi Ngcobo: Insert to all depts

## Q1 Summary (hidden)
SUMMARY REPORT FOR QUARTER 1 OF 2021/2022 : REPORT PER KPAs
|  | Due Indicators: | Achieved | Not achieved | Not reported/ Not due | Total indicators per KPA
| KPA 1 - BASIC SERVICE DELIVERY AND INFRASTRUCTURE | 13 | 10 | 3 | 3 | 16
| KPA 2 - MUNICIPAL TRANSFORMATION AND ORGANIZATIONAL DEVELOPMENT | 9 | 8 | 1 | 9 | 18
| KPA 3 - MUNICIPAL FINANCIAL VIABILITY AND MANAGEMENT | 9 | 1 | 8 | 4 | 13
| KPA 4 - GOOD GOVERNANCE AND PUBLIC PARTICIPATION | 48 | 33 | 15 | 21 | 69
| KPA 05 - LOCAL ECONOMIC DEVELOPMENT | 2 | 0 | 2 | 4 | 6
| TOTAL: | 81 | 52 | 29 | 41 | 122
| Percentage: |  | 64% | 36%

## Sheet4 (hidden)
| Achieved | Not achieved | Due Indicators:
KPA 1 - BASIC SERVICE DELIVERY AND INFRASTRUCTURE | 10 | 3 | 13
KPA 2 - MUNICIPAL TRANSFORMATION AND ORGANIZATIONAL DEVELOPMENT | 8 | 1 | 9
KPA 3 - MUNICIPAL FINANCIAL VIABILITY AND MANAGEMENT | 1 | 8 | 9
KPA 4 - GOOD GOVERNANCE AND PUBLIC PARTICIPATION | 33 | 15 | 48
KPA 05 - LOCAL ECONOMIC DEVELOPMENT | 0 | 2 | 2
TOTAL: | 52 | 29 | 81
Percentage: | 64% | 36%