## Organizational SDBIP
ZULULAND DISTRICT MUNICIPALITY 2022/2023
ORGANIZATIONAL SERVICE DELIVERY AND BUDGET IMPLEMENTATION PLAN
KPA 01 - BASIC SERVICE DELIVERY AND INFRASTRUCTURE
Strategic Objective(SO) | KPI No. | Key Performance Indicator | Unit of Measure | Formula | IDP Strategic Objective Ref No. | Baseline | QUARTERLY TARGETS | [13 empty] | target date / reporting frequency | Budget Allocated (2022/23) | Vote No. | Responsible Department | STATUS | REASON FOR VIARIANCE | MEASURES TAKEN TO IMPROVE PERFORMANCE | Portfolio of Evidence
[7 empty] | Target Q1 30 Sep 2022 | Actual Q 1 30 Sep 2021 | STATUS - Q1 | Target Q2 31 Dec 2022 | Actual Q2 31 Dec 2021 | STATUS Q2 | Target Q3 31 Mar 2023 | Actual Q3 31 Mar 2022 | POE | Target Q4 30 June 2023 | Actual Q4 30 June 2022 | POE | Annual Target 01 July 2022 - 30 June 2023 | Actual Annual 01 July 2021 - 30 June 2022
Continuously managing all developed infrastructure capital assets to minimize the total cost of owning and operating these assets while delivering the desired service levels & protecting the natural environment ( Effective Asset Management, internal&community capacity building, collecting revenue, tariffs, monitoring & evaluation, environmental management)
Continuously managing all existing infrastructure capital assets to minimize the total cost of owning and operating these assets. (Effective Asset Management, internal & community capacity building, collecting revenue, tariffs, monitoring & evaluation, environmental management) | 1 | Number of lightning conductors installed in identified rural households within ZDM per quarter | Number | N/A | SO 1.1.1 | TBT | 25 lightning conductors installed in identified rural households per quarter within ZDM | 36 | Achieved | 25 lightning conductors installed in identified rural households per quarter within ZDM | 24 | Not Achieved | 25 lightning conductors installed in identified rural households per quarter within ZDM |  |  | 25 lightning conductors installed in identified rural households per quarter within ZDM |  |  | 100 lightning conductors installed in identified rural households within ZDM by 30 June 2023 |  | Quarterly | 500000 |  | Corporate Services | Achieved |  |  | Certificate of compliance and Beneficiary list with GPS coordinates
| 2 | Date verification on ZDM infrastructure assets performed | Date | N/A |  |  | N/A | Due in Q4 | Due in Q4 | N/A | Due in Q4 | Due in Q4 | N/A |  |  | Verification on ZDM infrastructure assets performed by 30 June 2023 |  |  | Verification on ZDM infrastructure assets performed by 30 June 2023 |  | 30-Jun-23 | Internal |  | Budget & Treasury | Due in Q4 |  |  | Engineers certificate
| 3 | Number of ZDM water contracts under construction per quarter | Number | N/A |  |  | 20 ZDM water contracts under construction per quarter | 23 | Achieved | 15 ZDM water contracts under construction per quarter | "18 | Achieved | 15 ZDM water contracts under construction per quarter |  |  | 14 ZDM water contracts under construction per quarter |  |  | 14 ZDM water contracts under construction by 30 June 2023 |  | Quarterly | 369777000 |  | Planning services | Achieved |  |  | Contracts List and Appointment letters of service providers
| 4 | Number of ZDM sanitation contracts under construction per quarter | Number | N/A |  |  | 2 ZDM sanitation contracts under construction per quarter | 2 | Achieved | 2 ZDM sanitation contracts under construction per quarter | 2 | Achieved | 2 ZDM sanitation contracts under construction per quarter |  |  | 2 ZDM sanitation contracts under construction per quarter |  |  | 2 ZDM sanitation contracts under construction by 30 June 2023 |  | Quarterly |  |  | Planning services | Achieved |  |  | Contracts list or Progress reports and Appointment letters for service providers
| 5 | Number of ZDM contracts completed annually | Number | N/A |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2 ZDM contracts completed annually |  |  | 2 ZDM contracts completed by 30 June 2023 |  | 30 Jun 23 |  |  | Planning services | Not Achieved |  |  | Certificate of completion
| 6 | Percentage of ZDM Water determinants that pass laboratory tests per quarter | Percentage | N/A |  |  | 85% ZDM Water determinants that pass laboratory tests per quarter | 96% | Achieved | 85% ZDM Water determinants that pass laboratory tests per quarter | 63% | Not Achieved | 85% ZDM Water determinants that pass laboratory tests per quarter |  |  | 85% ZDM Water determinants that pass laboratory tests per quarter |  |  | 85% ZDM Water determinants that pass laboratory tests by 30 June 2023 |  | Quarterly |  |  | Technical Services | Achieved |  |  | Lab results
| 7 | The average time taken to fix spillages per quarter | Hours | N/A |  |  | 48Hrs average time taken to fix spillages per quarter | 28,11 hrs | Achieved | 48Hrs average time taken to fix spillages per quarter | 34,6hrs | Achieved | 48Hrs average time taken to fix spillages per quarter |  |  | 48Hrs average time taken to fix spillages per quarter |  |  | 48Hrs average time taken to fix spillages by 30 June 2023 |  | Quarterly |  |  | Technical Services | Achieved |  |  | Job card summary report
Establishing and maintaining partnerships with government and private sector to accelerate provision of universal, equitable & consistent access to the municipal services that local communities are entitled to. | 8 | Number of households within ZDM to be provided with access to water within RDP standard annually | Number | N/A | SO 1.2.1 |  | 327 households within ZDM to be provided with access to water within RDP standard annually | 331 | Achieved | 395 households within ZDM to be provided with access to water within RDP standard annually | 0 | Not Achieved | N/A |  |  | N/A |  |  | 722 households within ZDM to be provided with access to water within RDP standard by 30 June 2023 |  | 30 Jun 23 |  |  | Planning Services | Achieved |  |  | List of beneficiaries and GPS co-ordinates
| 9 | Number of households within ZDM to be provided with sanitation facilities within RDP standard per quarter | Number | N/A |  |  | 678 households within ZDM to be provided with sanitation facilities within RDP standard per quarter | 209 | Not Achieved | 564 households within ZDM to be provided with sanitation facilities within RDP standard per quarter | 598 | Achieved | 71 households within ZDM to be provided with sanitation facilities within RDP standard per quarter |  |  | 71 households within ZDM to be provided with sanitation facilities within RDP standard per quarter |  |  | 1384 households within ZDM to be provided with sanitation facilities within RDP standard by 30 June 2023 |  | Quarterly |  |  | Planning Services | Not Achieved |  |  | List of beneficiaries and GPS co-ordinates
| 10 | Number of evaluation reports of ZDM water service provider (consultants) performed per quarter | Number | N/A |  |  | 1 evaluation report of ZDM water service provider (consultants) performed per quarter | 1 | Achieved | 1 evaluation report of ZDM water service provider (consultants) performed per quarter | 1 | Achieved | 1 evaluation report of ZDM water service provider (consultants) performed per quarter |  |  | 1 evaluation report of ZDM water service provider (consultants) performed per quarter |  |  | 4 evaluation reports of ZDM water service provider (consultants) performed by 30 June 2023 |  | Quarterly | Internal | Achieved | Planning Services | Achieved |  |  | Evaluation reports
| 14 | The average time taken to fix pipeline blockages within ZDM per quarter |  | N/A |  |  | 24 hrs average time taken to fix pipeline blockages within ZDM per quarter | 3Hrs | Achieved | 24 hrs average time taken to fix pipeline blockages within ZDM per quarter |  |  | 24 hrs average time taken to fix pipeline blockages within ZDM per quarter |  |  | 24 hrs average time taken to fix pipeline blockages within ZDM per quarter |  |  | 24 hrs average time taken to fix pipeline blockages within ZDM per quarter |  | Quarterly |  |  | Technical Services | Achieved |  |  | Job cards summary report
KPA 02 - LOCAL ECONOMIC & SOCIAL DEVELOPMENT
Strategic Objective(SO) | KPI No. | Key Performance Indicator | Unit of Measure | Formula | IDP Strategic Objective Ref No. | Baseline | Target Q1 30 Sep 2022 | Actual Q 1 30 Sep 2021 | STATUS -Q1 | Target Q2 31 Dec 2022 | Actual Q2 31 Dec 2021 | STATUS Q2 | Target Q3 31 Mar 2023 | Actual Q3 31 Mar 2022 | POE | Target Q4 30 JUNE 2023 | Actual Q4 | POE | Annual Target 01 July 2022 - 30 June 2023 | Actual Annual 01 July 2021 - 30 June 2022 | target date / reporting frequency | Budget Allocated (2022/23) |  | Responsible Department | STATUS | REASON FOR VIARIANCE | MEASURES TAKEN TO IMPROVE PERFORMANCE | Portfolio of Evidence
Building the capacity of the people to engage in the economy | 11 | Number of reports on the Emerging Farmers and SMME's as per the approved ZDM support plan submitted to Community Services Portfolio Committee per quarter | Date | N/A | SO 2.1.2 |  | 1 report on the Emerging Farmers and SMME's as per the approved ZDM support plan submitted to Community Services Portfolio Committee per quarter | 0 | Not Achieved | 1 report on the Emerging Farmers and SMME's as per the approved ZDM support plan submitted to Community Services Portfolio Committee per quarter | 0 | Not Achieved | 1 report on the Emerging Farmers and SMME's as per the approved ZDM support plan submitted to Community Services Portfolio Committee per quarter |  |  | 1 report on the Emerging Farmers and SMME's as per the approved ZDM support plan submitted to Community Services Portfolio Committee per quarter |  |  | 4 reports on the Emerging Farmers and SMME's as per the approved ZDM support plan submitted to Community Services Portfolio Committee by 30 June 2023 |  | Quarterly |  |  | Community services | Not Achieved |  |  | Report and proof of submission
| 12 | Number of students trained in music or drama within ZDM annually | Number | N/A |  |  | N/A | Due in Q4 | Due in Q4 | N/A |  |  | N/A |  |  | 18 Students trained in music or drama within ZDM by 30 June 2023 |  |  | 18 Students trained in music within ZDM by 30 June 2023 (8 - music/10 - drama) |  | 30-Jun-23 |  |  | Community Services | Due in Q4 |  |  | Graduation ceremony list
| 13 | Number of students within ZDM trained in visual art annually | Number | N/A |  |  | N/A | Due in Q4 | Due in Q4 | N/A |  |  | N/A |  |  | 10 students within ZDM trained in visual art by 30 June 2023 |  |  | 10 students within ZDM trained in visual art by 30 June 2023 |  | 30 Jun 23 |  |  | Community Services | Due in Q4 |  |  | Graduation ceremony list
| 14 | Number of students within ZDM trained in fashion design annually | Number | N/A |  |  | N/A | Due in Q4 | Due in Q4 | N/A |  |  | N/A |  |  | 15 students within ZDM trained in fashion design by 30 June 2023 |  |  | 15 students within ZDM trained in fashion design by 30 June 2023 |  | 2023-06-30 |  |  | Community Services | Due in Q4 |  |  | Graduation ceremony list
| 15 | Number of ZDM LED Forum meetings held per quarter | Number | N/A | SO 2.1.3 |  | 1 ZDM LED Forum meeting held per quarter | 1 | Achieved | 1 ZDM LED Forum meeting held per quarter | 1 | Achieved | 1 ZDM LED Forum meeting held per quarter |  |  | 1 ZDM LED Forum meeting held per quarter |  |  | 4 ZDM LED Forum meetings held by 30 June 2023 |  | 2023-06-30 |  |  | Community Services | Achieved |  |  | Notice, Agenda, and Attendance register
Consolidating and expanding tourism | 16 | Number of implementation reports on Tourism & Markerting Strategy submitted to Community Services Portfolio Committee | Number | N/A | SO 2.2.1 |  | 1 implementation report on Tourism & Markerting Strategy submitted to Community Services Portfolio Committee per quarter | 1 | Achieved | 1 implementation report on Tourism & Markerting Strategy submitted to Community Services Portfolio Committee per quarter | 1 | Achieved | 1 implementation report on Tourism & Markerting Strategy submitted to Community Services Portfolio Committee per quarter |  |  | 1 implementation report on Tourism & Markerting Strategy submitted to Community Services Portfolio Committee per quarter |  |  | 4 implementation reports on Tourism & Markerting Strategy submitted to Community Services Portfolio Committee per quarter |  | Quarterly |  |  | Community Services | Achieved |  |  | Copy of implementation reports on Tourism & Markerting Strategy and proof of submission
Supporting the well-being of vulnerable groups through short and long term initiatives | 17 | Number of jobs created through the ZDM municipal EPWP initiatives including capital projects | Number | N/A | SO 2.2.5 |  | N/A | Due in Q4 | Due in Q4 | N/A |  |  | N/A |  |  | 1370 jobs created through the ZDM municipal EPWP initiatives including capital projects by 30 June 2023 |  |  | 1370 jobs created through the ZDM municipal EPWP initiatives including capital projects by 30 June 2023 |  | 2023-06-30 |  |  | Community Services | Due in Q4 |  |  | Report retrieved from the EPWP system
| 18 | Number of implementation reports on Indigent Policy submitted toEXCO per quarter | Number | N/A |  |  | 1 implementation reports on Indigent Policy submitted to EXCO per quarter | 3 implementation reports on Indigent Policy submitted to EXCO per quarter | 3 implementation reports on Indigent Policy submitted to EXCO per quarter | 1 implementation reports on Indigent Policy submitted to EXCO per quarter | 1 implementation reports on Indigent Policy submitted to EXCO per quarter | 1 implementation reports on Indigent Policy submitted to EXCO per quarter | 1 implementation reports on Indigent Policy submitted to EXCO per quarter | 1 implementation reports on Indigent Policy submitted to EXCO per quarter | 1 implementation reports on Indigent Policy submitted to EXCO per quarter | 1 implementation reports on Indigent Policy submitted to EXCO per quarter |  |  | 3 implementation reports on Indigent Policy submitted to EXCO by 30 June 2023 |  | Quarterly |  |  | Budget & Treasury | Achieved |  |  | Copy of Indigent Policy Implementation report and proof of submission
| 19 | Number of jobs maintained through ZDM EPWP integrated grant projects | Number | N/A |  |  | N/A | Due in Q4 | Due in Q4 | N/A |  |  | N/A |  |  | 600 jobs maintained through ZDM EPWP integrated grant projects by 30 June 2023 |  |  | 600 jobs maintained through ZDM EPWP integrated grant projects by 30 June 2023 |  | 2023-06-30 |  |  | Community Services | Due in Q4 |  |  | List of participants retrieved from HR system
KPA 03 - MUNICIPAL FINANCIAL VIABILITY AND MANAGEMENT
Strategic Objective(SO) | KPI No. | Key Performance Indicator | Unit of Measure | Formula | Strategic Objective | Baseline | Target Q1 30 Sep 2022 | Actual Q 1 30 Sep 2021 | STATUS - Q1 | Target Q2 31 Dec 2022 | Actual Q2 31 Dec 2021 | STATUS Q2 | Target Q3 31 Mar 2023 | Actual Q3 31 Mar 2022 | POE | Target Q4 30 June 2023 | Actual Q4 30 June 2022 | POE | Annual Target 01 July 2022 - 30 June 2023 | Actual Annual 01 July 2021 - 30 June 2022 | target date / reporting frequency | Budget Allocated (2022/23) |  | Responsible Department | STATUS | REASON FOR VIARIANCE | MEASURES TAKEN TO IMPROVE PERFORMANCE | Portfolio of Evidence
Establishing and maintaining a sound and sustainable management of the fiscal and financial affairs of the municipality and its entities | 20 | Date Submission of Sec 54 (f) Mid Year Budget & Performance Assessment to the Council | Date | N/A | SO 3.1.1 |  | N/A | Due in Q3 | Due in Q3 | N/A |  |  | Submission of Sec 54(f) Mid Year Budget & Performance Assessment to the Council by 31 January 2023 |  |  | N/A |  |  | Submission of Sec 54(f) Mid Year Budget & Performance Assessment to the Council by 31 January 2023 |  | 2023-01-31 |  |  | Budget & Treasury | Due in Q3 |  |  | Council resolution and Copy of Sec 54 Mid Year Budget & Performance Assessment
| 21 | Percentage of disconnections implemented to identified non-paying ZDM customers per quarter | Percentage | N/A |  |  | 100% disconnections implemented to identified non-paying ZDM customers per quarter | 100% | Achieved | 100% disconnections implemented to identified non-paying ZDM customers per quarter | 0 | Not Achieved | 100% disconnections implemented to identified non-paying ZDM customers per quarter |  |  | 100% disconnections implemented to identified non-paying ZDM customers per quarter |  |  | 100% disconnections implemented to identified non-paying ZDM customers by 30 June 2023 |  | Quarterly |  |  | Budget & Treasury | Achieved |  |  | Disconnection report and debtors age analysis report
| 22 | Number of reports on Irregular Expenditure submitted to EXCO | Number | N/A |  |  | 1 report on Irregular Expenditure submitted to EXCO per quarter | 1 report on Irregular Expenditure submitted to EXCO per quarter | 1 report on Irregular Expenditure submitted to EXCO per quarter | 1 report on Irregular Expenditure submitted to EXCO per quarter | 1 report on Irregular Expenditure submitted to EXCO per quarter | 1 report on Irregular Expenditure submitted to EXCO per quarter | 1 report on Irregular Expenditure submitted to EXCO per quarter |  |  | 1 report on Irregular Expenditure submitted to EXCO per quarter |  |  | 4 reports on Irregular Expenditure submitted to EXCO by 30 June 2023 |  | Quarterly |  |  | Budget & Treasury | Achieved |  |  | Proof of submission and Copy of Irregular Expenditure Report
| 23 | Date consolidated procurement plan submitted to MANCO | Date | N/A |  |  | Consolidated procurement plan submitted to MANCO by 31 Aug 2022 | 30 Jun 2022 | Achieved | N/A | Reported in Q1 | Reported in Q1 | N/A |  |  | N/A |  |  | Consolidated procurement plan submitted to MANCO by 31 Aug 2022 |  | 31-Aug-22 |  |  | Budget & Treasury | Achieved |  |  | Copy of consolidated procurement plan and proof of submission
Apply sound financial management practises to keep a positive cash balance, coverage and liquidity ratios | 24 | Date reports on Sec 13 of the MFMA submitted to AG | Date | N/A | SO 3.1.2 |  | Reports on Sec 13 of the MFMA submitted to AG by 31 July 2022 | 29 Jul 2022 | Achieved | N/A | Reported in Q1 | Reported in Q1 | N/A |  |  | N/A |  |  | Reports on Sec 13 of the MFMA submitted to AG by 31 July 2022 |  | 31 July 2022 |  |  | Budget & Treasury | Achieved |  |  | Proof of submission and copy of Sec 13 reports
Manage, monitor and review existing financial systems to support accurate and credible reporting, budget monitoring and compliance | 25 | Date verification report on ZDM movable assets submitted to EXCO | Date | N/A | SO 3.1.3 |  | N/A | Due in Q4 | Due in Q4 | N/A |  |  | N/A |  |  | Verification report on ZDM movable assets submitted to EXCO by 30 June 2023 |  |  | Verification report on ZDM movable assets submitted to ECXO by 30 June 2023 |  | 30 Jun 2023 |  |  | Budget & Treasury | Due in Q4 |  |  | Copy of Verification report on ZDM movable assets and proof of submission
| 26 | Date adjustment Budget submitted to council | Date | N/A |  |  | N/A | Due in Q3 | Due in Q3 | N/A |  |  | Adjustment Budget submitted to council by 28 Feb 2023 |  |  | N/A |  |  | Adjustment Budget submitted to council by 28 February 2023 |  | 28-Feb-2023 |  |  | Budget & Treasury | Due in Q3 |  |  | Council Resolution and copy of adjustment Budget
| 27 | Date updates performed on the ZDM municipal fixed assets register | Date | N/A |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | Update performed on the ZDM municipal fixed assets register by 30 June 2023 |  |  | Update performed on the ZDM municipal fixed assets register by 30 June 2023 |  | 30 Jun 2023 |  |  | Budget & Treasury | Due in Q4 |  |  | Updated FAR
| 28 | Number of updated grant registers submitted to EXCO per quarter | Number | N/A |  |  | 1 updated grant register submitted EXCO per quarter | 1 | Achieved | 1 updated grant register submitted EXCO per quarter | 1 updated grant register submitted EXCO per quarter | 1 updated grant register submitted EXCO per quarter | 1 updated grant register submitted EXCO per quarter | 1 updated grant register submitted EXCO per quarter | 1 updated grant register submitted EXCO per quarter | 1 updated grant register submitted EXCO per quarter |  |  | 4 updated grant registers submitted EXCO by 30 June 2023 |  | Quarterly |  |  | Budget & Treasury | Achieved |  |  | Copy of grant register and Proof of Submission
| 29 | Percentage of Collection Rate achieved per quarter | Percentage | N/A |  |  | 60% Collection Rate achieved per quarter | 53% | Not Achieved | 60% Collection Rate achieved per quarter | 42% | Not Achieved | 60% Collection Rate achieved per quarter |  |  | 60% Collection Rate achieved per quarter |  |  | 60% Collection Rate achieved by 30 June 2023 |  | Quarterly |  |  | Budget & Treasury | Not Achieved |  |  | Copy of Collection Report
| 30 | Date 2022/2023 IDP Process Plan including Budget time table submitted to Council | Date | N/A |  |  | 2022/2023 IDP Process Plan including Budget time table submitted Council by 31-Aug-22 | 30 August 2022 | Achieved | N/A | Reported in Q1 | Reported in Q1 | N/A |  |  | N/A |  |  | 2022/2023 IDP Process Plan including Budget time table submitted Council by 31 August 2022 |  | 31 August 2022 |  |  | Budget & Treasury and Planning Services | Achieved |  |  | Council Resolution and copy of IDP Process Plan including Budget time table
| 31 | Date draft Budget submitted to Council | Date | N/A |  |  | N/A | Due in Q3 | Due in Q3 | N/A |  |  | Draft Budget submitted to Council by 31 March 2023 |  |  | N/A |  |  | Draft Budget submitted to Council by 31 March 2023 |  | 31 March 2023 |  |  | Budget & Treasury | Due in Q3 |  |  | Council Resolution and copy of the draft budget
| 32 | Date Final Budget approved by Council | Date | N/A |  |  | N/A | Due in Q4 | Due in Q4 | N/A |  |  | N/A |  |  | Final Budget approved by Council by 31 May 2023 |  |  | Final Budget approved by Council by 31 May 2023 |  | 31-May-23 |  |  | Budget & Treasury | Due in Q4 |  |  | Council Resolution and copy of approved budget
| 33 | Date draft budget related policies submitted to Council | Date | N/A |  |  | N/A | Due in Q3 | Due in Q3 | N/A |  |  | Draft budget related policies submitted to Council by 31 March 2023 |  |  | N/A |  |  | Draft budget related policies submitted to Council by 31 March 2023 |  | 31-Mar-23 |  |  | Budget & Treasury | Due in Q3 |  |  | Council Resolution and copy of draft budget related policies
| 34 | Date final budget related policies submitted to Council | Date | N/A |  |  | N/A | Due in Q4 | Due in Q4 | N/A |  |  | N/A |  |  | Final budget related policies submitted to Council by 30 June 2023 |  |  | Final budget related policies submitted to Council by 30 June 2023 |  | 30-Jun-23 |  |  | Budget & Treasury | Due in Q4 |  |  | Council Resolution and copy final budget related policies
| 35 | Number of MSCOA data strings uploaded to Local Government portal per quarter | Number | N/A |  |  | 3 MSCOA data strings uploaded to Local Government portal per quarter | 3 | Achieved | 3 MSCOA data strings uploaded to Local Government portal per quarter | 3 | Achieved | 3 MSCOA data strings uploaded to Local Government portal per quarter |  |  | 3 MSCOA data strings uploaded to Local Government portal per quarter |  |  | 12 MSCOA data strings uploaded to Local Government portal by 30 June 2023 |  | Quarterly |  |  | Budget & Treasury | Achieved |  |  | Print screen of system upload and copy of data strings
| 36 | Date of Submission of Sec 72 Mid - Year Budget & Performance Assessment to the Mayor & Provincial Treasury | Date | N/A |  |  | N/A | Due in Q3 | Due in Q3 | N/A |  |  | Submission of Sec 72 Mid - Year Budget & Performance Assessment to the Mayor & Provincial Treasury by 25 January 2023 |  |  | N/A |  |  | Submission of Sec 72 Mid - Year Budget & Performance Assessment to the Mayor & Provincial Treasury by 25 January 2023 |  | 2023-01-25 |  |  | Budget & Treasury | Due in Q3 |  |  | Proof of submission and copy of Sec72 Mid - Year Budget & Performance Assessment
| 37 | Number of Sec 52 reports submitted to Council per quarter | Number | N/A |  |  | 1 Sec 52 report submitted to Council per quarter (previous quarter) | 1 | Achieved | 1 Sec 52 report submitted to Council per quarter (previous quarter) | 1 | Achieved | 1 Sec 52 report submitted to Council per quarter (previous quarter) |  |  | 1 Sec 52 report submitted to Council per quarter (previous quarter) |  |  | 4 Sec 52 reports submitted to Council by 30 June 2023 |  | Quarterly |  |  | Budget & Treasury | Achieved |  |  | Council Resolution and copy of Sec 52 report
| 38 | Number of Sec 66 reports submitted to Council per quarter | Number | N/A |  |  | 3 Sec 66 reports submitted to Council per quarter (previous quarter) | 3 | Achieved | 3 Sec 66 reports submitted to Council per quarter (previous quarter) | 3 | Not Achieved | 3 Sec 66 reports submitted to Council per quarter (previous quarter) |  |  | 3 Sec 66 reports submitted to Council per quarter (previous quarter) |  |  | 12 Sec 66 reports submitted to Council by 30 June 2023 |  | Quarterly |  |  | Budget & Treasury | Achieved |  |  | Council Resolution and copy of Sec 66 report
| 39 | Number of Sec 11 reports submitted to Council, Provincial Treasury and Auditor General per quarter | Number | N/A |  |  | 1 Sec 11 report submitted to Council, Provincial Treasury and Auditor General per quarter | 1 | Achieved | 1 Sec 11 report submitted to Council, Provincial Treasury and Auditor General per quarter | 1 | Achieved | 1 Sec 11 report submitted to Council, Provincial Treasury and Auditor General per quarter |  |  | 1 Sec 11 report submitted to Council, Provincial Treasury and Auditor General per quarter |  |  | 4 Sec 11 reports submitted to Council, Provincial Treasury and Auditor General per quarter by 30 June 2023 |  | Quarterly |  |  | Budget & Treasury | Achieved |  |  | Council Resolution; Proof of submission and copy of Sec 11 reports
| 40 | Number of reports based on updated Grants Register submitted to EXCO | Number | N/A |  |  | 3 reports based on updated Grants Register submitted to EXCO per quarter | 3 | Achieved | 3 reports based on updated Grants Register submitted to EXCO per quarter | 3 reports based on updated Grants Register submitted to EXCO per quarter | 3 reports based on updated Grants Register submitted to EXCO per quarter | 3 reports based on updated Grants Register submitted to EXCO per quarter | 3 reports based on updated Grants Register submitted to EXCO per quarter | 3 reports based on updated Grants Register submitted to EXCO per quarter | 3 reports based on updated Grants Register submitted to EXCO per quarter |  |  | 12 reports based on updated Grants Register submitted EXCO by 30 June 2023 |  | Quarterly |  |  | Budget & Treasury | Achieved |  |  | Updated grant register and Proof of Submission
| 41 | Number of monthly budget statements (Sec 71 reports) submitted to Mayor and Provincial Treasury per quarter | Number | N/A |  |  | 3 monthly budget statements (Sec 71 reports) submitted to Mayor and Provincial Treasury per quarter | 3 | Achieved | 3 monthly budget statements (Sec 71 reports) submitted to Mayor and Provincial Treasury per quarter | 3 | Achieved | 3 monthly budget statements (Sec 71 reports) submitted to Mayor and Provincial Treasury per quarter |  |  | 3 monthly budget statements (Sec 71 reports) submitted to Mayor and Provincial Treasury per quarter |  |  | 12 monthly budget statements (Sec 71 reports) submitted to Mayor and Provincial Treasury by 30 June 2023 |  | Quarterly |  |  | Budget & Treasury | Achieved |  |  | Proof of submission and soft copy of Sec 71 report
Refine procurement systems and processes to respond to the demand for services | 42 | Percentage of tenders finalised within 3 months after date of advertisement per quarter | Percentage | N/A | SO 3.1.4 |  | 100% of tenders finalised within 3 months after date of advertisement per quarter | 100% | Achieved | 100% of tenders finalised within 3 months after date of advertisement per quarter | 100% | Achieved | 100% of tenders finalised within 3 months after date of advertisement per quarter |  |  | 100% of tenders finalised within 3 months after date of advertisement per quarter |  |  | 100% of tenders finalised within 3 months after date of advertisement by 30 June 2023 |  | Quarterly |  |  | Budget & Treasury | Achieved |  |  | Adverts and appointment letters
| 43 | Number of SCM quarterly reports submitted to EXCO per quarter | Number | N/A |  |  | 1 SCM quarterly report submitted to EXCO per quarter | 1 | Achieved | 1 SCM quarterly report submitted to EXCO per quarter | 1 | Achieved | 1 SCM quarterly report submitted to EXCO per quarter |  |  | 1 SCM quarterly report submitted to EXCO per quarter |  |  | 4 SCM quarterly reports submitted to EXCO by 30 June 2023 |  | Quarterly |  |  | Budget & Treasury | Achieved |  |  | Proof of submission and Copy of SCM Quarterly reports
KPA 04 - GOOD GOVERNANCE AND PUBLIC PARTICIPATION
Strategic Objective(SO) | KPI No. | Key Performance Indicator | Unit of Measure | Formula | Responsible Department | Baseline | Target Q1 30 Sep 2022 | Actual Q 1 30 Sep 2021 | STATUS - Q1 | Target Q2 31 Dec 2022 | Actual Q2 31 Dec 2021 | STATUS Q2 | Target Q3 31 Mar 2023 | Actual Q3 31 Mar 2022 | POE | Target Q4 30 June 2023 | Actual Q4 30 June 2022 | POE | Annual Target 01 July 2022 - 30 June 2023 | Actual Annual 01 July 2021 - 30 June 2022 | target date / reporting frequency | Budget Allocated (2022/23) |  | Responsible Department | STATUS | REASON FOR VIARIANCE | MEASURES TAKEN TO IMPROVE PERFORMANCE | Portfolio of Evidence
Promoting transparent and accountable governance through regular community engagements and effective administration. | 44 | Number of ZDM Municipal Health awareness campaigns held per quarter | Number | N/A |  |  | 2 ZDM Municipal Health awareness campaign held per quarter | 2 | Achieved | 2 ZDM Municipal Health awareness campaign held per quarter | 2 | Achieved | 2 ZDM Municipal Health awareness campaign held per quarter |  |  | 2 ZDM Municipal Health awareness campaign held per quarter |  |  | 8 ZDM Municipal Health awareness campaigns by 30 June 2023 |  | Quarterly |  |  | Community Services | Achieved |  |  | OOP and Attendance Register
| 45 | Number of ZDM disaster awareness campaigns held per quarter | Number | N/A |  |  | 9 ZDM disaster awareness campaign held per quarter | 9 ZDM disaster awareness campaign held per quarter | 9 ZDM disaster awareness campaign held per quarter | 9 ZDM disaster awareness campaign held per quarter | 9 ZDM disaster awareness campaign held per quarter | 9 ZDM disaster awareness campaign held per quarter | 9 ZDM disaster awareness campaign held per quarter |  |  | 9 ZDM disaster awareness campaign held per quarter |  |  | 36 ZDM disaster awareness campaigns held by 30 June 2023 |  | Quarterly |  |  | Corporate Services | Achieved |  |  | Pictures
| 46 | Number of ZDM District Civil Society Forum meetings held per quarter | Number | N/A |  | new KPI | 1 ZDM District Civil Society Forum meeting held per quarter | 1 | Achieved | 1 ZDM District Civil Society Forum meeting held per quarter | 1 | Achieved | 1 ZDM District Civil Society Forum meeting held per quarter |  |  | 1 ZDM District Civil Society Forum meeting held per quarter |  |  | 4 ZDM District Civil Society Forum meetings held by 30 June 2023 |  | Quarterly |  |  | Community Services | Achieved |  |  | Notice, Agenda, and Attendance register
Systematic development and or review and monitoring implementation of all municipal policies, bylaws, strategies, plans and frameworks in line with any applicable legislation | 47 | Number of implementation reports on the ZDM LED strategy submitted to Community Services Portfolio Committee per quarter | Date | N/A | SO 4.1.4 |  | 1 implementation report on the ZDM LED strategy submitted to Community Services Portfolio Committee per quarter | 1 | Achieved | 1 implementation report on the ZDM LED strategy submitted to Community Services Portfolio Committee per quarter | 1 | Achieved | 1 implementation report on the ZDM LED strategy submitted to Community Services Portfolio Committee per quarter |  |  | 1 implementation report on the ZDM LED strategy submitted to Community Services Portfolio Committee per quarter |  |  | 4 implementation reports on the ZDM LED strategy submitted to Community Services Portfolio Committee by 30 June 2023 |  | 30-Jun-23 |  |  | Community Services | Achieved |  |  | Proof of submission and copy of LED strategy implementation reports
| 48 | Number of implementation reports on Indonsa Arts & Craft Centre business strategy submitted to Community Services Portfolio Committee per quarter | Date | N/A |  |  | 1 implementation report on Indonsa Arts & Craft Centre business strategy submitted to Community Services Portfolio Committee per quarter | 1 | Achieved | 1 implementation report on Indonsa Arts & Craft Centre business strategy submitted to Community Services Portfolio Committee per quarter | 1 | Achieved | 1 implementation report on Indonsa Arts & Craft Centre business strategy submitted to Community Services Portfolio Committee per quarter |  |  | 1 implementation report on Indonsa Arts & Craft Centre business strategy submitted to Community Services Portfolio Committee per quarter |  |  | 4 implementation report on Indonsa Arts & Craft Centre business strategy submitted to Community Services Portfolio Committee by 30 June 2023 |  | 30-Jun-23 |  |  | Community Services | Achieved |  |  | Copy of Implementation reports on Indonsa Arts & Crafts Centre business strategy and proof of submission
| 49 | Date revised ZDM internal audit charter adopted by Audit Committee | Date | N/A |  |  | N/A | Due in Q4 | Due in Q4 | N/A |  |  | N/A |  |  | Revised ZDM internal audit charter adopted by Audit Committee by 30 June 2023 |  |  | Revised ZDM internal audit charter adopted by Audit Committee by 30 June 2023 |  | 30 Jun 23 |  |  | OMM | Due in Q4 |  |  | Copy of Internal Audit Charter and Audit Committee minutes
| 50 | Date ZDM Service Delivery Charter adopted by council | Date | N/A |  | To be confirmed | N/A | Due in Q3 | Due in Q3 | N/A |  |  | N/A |  |  | ZDM Service Delivery Charter adopted council by 30 June 2023 |  |  | ZDM Service Delivery Charter adopted council by 30 June 2023 |  | 2023-06-30 |  |  | Corporate Service | Due in Q3 |  |  | Council resolution and Copy of Service delivery Charter
| 51 | Date WSIG and RBIG Annual Implementation Plan submitted to Department of Water and Sanitation | Date |  |  |  | N/A | Due in Q4 | Due in Q4 | N/A |  |  | N/A |  |  | WSIG and RBIG Annual Implementation Plan submitted to Department of Water and Sanitation by 30 Jun 2023 |  |  | WSIG and RBIG Annual Implementation Plan submitted to Department of Water and Sanitation by 30 Jun 2023 |  | 2023-06-15 | Internal |  | Planning Services | Due in Q4 |  |  | Proof of Submission and copy of WSIG and RBIG Annual Implementation Plan report
| 52 | Date PMU Business Plan submitted to KZN-COGTA | Date |  |  |  | N/A | Due in Q4 | Due in Q4 | N/A |  |  | N/A |  |  | PMU Business Plan submitted to KZN-COGTA by 30 April 2023 |  |  | PMU Business Plan submitted to KZN-COGTA by 30 April 2023 |  | 2023-04-30 | Internal |  | Planning Services | Due in Q4 |  |  | Proof of Submission and copy of PMU Business Plan report
| 53 | Date Three Year Proforma Implementation Plan submitted to KZN-COGTA | Date |  |  |  | N/A | Due in Q3 | Due in Q3 | N/A |  |  | Three Year Proforma Implementation Plan submitted to KZN-COGTA by 30 January 2023 |  |  | N/A |  |  | Three Year Proforma Implementation Plan submitted to KZN-COGTA by 30 January 2023 |  | 2023-01-30 | Internal |  | Planning Services | Due in Q3 |  |  | Proof of Submission and copy of three year proforma Implementation plan
| 54 | Date MSA Sec 11(3)(a) MFMA 16(1), 24(2), 53(1)( c)(i), 62(1)(f), 79(1)(c ) Policies and bylaws submitted to the Council | Date | N/A |  | To be confirmed | N/A | Due in Q4 | Due in Q4 | N/A |  |  | N/A |  |  | MSA Sec 11(3)(a) MFMA 16(1), 24(2), 53(1)( c)(i), 62(1)(f), 79(1)(c ) Policies and bylaws submitted to the Council by 30 June 2023 |  |  | MSA Sec 11(3)(a) MFMA 16(1), 24(2), 53(1)( c)(i), 62(1)(f), 79(1)(c ) Policies and bylaws submitted to the Council by 30 June 2023 |  | 2023-06-30 | - | - | Corporate Services | Due in Q4 |  |  | Council resolutions and copy of polices and bylaws
KPA 05 - MUNICIPAL TRANSFORMATION & ORGANIZATIONAL DEVELOPMENT
Strategic Objective(SO) | KPI No. | Key Performance Indicator | Unit of Measure | Formula | Responsible Department | Baseline | Target Q1 30 Sep 2022 | Actual Q 1 30 Sep 2021 | STATUS - Q1 | Target Q2 31 Dec 2022 | Actual Q2 31 Dec 2021 | STATUS Q2 | Target Q3 31 Mar 2023 | Actual Q3 31 Mar 2022 | POE | Target Q4 30 June 2023 | Actual Q4 30 June 2022 | POE | Annual Target 01 July 2022 - 30 June 2023 | Actual Annual 01 July 2021 - 30 June 2022 | target date / reporting frequency | Budget Allocated (2022/23) |  | Responsible Department | STATUS |  |  | Portfolio of Evidence
Investing in a workforce to meet service delivery demand through implementing a culture of continuous learning and improvement | 55 | Number of policy workshops conducted for ZDM employees per quarter | Number | N/A | SO 5.1.1 |  | 1 policy workshop conducted for ZDM employees per quarter | 1 | Achieved | 1 policy workshop conducted for ZDM employees per quarter | 1 | Achieved | 1 policy workshop conducted for ZDM employees per quarter |  |  | 1 policy workshop conducted for ZDM employees per quarter |  |  | 4 policy workshops conducted for ZDM employees by 30 June 2023 |  | Quarterly |  |  | Corporate Services | Achieved |  |  | Notice, Attendance Register and copy of presentations made
| 56 | Number of ZDM employees trained on Batho Pele principles per quarter | Number | N/A |  | To be confirmed | 30 ZDM employees trained on Batho Pele principles per quarter | 45 | Achieved | 30 ZDM employees trained on Batho Pele principles per quarter | 35 | Achieved | 30 ZDM employees trained on Batho Pele principles per quarter |  |  | 30 ZDM employees trained on Batho Pele principles per quarter |  |  | 120 ZDM employees trained on Batho Pele principles by 30 June 2023 |  | Quarterly |  |  | Corporate services | Achieved |  |  | Notice, Attendance Register and copy of presentations made
| 57 | Number workshops conducted on labour relations matters to ZDM employees per quarter | Number | N/A |  |  | 1 workshop conducted on labour relations matters to ZDM employees per quarter | 1 | Achieved | 1 workshop conducted on labour relations matters to ZDM employees per quarter | 1 | Achieved | 1 workshop conducted on labour relations matters to ZDM employees per quarter |  |  | 1 workshop conducted on labour relations matters to ZDM employees per quarter |  |  | 4 workshops conducted on labour relations matters to ZDM employees by 30 June 2023 |  | Quarterly |  |  | Corporate Services | Achieved |  |  | Notice, Attendance Register and copy of presentations made
| 58 | Date WSP report submitted to LGSETA | Date | N/A |  | new KPI | N/A | Due in Q4 | Due in Q4 | N/A |  |  | N/A |  |  | WSP report submitted to LGSETA by 30 June 2023 |  |  | WSP report submitted to LGSETA by 30 June 2023 |  | 2023-06-30 |  |  | Corporate services | Due in Q4 |  |  | Copy of WSP Report and Proof of submission
Promoting sound labour relations through promoting effective human resource practises | 59 | Date employment equity reports submitted to Department of Labour | Date | N/A | SO 5.1.2 |  | N/A | Due in Q3 | Due in Q3 | N/A |  |  | Employment equity reports submitted to Department of Labour by 15 Jan 2023 |  |  | N/A |  |  | Employment equity reports submitted to Department of Labour by 15 Jan 2023 |  | 2023-03-31 |  |  | Corporate Services | Due in Q3 |  |  | Proof of submission and copy of employment equity plan report
| 60 | Date employment equity plan reports submitted to Local Labour Forum | Date | N/A |  |  | N/A | Due in Q4 | Due in Q4 | 1 employment equity report submitted to Local Labour Forum by 31 Dec 2022 |  |  | N/A |  |  | N/A |  |  | 1 employment equity report submitted to Local Labour Forum by 31 Dec 2022 |  | 2022-12-31 |  |  | Corporate Services | Due in Q4 |  |  | Proof of submission and Employment equity Plan
| 61 | Date 2023/2024 ZDM organogram approved by council | Date | N/A |  |  | N/A | Due in Q4 | Due in Q4 | N/A |  |  | N/A |  |  | 2023/2024 ZDM organogram approved by council by 30 June 2023 |  |  | 2023/2024 ZDM organogram approved by council by 30 June 2023 |  | 2023-06-30 |  |  | Corporate Services | Due in Q4 |  |  | Council Resolution and organogram
Optimise workforce productivity by enforcing a sound organizational culture | 62 | Number of District monthly statistics report submissions to Provincial Department of Health per quarter | Number | N/A | SO 5.1.3 |  | 3 District monthly statistics report submissions to Provincial Department of Health per quarter | 7 | Achieved | 3 District monthly statistics report submissions to Provincial Department of Health per quarter | 7 | Achieved | 3 District monthly statistics report submissions to Provincial Department of Health per quarter |  |  | 3 District monthly statistics report submissions to Provincial Department of Health per quarter |  |  | 12 District monthly statistics report submissions to Provincial Department of Health by 30 June 2023 |  | Quarterly |  |  | Community Services | Achieved |  |  | Proof of Submission and soft copy of district monthly statistics report
| 63 | Number of Quarterly evaluation reports on Integrated grant EPWP submitted to Department of Public Works per quarter | Number | N/A |  | new KPI | 1 Quarterly evaluation report on Integrated grant EPWP submitted to Department of Public Works per quarter | 1 | Achieved | 1 Quarterly evaluation report on Integrated grant EPWP submitted to Department of Public Works per quarter | 1 | Achieved | 1 Quarterly evaluation report on Integrated grant EPWP submitted to Department of Public Works per quarter |  |  | 1 Quarterly evaluation report on Integrated grant EPWP submitted to Department of Public Works per quarter |  |  | 4 Quarterly evaluation reports on Integrated grant EPWP submitted to Department of Public Works by 30 June 2023 |  | Quarterly |  |  | Community Services | Achieved |  |  | Proof of submission and Quarterly evaluation reports
| 64 | Number of integrated grant expenditure reports submitted to the Department of Public Works per quarter | Number | N/A |  |  | 3 integrated grant expenditure reports submitted to the Department of Public Works per quarter | 3 | Achieved | 3 integrated grant expenditure reports submitted to the Department of Public Works per quarter | 3 | Achieved | 3 integrated grant expenditure reports submitted to the Department of Public Works per quarter |  |  | 3 integrated grant expenditure reports submitted to the Department of Public Works per quarter |  |  | 12 integrated grant expenditure reports submitted to the Department of Public Works by 30 June 2023 |  | Quarterly |  |  | Community service | Achieved |  |  | Acknowledgment of receipts and copies of expenditure reports
| 65 | Date of submission of narrative 2021/2022 Annual Report on EPWP to Department of Public Works | Date | N/A |  |  | Submission on narrative 2021/2022 Annual Report on EPWP to Department of Public Works by 15 July 2022 |  | Achieved | N/A | N/A | N/A | N/A |  |  | N/A |  |  | Submission on narrative 2021/2022 Annual Report on EPWP to Department of Public Works by 15 July 2022 |  | 15-Jul-22 |  |  | Community Services | Achieved |  |  | Proof of submission and copy of report
| 66 | Number of MIG Claims uploads onto MIG MIS and submission of the MIG Expenditure and Commitments Schedule [MECS] to KZN-COGTA per quarter | Number |  |  |  | 3 MIG Claims uploads onto MIG MIS and submission of the MIG Expenditure and Commitments Schedule [MECS] to KZN-COGTA per quarter | 3 | Achieved | 3 MIG Claims uploads onto MIG MIS and submission of the MIG Expenditure and Commitments Schedule [MECS] to KZN-COGTA per quarter | 3 | Achieved | 3 MIG Claims uploads onto MIG MIS and submission of the MIG Expenditure and Commitments Schedule [MECS] to KZN-COGTA per quarter |  |  | 3 MIG Claims uploads onto MIG MIS and submission of the MIG Expenditure and Commitments Schedule [MECS] to KZN-COGTA per quarter |  |  | 12 MIG Claims uploads onto MIG MIS and submission of the MIG Expenditure and Commitments Schedule [MECS] to KZN-COGTA by 30 June 2023 |  | Quarterly |  |  | Planning Services | Achieved |  |  | Print screen of system upload
| 67 | Number of WSIG and RBIG QPE Reports submitted to Department of Water & Sanitation per quarter | Number |  |  |  | 1 WSIG and RBIG QPE Report submitted to Department of Water & Sanitation per quarter | 2 | Achieved | 1 WSIG and RBIG QPE Report submitted to Department of Water & Sanitation per quarter | 0 | Not Achieved | 1 WSIG and RBIG QPE Report submitted to Department of Water & Sanitation per quarter |  |  | 1 WSIG and RBIG QPE Report submitted to Department of Water & Sanitation per quarter |  |  | 4 WSIG and RBIG QPE Reports submitted to Department of Water & Sanitation by 30 June 2023 |  | Quarterly |  |  | Planning Services | Achieved |  |  | Proof of Submission and copy of report
| 68 | Date MIG Annual Performance Evaluation Report submitted to KZN-COGTA | Date |  |  |  | MIG Annual Performance Evaluation Report submitted to KZN-COGTA by 30 Sept 2022 | 31 August 2022 | Achieved | N/A | N/A | N/A | N/A |  |  | N/A |  |  | MIG Annual Performance Evaluation Report submitted to KZN-COGTA by 30 Sept 2022 |  | 2022-09-30 |  |  | Planning Services | Achieved |  |  | Proof of Submission and copy of MIG Annual Performance Evaluation Report
| 69 | Number of MIG Expenditure Proof of Payments uploaded to KZN-COGTA on MIG MIS per quarter | Number |  |  |  | 3 MIG Expenditure Proof of Payments uploaded to KZN-COGTA on MIG MIS per quarter | 3 | Achieved | 3 MIG Expenditure Proof of Payments uploaded to KZN-COGTA on MIG MIS per quarter | 3 | Achieved | 3 MIG Expenditure Proof of Payments uploaded to KZN-COGTA on MIG MIS per quarter |  |  | 3 MIG Expenditure Proof of Payments uploaded to KZN-COGTA on MIG MIS per quarter |  |  | 12 MIG Expenditure Proof of Payments uploaded to KZN-COGTA on MIG MIS by 30 June 2023 |  | Quarterly |  |  | Planning Services | Achieved |  |  | Proof of Submission and proof of payments
| 70 | Number of WSIG and RBIG Monthly Reports (5B) submitted to Department of Water & Sanitation per quarter | Number |  |  |  | 3 WSIG and RBIG Monthly Reports (5B) submitted to Department of Water & Sanitation per quarter | 3 | Achieved | 3 WSIG and RBIG Monthly Reports (5B) submitted to Department of Water & Sanitation per quarter | 3 | Achieved | 3 WSIG and RBIG Monthly Reports (5B) submitted to Department of Water & Sanitation per quarter |  |  | 3 WSIG and RBIG Monthly Reports (5B) submitted to Department of Water & Sanitation per quarter |  |  | 12 WSIG and RBIG Monthly Reports (5B) submitted to Department of Water & Sanitation by 30 June 2023 |  | Quarterly |  |  | Planning Services | Achieved |  |  | Proof of Submission and copy WSIG and RBIG monthly report
| 71 | Date Final 2023/2024 IDP submitted to Council for adoption | Date | N/A |  |  | N/A | Due in Q4 | Due in Q4 | N/A |  |  | N/A |  |  | Final 2023/2024 IDP submitted to Council for adoption by 31 May 2023 |  |  | Final 2023/2024 IDP submitted to Council for adoption by 31 May 2023 |  | 2023-05-31 |  |  | Planning Services | Due in Q4 |  |  | Council Resolution and copy of final IDP
| 72 | Date final SDBIP 2023/2024 submitted to the Mayor | Date | N/A |  |  | N/A | Due in Q4 | Due in Q4 | N/A |  |  | N/A |  |  | Final SDBIP 2023/2024 submitted to the Mayor by 28 June 2023 |  |  | Final SDBIP 2023/2024 submitted to the Mayor by 28 June 2023 |  | 28-Jun-2023 |  |  | OMM | Due in Q4 |  |  | Proof of Submission and signed SDBIP
| 73 | Date Annual Report adopted by Council | Date | N/A |  |  | N/A | Due in Q3 | Due in Q3 | N/A |  |  | Annual Report adopted by Council by 31 Jan 2023 |  |  | N/A |  |  | Annual Report adopted by Council by 31 Jan 2023 |  | 31-Jan-23 |  |  | Planning Services | Due in Q3 |  |  | Council Resolution and copy of annual report
| 74 | Date AFS submitted to AG | Date | N/A |  |  | AFS submitted to AG by 31 Aug 2022 | 31 Aug 2022 | Achieved | N/A | Reported in Q1 | Reported in Q1 | N/A |  |  | N/A |  |  | AFS submitted to AG by 31 Aug 2022 |  | 2022-08-31 |  |  | Budget & Treasury | Achieved |  |  | Proof of submission and copy of AFS
| 75 | Date AFS audit opinion 2021/2022 achieved | Date | N/A |  |  | N/A | Due in Q2 | Due in Q2 | AFS audit opinion 2021/2022 achieved by 31 December 2022 | 2022-11-30 | Achieved | N/A |  |  | N/A |  |  | AFS audit opinion 2021/2022 achieved by 31 December 2022 |  | 31-Dec-2022 |  |  | Budget & Treasury | Due in Q2 |  |  | Audit Report
| 76 | Date APR audit opinion 2021/2022 achieved | Date | N/A |  |  | N/A | Due in Q2 | Due in Q2 | APR unqualified audit opinion 2021/2022 achieved by 31 December 2022 | 2022-11-30 | Achieved | N/A |  |  | N/A |  |  | APR unqualified audit opinion 2021/2022 achieved by 31 December 2022 |  | 31-Dec-2022 |  |  | OMM | Due in Q2 |  |  | Audit Report
| 77 | Date AG corrective action plan developed | Date | N/A |  |  | N/A | Due in Q2 | Due in Q2 | AG Corrective action plan developed by 31 December 2022 | 2022-12-13 | Achieved | N/A |  |  | N/A |  |  | AG Corrective action plan developed by 31 December 2022 |  | 31-Dec-2022 |  |  | OMM | Due in Q2 |  |  | Copy Action Plan
| 78 | Percentage of resolved issues as per corrective action plan targets | Percentage | N/A |  |  | N/A | Due in Q4 | Due in Q4 | N/A | Due in Q4 | Due in Q4 | 50% resolved issues as per corrective action plan targets by 30 June 2023 |  |  | 50% resolved issues as per corrective action plan targets by 30 June 2023 |  |  | 100% resolved issues as per corrective action plan targets by 30 June 2023 |  | 30-Jun-23 |  |  | Budget & Treasury | Due in Q4 |  |  | Updated action plan
Monitor, review and progressively improve service delivery performance through improvement of business processes and systems, performance auditing, risk management and oversight | 79 | Number of PMS reports submitted to Internal Audit per quarter | Number | N/A | SO 5.1.4 |  | 1 PMS report submitted to Internal Audit per quarter | 1 | Achieved | 1 PMS report submitted to Internal Audit per quarter | 1 | Achieved | 1 PMS report submitted to Internal Audit per quarter |  |  | 1 PMS report submitted to Internal Audit per quarter |  |  | 4 PMS reports submitted to Internal Audit by 30 June 2023 |  | Quarterly |  |  | OMM | Achieved |  |  | Proof of submission
| 80 | Date Performance Agreements for ZDM Senior Managers submitted to KZN-COGTA | Date | N/A |  | NEW KPI | Performance Agreements for ZDM Senior Managers submitted to KZN-COGTA by 14 Aug 2022 | 12 Aug 22 | Achieved | N/A | Reported in Q1 |  | N/A |  |  | N/A |  |  | Performance Agreements for ZDM Senior Managers submitted to KZN-COGTA by 14 Aug 2022 |  | 2022-08-14 |  |  | OMM | Achieved |  |  | Proof of submission and signed performance agreements
| 81 | Date Performance Agreements for ZDM Senior Managers published in print and electronic platforms | Date | N/A |  |  | Performance Agreements for ZDM Senior Managers published in print and electronic platforms by 30 August 2022 | 12 Aug 22 & 15 Aug 2022 | Achieved | N/A | Reported in Q1 |  | N/A |  |  | N/A |  |  | Performance Agreements for ZDM Senior Managers published in print and electronic platforms by 30 August 2022 |  | 2022-08-30 |  |  | OMM | Achieved |  |  | Copy of advert and print screen of ZDM website
| 82 | Date Internal Audit Plan 2022/2023 submitted to Audit Committee for adoption | Date | N/A |  | NEW KPI | Internal Audit Plan 2022/2023 submitted to Audit Committee for adoption by 30 Sept 2022 | 26 Sep 2022 | Achieved | N/A | Reported in Q1 |  | N/A |  |  | N/A |  |  | Internal Audit Plan 2022/2023 submitted to Audit Committee for adoption by 30 Sept 2022 |  | 30 Sep 2022 |  |  | OMM | Achieved |  |  | Internal Audit Plan and Audit Committee minutes
| 83 | Number of Consolidated Internal Audit reports submitted to the Audit committee per quarter | Number | N/A |  |  | 1 Consolidated Internal Audit report submitted to the Audit committee per quarter | 2 | Achieved | 1 Consolidated Internal Audit report submitted to the Audit committee per quarter | 1 | Achieved | 1 Consolidated Internal Audit report submitted to the Audit committee per quarter |  |  | 1 Consolidated Internal Audit report submitted to the Audit committee per quarter |  |  | 4 Consolidated Internal Audit reports submitted to the Audit committee by 30 June 2023 |  | Quarterly |  |  | OMM | Achieved |  |  | IA reports and Audit Committee minutes
| 84 | Number of Audit Committee meetings coordinated per quarter | Number | N/A |  |  | 1 Audit committee meeting coordinated per quarter | 2 | Achieved | 1 Audit committee meeting coordinated per quarter | 1 | Achieved | 1 Audit committee meeting coordinated per quarter |  |  | 1 Audit committee meeting coordinated per quarter |  |  | 4 Audit committee meetings coordinated by 30 June 2023 |  | Quarterly |  |  | OMM | Achieved |  |  | Notice, Agenda, and Attendance register
| 85 | Date ZDM Annual Performance Report submitted to AG | Date | N/A |  |  | ZDM Annual Performance Report submitted to AG by 31 August 2022 | 31 August 2022 | Achieved | N/A | Reported in Q1 | Reported in Q1 | N/A |  |  | N/A |  |  | ZDM Annual Performance Report submitted to AG by 31 August 2022 |  | 2022-08-31 |  |  | OMM | Achieved |  |  | Proof of submission and copy of the APR
| 86 | Number of MPMR Sec 14 (2)(g) meetings in relation to Audit Committee secretariat services provided per quarter | Number | N/A |  |  | 1 MPMR Sec 14 (2)(g) meeting in relation to Audit Committee secretariat services provided held per quarter | 2 | Achieved | 1 MPMR Sec 14 (2)(g) meeting in relation to Audit Committee secretariat services provided held per quarter | 1 | Achieved | 1 MPMR Sec 14 (2)(g) meeting in relation to Audit Committee secretariat services provided held per quarter |  |  | 1 MPMR Sec 14 (2)(g) meeting in relation to Audit Committee secretariat services provided held per quarter |  |  | 4 MPMR Sec 14 (2)(g) meetings in relation to Audit Committee secretariat services provided held by 30 June 2023 |  | Quarterly |  |  | Corporate Services | Achieved |  |  | Notice, Agenda and attendance register
| 87 | Number of EXCO Meetings coordinated per quarter | Number | N/A |  |  | 1 EXCO Meeting coordinated per quarter | 3 | Achieved | 1 EXCO Meeting coordinated per quarter | 4 | Achieved | 1 EXCO Meeting coordinated per quarter |  |  | 1 EXCO Meeting coordinated per quarter |  |  | 4 EXCO Meetings coordinated by 30 June 2023 |  | Quarterly |  |  | Corporate Services | Achieved |  |  | Notice, Agenda and attendance register
| 88 | Number of MSA Sec 79 (1) Number of portfolio committee meetings coordinated per quarter | Number | N/A |  | new KPI | 4 MSA Sec 79 (1) portfolio committee meetings coordinated per quarter | 5 | Achieved | 4 MSA Sec 79 (1) portfolio committee meetings coordinated per quarter | 7 | Achieved | 4 MSA Sec 79 (1) portfolio committee meetings coordinated per quarter |  |  | 4 MSA Sec 79 (1) portfolio committee meetings coordinated per quarter |  |  | 16 MSA Sec 79 (1) portfolio committee meetings coordinated by 30 June 2023 |  | Quarterly | - | - | Corporate Services | Achieved |  |  | Notice, Agenda and attendance register
| 89 | Number of MPAC meetings coordinated per quarter | Number | N/A |  |  | 1 MPAC meeting coordinated per quarter | 2 | Achieved | 1 MPAC meeting coordinated per quarter | 1 | Achieved | 1 MPAC meeting coordinated per quarter |  |  | 1 MPAC meeting coordinated per quarter |  |  | 4 MPAC meetings coordinated by 30 June 2023 |  | Quarterly |  |  | Corporate Services | Achieved |  |  | Notice, Agenda and attendance register
| 90 | Number of Council Meetings coordinated per quarter | Number | N/A |  | To be confirmed | 1 Council Meeting coordinated per quarter | 1 | Achieved | 1 Council Meeting coordinated per quarter | 4 | Achieved | 1 Council Meeting coordinated per quarter |  |  | 1 Council Meeting coordinated per quarter |  |  | 4 Council Meetings coordinated by 30 June 2023 |  | Quarterly |  |  | Corporate Services | Achieved |  |  | Notice, Agenda and attendance register
| 91 | Number of Revenue Steering Committee meetings conducted per quarter | Number | N/A |  |  | 1 Revenue Steering Committee meeting conducted per quarter | 1 | Achieved | 1 Revenue Steering Committee meeting conducted per quarter | 1 | Achieved | 1 Revenue Steering Committee meeting conducted per quarter |  |  | 1 Revenue Steering Committee meeting conducted per quarter |  |  | 4 Revenue Steering Committee meetings conducted by 30 June 2023 |  | Quarterly |  |  | Budget & Treasury | Achieved |  |  | Notice, Agenda, and Attendance register
| 92 | Number of ICT steering committee meetings held per quarter | Number | N/A |  |  | 1 ICT steering committee meeting held per quarter | 1 | Achieved | 1 ICT steering committee meeting held per quarter | 1 | Achieved | 1 ICT steering committee meeting held per quarter |  |  | 1 ICT steering committee meeting held per quarter |  |  | 4 ICT steering committee meetings held by 30 June 2023 |  | Quarterly |  |  | Corporate Services | Achieved |  |  | Notice, Agenda and attendance register
Establishing consistency and alignment between the district and locals by regular co-ordination of Integovernmental Relations | 93 | Number of Municipal Manager Technical IGR/DDM meetings coordinated per quarter | Number | N/A | SO 5.1.6 | NEW KPI | 1 Municipal Manager Technical IGR/DDM meeting coordinated per quarter | 0 | Not Achieved | 1 Municipal Manager Technical IGR/DDM meeting coordinated per quarter | 1 | Achieved | 1 Municipal Manager Technical IGR/DDM meeting coordinated per quarter |  |  | 1 Municipal Manager Technical IGR/DDM meeting coordinated per quarter |  |  | 4 Municipal Manager Technical IGR/DDM meetings coordinated by 30 June 2023 |  | Quarterly |  |  | OMM | Not Achieved |  |  | Notice, Agenda, and Attendance register
| 94 | Number of Provincial Council for AIDS (PCA) presentations submitted to Office of the Premier by ZDM per quarter | Number | N/A |  |  | 1 Provincial Council for AIDS (PCA) presentation submitted to Office of the Premier by ZDM per quarter | 1 | Achieved | 1 Provincial Council for AIDS (PCA) presentation submitted to Office of the Premier by ZDM per quarter | 1 | Achieved | 1 Provincial Council for AIDS (PCA) presentation submitted to Office of the Premier by ZDM per quarter |  |  | 1 Provincial Council for AIDS (PCA) presentation submitted to Office of the Premier by ZDM per quarter |  |  | 4 Provincial Council for AIDS (PCA) presentations submitted to Office of the Premier by ZDM by 30 June 2023 |  | Quarterly |  |  | Community Services | Achieved |  |  | Copy of PCA presentations and proof submission
| 95 | Number of reports submitted to Community Services Portfolio Comittee on Civil Society Forum per quarter | Number | N/A |  |  | 1 report submitted to Community Services Portfolio Comittee on Civil Society Forum per quarter | 0 | Not Achieved | 1 report submitted to Community Services Portfolio Comittee on Civil Society Forum per quarter | 0 | Not Achieved | 1 report submitted to Community Services Portfolio Comittee on Civil Society Forum per quarter |  |  | 1 report submitted to Community Services Portfolio Comittee on Civil Society Forum per quarter |  |  | 4 reports submitted to Community Services Portfolio Committee on Civil Society Forum by 30 June 2023 |  | Quarterly |  |  | Community Services | Not Achieved |  |  | Proof of submission and copy of the report
| 96 | Number of ZDM EPWP forum meeting conducted per quarter | Number | N/A |  |  | 1 ZDM EPWP forum meeting conducted per quarter | 1 | Achieved | 1 ZDM EPWP forum meeting conducted per quarter | 1 | Achieved | 1 ZDM EPWP forum meeting conducted per quarter |  |  | 1 ZDM EPWP forum meeting conducted per quarter |  |  | 4 ZDM EPWP forum meetings conducted by 30 June 2023 |  | Quarterly |  |  | Community Services | Achieved |  |  | Notice, Agenda, and Attendance register
| 97 | Number of ZDM Tourism Forum meetings held per quarter | Number | N/A |  |  | 1 ZDM Tourism Forum meeting held per quarter | 1 | Achieved | 1 ZDM Tourism Forum meeting held per quarter | 1 | Achieved | 1 ZDM Tourism Forum meeting held per quarter |  |  | 1 ZDM Tourism Forum meeting held per quarter |  |  | 4 ZDM Tourism Forum meetings held by 30 June 2023 |  | Quarterly |  |  | Community Services | Achieved |  |  | Notice, Agenda, and Attendance register
| 98 | Number of ZDM District Youth Committee Meetings held per quarter | Number | N/A |  |  | 1 ZDM District Youth Committee Meeting held per quarter | 1 | Achieved | 1 ZDM District Youth Committee Meeting held per quarter | 1 | Achieved | 1 ZDM District Youth Committee Meeting held per quarter |  |  | 1 ZDM District Youth Committee Meeting held per quarter |  |  | 4 ZDM District Youth Committee Meetings held per quarter |  | Quarterly |  |  | OMM | Achieved |  |  | Notice, Agenda and Attendance register
| 99 | Date ZDM Youth in Business Seminar held | Date | N/A |  | new KPI | ZDM Youth in Business Seminar held by 30 Sep 2022 | 22 - 23 Sep 2022 | Achieved | N/A | Reported in Q1 | Reported in Q1 | N/A |  |  | N/A |  |  | ZDM Youth in Business Seminar held by 30 Sep 2022 |  | 30 Sep 2022 |  |  | OMM | Achieved |  |  | Notice, Agenda and Attendance register
| 100 | Date ZDM Youth Skills Development Program held | Date | N/A |  | new KPI | N/A | Due in Q4 | Due in Q4 | N/A | Due in Q4 | Due in Q4 | N/A |  |  | ZDM Youth Skills Development Program held by 30 June 2023 |  |  | ZDM Youth Skills Development Program held by 30 June 2023 |  | 30 Jun 2023 |  |  | OMM | Due in Q4 |  |  | Attendance register and Programme
Monitor and enhance compliance with health and safety standards to improve employee working conditions and the public | 101 | Number of funeral parlours inspected within ZDM per quarter | Number | N/A | SO 5.1.7 |  | 30 funeral parlours inspected within ZDM per quarter | 32 | Achieved | 30 funeral parlours inspected within ZDM per quarter | 34 | Achieved | 30 funeral parlours inspected within ZDM per quarter |  |  | 30 funeral parlours inspected within ZDM per quarter |  |  | 120 funeral parlours inspected within ZDM by 30 June 2023 |  | Quarterly |  |  | Community Services | Achieved |  |  | Summary of Inspection Register
| 102 | Number of water samples within ZDM collected for independent laboratory testing per quarter | Number | N/A |  |  | 20 water samples within ZDM collected for independent laboratory testing per quarter | 21 | Achieved | 20 water samples within ZDM collected for independent laboratory testing per quarter | 20 | Achieved | 20 water samples within ZDM collected for independent laboratory testing per quarter |  |  | 20 water samples within ZDM collected for independent laboratory testing per quarter |  |  | 80 water samples within ZDM collected for independent laboratory testing by 30 June 2023 |  | Quarterly |  |  | Community Service | Achieved |  |  | Copy of Lab results
| 103 | Number of food premises inspected within ZDM per quarter | Number | N/A |  |  | 60 food premises inspected within ZDM per quarter | 109 | Achieved | 60 food premises inspected within ZDM per quarter | 109 | Achieved | 60 food premises inspected within ZDM per quarter |  |  | 60 food premises inspected within ZDM per quarter |  |  | 240 food premises inspected within ZDM by 30 June 2023 |  | Quarterly |  |  | Community Services | Achieved |  |  | Summary of Inspection Register
| 104 | Number of food samples within ZDM collected for independent laboratory testing per quarter | Number |  |  |  | 20 food samples within ZDM collected for independent laboratory testing per quarter | 21 | Achieved | 20 food samples within ZDM collected for independent laboratory testing per quarter | 21 | Achieved | 20 food samples within ZDM collected for independent laboratory testing per quarter |  |  | 20 food samples within ZDM collected for independent laboratory testing per quarter |  |  | 80 food samples within ZDM collected for independent laboratory testing by 30 June 2023 |  | Quarterly |  |  | Community Services | Achieved |  |  | Copy of Lab Results
,
MUNICIPAL MANAGER
Note on C6: Mlungisi Ngcobo: Look at target within stds??
Note on C32: Mlungisi Ngcobo: Include: No of consumers who approached the municipality to make arrangements after disconnections
Note on H32: Mlungisi Ngcobo: Include: No of consumers who approached the municipality to make arrangements after disconnections
Note on K32: Mlungisi Ngcobo: Include: No of consumers who approached the municipality to make arrangements after disconnections
Note on N32: Mlungisi Ngcobo: Include: No of consumers who approached the municipality to make arrangements after disconnections
Note on Q32: Mlungisi Ngcobo: Include: No of consumers who approached the municipality to make arrangements after disconnections
Note on T32: Mlungisi Ngcobo: Include: No of consumers who approached the municipality to make arrangements after disconnections
Note on C103: Mlungisi Ngcobo: Insert to all depts
Note on H103: Mlungisi Ngcobo: Insert to all depts
Note on K103: Mlungisi Ngcobo: Insert to all depts
Note on N103: Mlungisi Ngcobo: Insert to all depts
Note on Q103: Mlungisi Ngcobo: Insert to all depts
Note on T103: Mlungisi Ngcobo: Insert to all depts
Note on C110: Mlungisi Ngcobo: Insert to all depts
Note on H110: Mlungisi Ngcobo: Insert to all depts
Note on K110: Mlungisi Ngcobo: Insert to all depts
Note on N110: Mlungisi Ngcobo: Insert to all depts
Note on Q110: Mlungisi Ngcobo: Insert to all depts
Note on T110: Mlungisi Ngcobo: Insert to all depts

## Quarter 1 Summary
ORGANIZATIONAL SUMMARY REPORT FOR QUARTER 1 2022/2023 : REPORT PER KPAs
KEY PERFORMANCE AREAS | Achieved | Not achieved | Total indicators per KPA
KPA 1 - BASIC SERVICE DELIVERY AND INFRASTRUCTURE | 7 | 3 | 10
KPA 2- LOCAL ECONOMIC DEVELOPMENT | 3 | 1 | 4
KPA 3 - MUNICIPAL FINANCIAL VIABILITY AND MANAGEMENT | 15 | 1 | 16
KPA 4 - GOOD GOVERNANCE AND PUBLIC PARTICIPATION | 6 | 0 | 6
KPA 05 -Municipal Transformation & Organizational Development | 36 | 3 | 39
TOTAL: | 67 | 8 | 75
Percentage: | 89% | 11%

## Quarter 2 Summary
ORGANIZATIONAL SUMMARY REPORT FOR QUARTER 2 2022/2023 : REPORT PER KPAs
KEY PERFORMANCE AREAS | Achieved | Not achieved | Total indicators per KPA
KPA 1 - BASIC SERVICE DELIVERY AND INFRASTRUCTURE | 5 | 5 | 10
KPA 2- LOCAL ECONOMIC DEVELOPMENT | 2 | 2 | 4
KPA 3 - MUNICIPAL FINANCIAL VIABILITY AND MANAGEMENT | 8 | 5 | 13
KPA 4 - GOOD GOVERNANCE AND PUBLIC PARTICIPATION | 6 | 0 | 6
KPA 05 -Municipal Transformation & Organizational Development | 31 | 2 | 33
TOTAL: | 52 | 14 | 66
Percentage: | 80% | 20%

## Q1 Summary (hidden)
SUMMARY REPORT FOR QUARTER 1 OF 2021/2022 : REPORT PER KPAs
|  | Due Indicators: | Achieved | Not achieved | Not reported/ Not due | Total indicators per KPA
| KPA 1 - BASIC SERVICE DELIVERY AND INFRASTRUCTURE | 13 | 10 | 3 | 3 | 16
| KPA 2 - MUNICIPAL TRANSFORMATION AND ORGANIZATIONAL DEVELOPMENT | 9 | 8 | 1 | 9 | 18
| KPA 3 - MUNICIPAL FINANCIAL VIABILITY AND MANAGEMENT | 9 | 1 | 8 | 4 | 13
| KPA 4 - GOOD GOVERNANCE AND PUBLIC PARTICIPATION | 48 | 33 | 15 | 21 | 69
| KPA 05 - LOCAL ECONOMIC DEVELOPMENT | 2 | 0 | 2 | 4 | 6
| TOTAL: | 81 | 52 | 29 | 41 | 122
| Percentage: |  | 64% | 36%

## Sheet4 (hidden)
| Achieved | Not achieved | Due Indicators:
KPA 1 - BASIC SERVICE DELIVERY AND INFRASTRUCTURE | 10 | 3 | 13
KPA 2 - MUNICIPAL TRANSFORMATION AND ORGANIZATIONAL DEVELOPMENT | 8 | 1 | 9
KPA 3 - MUNICIPAL FINANCIAL VIABILITY AND MANAGEMENT | 1 | 8 | 9
KPA 4 - GOOD GOVERNANCE AND PUBLIC PARTICIPATION | 33 | 15 | 48
KPA 05 - LOCAL ECONOMIC DEVELOPMENT | 0 | 2 | 2
TOTAL: | 52 | 29 | 81
Percentage: | 64% | 36%