## B&TO SDBIP
ZULULAND DISTRICT MUNICIPALITY 2022/2023
DEPARTMENTAL SERVICE DELIVERY AND BUDGET IMPLEMENTATION PLAN
KPA 1 - BASIC SERVICE DELIVERY AND INFRASTRUCTURE
Strategic Objective(SO) | KPI No. | Key Performance Indicator | Unit of Measure | Formula | Responsible Unit | IDP Strategies Objectives Ref No | QUARTERLY TARGETS | [13 empty] | target date / reporting frequency | Budget Allocated (2020/21) | Vote No. | QUARTER ONE | STATUS | REASON FOR VIARIANCE | MEASURES TAKEN TO IMPROVEME PERFORMANCE | Portolio of Evidence
[7 empty] | Target Q1 30 Sept 2023 | Actual Q 1 | POE | Target Q2 31 Dec 2023 | Actual Q2 | POE | Target Q3 31 March 2024 | Actual Q3 | POE | Target Q4 30 June 2024 | Actual Q4 | POE | Annual Target 01 July 2023 - 30 June 2024 | Annual Actual |  |  |  | ACTUAL
Continuously managing all existing infrastructure capital assets to minimize the total cost of owning and operating these assets. | 168 | Number of domestic water meters purchased | Number | N/A | Revenue | SO 1.1.1 | N/A |  |  | N/A |  |  | N/A |  |  | 500 domestic water meters purchased |  |  | 500 domestic water meters purchased by 30 June 2024 |  | 30 June 2024 | [6 empty] | Certificate of completion and Benificiary list with GPS coodinates
| 169 | Date verification on ZDM infrastructure assets performed | Date | N/A | Assets |  | N/A | Due in Quarter 4 | N/A | N/A |  |  | N/A | N/A |  | Verification on ZDM infrastructure assets performed by 30 June 2024 | N/A | N/A | Verification on ZDM infrastructure assets performed by 30 June 2024 |  | 30 June 2024 |  |  |  | Due in Quarter 4 |  |  | Engineers Certificate
KPA 02 - LOCAL ECONOMICS & SOCIAL DEVELOPMENT
Strategic Objective(SO) | KPI No. | Key Performance Indicator | Unit of Measure | Formula | Responsible Unit | IDP Strategies Objectives Ref No | Target Q1 30 Sept 2023 | Actual Q 1 | POE | Target Q2 31 Dec 2023 | Actual Q2 | POE | Target Q3 31 March 2024 | Actual Q3 | POE | Target Q4 30 June 2024 | Actual Q4 | POE | Annual Target 01 July 2022 - 30 June 2024 | Annual Actual | target date / reporting frequency |  |  |  | STATUS | REASON FOR VIARIANCE | MEASURES TAKEN TO IMPROVEME PERFORMANCE | Portolio of Evidence
Supporting the well-being of vulnerable groups through short and long term initiatives | 8 | Number of implementation reports on Indigent Policy submitted to EXCO per quarter | Number | N/A | Revenue | SO 2.2.5 | 1 implementation reports on Indigent Policy submitted to EXCO per quarter | 0 |  | 1 implementation reports on Indigent Policy submitted to EXCO per quarter | 1 implementation reports on Indigent Policy submitted to EXCO per quarter | 1 implementation reports on Indigent Policy submitted to EXCO per quarter | 1 implementation reports on Indigent Policy submitted to EXCO per quarter | 1 implementation reports on Indigent Policy submitted to EXCO per quarter | 1 implementation reports on Indigent Policy submitted to EXCO per quarter | 1 implementation reports on Indigent Policy submitted to EXCO per quarter |  |  | 4 implementation reports on Indigent Policy submitted to EXCO by 30 June 2024 |  | Quarterly | [6 empty] | Copy of Indigent Policy Implementation report and proof of submission
KPA 03 -MUNICIPAL FINANCIAL VIABILITY AND MANAGEMENT
Strategic Objective(SO) | KPI No. | Key Performance Indicator | Unit of Measure | Formula | Responsible Unit | IDP Strategies Objectives Ref No | Target Q1 30 Sept 2023 | Actual Q 1 | POE | Target Q2 31 Dec 2023 | Actual Q2 | POE | Target Q3 31 March 2024 | Actual Q3 | POE | Target Q4 30 June 2024 | Actual Q4 | POE | Annual Target 01 July 2022 - 30 June 2024 | Annual Actual | target date / reporting frequency |  |  |  | STATUS | REASON FOR VIARIANCE | MEASURES TAKEN TO IMPROVEME PERFORMANCE | Portolio of Evidence
Establishing and maintaining a sound and sustainable management of the fiscal and financial affairs of the municipality and its entities | 23 | Date Submission of Sec 54 (f) Mid Year Budget & Performance Assessment to the Council | Date | N/A | Budget &OMM | SO 3.1.1 | N/A | Due in Quarter 3 |  | N/A |  |  | Submission of Sec 54 (f) Mid Year Budget & Performance Assessment to the Council by 31 January 2024 |  |  | N/A |  |  | Submission of Sec 54(f) Mid Year Budget &Performance Assessment to the Council by 31 January 2024 |  | 2024-01-31 |  |  |  | Due in Quarter 3 |  |  | Council resolution and Copy of Sec 54 (f) Mid Year Budget & Performance Assessment
| 170 | Number of disconnection/ restriction reports submitted to CFO per quarter | Number | N/A | Revenue |  | 3 disconnections/ restrictions reports submitted to CFO per quarter | 63% |  | 3 disconnections/ restrictions reports submitted to CFO per quarter | 3 disconnection/ restriction reports submitted to CFO per quarter | 3 disconnection/ restriction reports submitted to CFO per quarter | 3 disconnections/ restrictions reports submitted to CFO per quarter | 3 disconnection/ restriction reports submitted to CFO per quarter | 3 disconnection/ restriction reports submitted to CFO per quarter | 3 disconnection/ restriction reports submitted to CFO per quarter |  |  | 12 disconnections/ restrictions reports submitted to CFO per quarter by 30 June 2024 |  | Quarterly |  |  |  | Not achieved |  |  | Disconnections/ restrictions reports and debtors age analysis report
| 27 | Number of reports on Irregular Expenditure submitted to EXCO per quarter | Number | N/A | SCM |  | I reports on Irregular Expenditure submitted to EXCO per quarter | 0 |  | I reports on Irregular Expenditure submitted to EXCO per quarter | I reports on Irregular Expenditure submitted to EXCO per quarter | I reports on Irregular Expenditure submitted to EXCO per quarter | I reports on Irregular Expenditure submitted to EXCO per quarter | I reports on Irregular Expenditure submitted to EXCO per quarter | I reports on Irregular Expenditure submitted to EXCO per quarter | I reports on Irregular Expenditure submitted to EXCO per quarter |  |  | 4 reports on Irregular Expenditure submitted to EXCO Committee by 30 June 2024 |  | Quarterly |  |  |  | Not achieved |  |  | Council resolution and Copy of Irregular Expenditure Report
| 171 | Date consolidated procurement plan submitted to MANCO | Date | N/A | SCM |  | Consolidated procurement plan submitted to MANCO by 31 Aug 2023 | 0 |  | N/A |  |  | N/A |  |  | N/A |  |  | Consolidated procurement plan submitted to MANCO by 31 August 2023 |  | 31 Aug 2023 |  |  |  | Not achieved |  |  | Copy of consolidated procurement plan and proof of submission
Apply sound financial management practises to keep a positive cash balance, coverage and liquidity ratios | 172 | Percentage of Implementation of the Financial Management Grant (FMG) expenditure per quarter | Percentage | N/A | budget | SO 3.1.2 | 25% Implementation of the Financial Management Grant (FMG) expenditure per quarter |  |  | 25% Implementation of the Financial Management Grant (FMG) expenditure per quarter | 25% Implementation of the Financial Management Grant (FMG) expenditure per quarter | 25% Implementation of the Financial Management Grant (FMG) expenditure per quarter | 25% Implementation of the Financial Management Grant (FMG) expenditure per quarter | 25% Implementation of the Financial Management Grant (FMG) expenditure per quarter | 25% Implementation of the Financial Management Grant (FMG) expenditure per quarter | 25% Implementation of the Financial Management Grant (FMG) expenditure per quarter |  |  | 100% Implementation of the Financial Management Grant (FMG) expenditure by 30 June 2024 |  | Quarterly | [6 empty] | Expenditure Reports
| 173 | Turnaround time for payment of creditors (days from date of receipt of invoice) | Days | N/A | Expenditure |  | Turnaround time for payment of creditors within 30 days |  |  | Turnaround time for payment of creditors within 30 days |  |  | Turnaround time for payment of creditors within 30 days |  |  | Turnaround time for payment of creditors within 30 days |  |  | Turnaround time for payment of creditors within 30 days, by 30 June 2024 |  | Quarterly | [6 empty] | Age Analysis
| 13 | Date reports on Sec 13 of the MFMA submitted to AG | Date | N/A | Budget |  | Reports on Sec 13 of the MFMA submitted to AG by 31 July 2023 |  |  | N/A | N/A | N/A | N/A |  |  | N/A |  |  | Reports on Sec 13 of the MFMA submitted to AG by 31 July 2023 |  | 2023-07-31 | [6 empty] | Proof of submission and copy of Sec 13 reports
Manage, monitor and review existing financial systems to support accurate and credible reporting, budget monitoring and compliance | 174 | Date verification report on ZDM movable and Fixed assets submitted to EXCO | Date | N/A | Assets | SO 3.1.3 | N/A |  |  | N/A | N/A | N/A | N/A |  |  | Verification report on ZDM movable and Fixed assets submitted to EXCO |  |  | Verification report on ZDM movable and Fixed assets submitted to EXCO by 30 June 2024 |  | 2024-06-30 | [6 empty] | Copy of Verification report on ZDM movable and fixed assets and Proof of submission
| 175 | Date adjustment Budget submitted to council | Date | N/A | budget |  | N/A | Due in Quarter 3 |  | N/A |  |  | Adjustment Budget submitted to council by 28 Feb 2024 |  |  | N/A |  |  | Adjustment Budget submitted to council by 28 Feb 2024 |  | 28-Feb-2024 |  |  |  | Due in Quarter 3 |  |  | Council Resolution and copy of adjustment Budget
| 27 | Date updates performed on the ZDM municipal fixed assets register | Number | N/A | Assets |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | Update performed on the ZDM municipal fixed assets register by 30 June 2023 |  |  | Update performed on the ZDM municipal fixed assets register by 30 June 2023 |  | 2023-06-30 |  |  |  | Not achieved |  |  | Updated FAR
| 176 | Number of updated grant registers submitted to EXCO per quarter | Number | N/A | Budget |  | 1 updated grant register submitted EXCO per quarter | Due in Quarter 4 |  | 1 updated grant register submitted EXCO per quarter | 1 updated grant register submitted EXCO per quarter | 1 updated grant register submitted EXCO per quarter | 1 updated grant register submitted EXCO per quarter | 1 updated grant register submitted EXCO per quarter | 1 updated grant register submitted EXCO per quarter | 1 updated grant register submitted EXCO per quarter |  |  | 4 updated grant registers submitted to EXCO by 30 June 2024 |  | Quarterly |  |  |  | Due in Quarter 4 |  |  | Copy of grant register and Proof of Submission
| 11 | Percentage of Collection Rate achieved per quarter | Percentage | N/A | Revenue |  | 60% Collection Rate achieved per quarter | 58% |  | 60% Collection Rate achieved per quarter |  |  | 60% Collection Rate achieved per quarter |  |  | 60% Collection Rate achieved per quarter |  |  | 60% Collection Rate achieved by 30 June 2024 |  | Quarterly |  |  |  | Not achieved |  |  | Copy of Collection report
| 177 | Date 2023/2024 IDP process plan including Budget timetable submitted to Council | Date | N/A | Budget & Planning |  | 2023/2024 IDP Process Plan including Budget time table submitted Council by 31 August 2023 | 2021-08-25 |  | N/A | N/A | N/A | N/A |  |  | N/A |  |  | 2023/2024 IDP Process Plan including Budget time table submitted Council by 31 August 2023 |  | 2023-08-31 |  |  |  | Achieved |  |  | Council resolution and copy of IDP process plan including budget timetable
| 178 | Date draft Budget submitted to Council | Date | N/A | Budget |  | N/A | Due in Quarter 3 |  | N/A |  |  | Draft Budget submitted to Council by 31 March 2024 |  |  | N/A |  |  | Draft Budget submitted to Council by 31 March 2024 |  | 31 Mar 2024 |  |  |  | Due in Quarter 3 |  |  | Council Resolution and copy of the draft budget
| 179 | Date Final Budget approved by Council | Date | N/A | Budget |  | N/A | Due in Quarter 4 |  | N/A |  |  | N/A |  |  | Final Budget approved by Council by 31 May 2024 |  |  | Final Budget approved by Council by 31 May 2024 |  | 31 May 2024 | Council Resolution |  |  | Due in Quarter 4 |  |  | Council Resolution and copy of the final budget
| 180 | Date draft budget related policies submitted to Council | Date | N/A | budget |  | N/A | Due in Quarter 3 |  | N/A |  |  | Draft budget related policies submitted to Council by 31 March 2024 |  |  | N/A |  |  | Draft budget related policies submitted by 31 Mar 2024 |  | 31 Mar 2024 | Council Resolution |  |  | Due in Quarter 3 |  |  | Council Resolution and copy of draft budget related policies
| 181 | Date final budget related policies submitted to Council | Date | N/A | budget |  | N/A | Due in Quarter 4 |  | N/A |  |  | N/A |  |  | Final budget related policies submitted to Council by 30 June 2024 |  |  | Final budget related policies submitted to Council by 30 June 2024 |  | 30 June 2024 |  |  |  | Due in Quarter 4 |  |  | Council Resolution and copy of final budget related policies
| 182 | Number of MSCOA data strings uploaded to Local Government portal per quarter | Number | N/A | Budget |  | 3 MSCOA data strings uploaded to Local Government portal per quarter | 3 |  | 3 MSCOA data strings uploaded to Local Government portal per quarter |  |  | 3 MSCOA data strings uploaded to Local Government portal per quarter |  |  | 3 MSCOA data strings uploaded to Local Government portal per quarter |  |  | 12 MSCOA data strings uploaded to LG portal by 30 June 2024 |  | Quarterly |  |  |  | Achieved |  |  | Print screen of system upload and copy of data strings
| 183 | Date of Submission of Sec 72 Mid - Year Budget & Performance Assessment to the Mayor & Provincial Treasury | DATE | N/A | Budget |  | N/A | Due in Quarter 3 |  | N/A |  |  | Submission of Sec 72 Mid - Year Budget & Performance Assessment to the Mayor & Provincial Treasury by 25 January 2024 |  |  | N/A |  |  | Submission of Sec 72 Mid Year Budget & Performance Assessment to the Mayor & Provincial Treasury by 25 January 2024 |  | 25 January 2024 | [6 empty] | Proof of submission and copy of Sec72 Mid - Year Budget & Performance Assessment
| 14 | Number of sec 52 reports submitted to council and PT per quarter | Number | N/A | Budget |  | 1 sec 52 reports submitted to council and PT per quarter | 0 |  | 1 sec 52 reports submitted to council and PT per quarter | 1 sec 52 reports submitted to council and PT per quarter | 1 sec 52 reports submitted to council and PT per quarter | 1 sec 52 reports submitted to council and PT per quarter | 1 sec 52 reports submitted to council and PT per quarter | 1 sec 52 reports submitted to council and PT per quarter | 1 sec 52 reports submitted to council and PT per quarter |  |  | 4 sec 52 reports submitted to council and PT per quarter |  | Quarterly |  |  |  | Not achieved |  |  | Proof of submission Council resolution and copy of sec 52 report
| 184 | Number of sec 66 reports submitted to Council per quarter | Number | N/A | Expenditure |  | 3 Sec 66 reports submitted to Council per quarter | Section 71 submitted |  | 3 Sec 66 reports submitted to Council per quarter |  |  | 3 Sec 66 reports submitted to Council per quarter |  |  | 3 Sec 66 reports submitted to Council per quarter |  |  | 12 Sec 66 reports submitted to Council by 30 June 2024 |  | Quarterly |  |  |  | Not achieved | Refer to section 71 |  | Proof of submission and Soft copy of Sec 66 report
| 185 | Number of Sec 11 reports submitted to Council, Provincial Treasury and Auditor General per quarter | Number | N/A | Budget |  | 1 Sec 11 report submitted to Council, Provincial Treasury and Auditor General per quarter | 0 |  | 1 Sec 11 report submitted to Council, Provincial Treasury and Auditor General per quarter |  |  | 1 Sec 11 report submitted to Council, Provincial Treasury and Auditor General per quarter |  |  | 1 Sec 11 report submitted to Council, Provincial Treasury and Auditor General per quarter |  |  | 4 Sec 11 reports submitted to Council, Provincial Treasury and Auditor General by 30 June 2024 |  | Quarterly |  |  | Budget & Treasury | Not Achieved |  |  | Council Resolution; Proof of submission and Soft copy of Sec 11 reports
| 186 | Number of monthly budget statement (sec 71 reports) submitted to Mayor and Provincial Treasury per quarter | Number | N/A | Budget |  | 3 monthly budget statement (sec 71 reports) submitted to Mayor and Provincial Treasury per quarter | 3 monthly budget statement (sec 71 reports) submitted to Mayor and Provincial Treasury per quarter | 3 monthly budget statement (sec 71 reports) submitted to Mayor and Provincial Treasury per quarter | 3 monthly budget statement (sec 71 reports) submitted to Mayor and Provincial Treasury per quarter | 3 monthly budget statement (sec 71 reports) submitted to Mayor and Provincial Treasury per quarter | 3 monthly budget statement (sec 71 reports) submitted to Mayor and Provincial Treasury per quarter | 3 monthly budget statement (sec 71 reports) submitted to Mayor and Provincial Treasury per quarter | 3 monthly budget statement (sec 71 reports) submitted to Mayor and Provincial Treasury per quarter | 3 monthly budget statement (sec 71 reports) submitted to Mayor and Provincial Treasury per quarter | 3 monthly budget statement (sec 71 reports) submitted to Mayor and Provincial Treasury per quarter |  |  | 12 monthly budget statement (sec 71 reports) submitted to Mayor and Provincial Treasury by 30 June 2024 |  | Quarterly | [6 empty] | Proof of submission and Soft copy of Sec 71 report
| 187 | Number of reconciliation performed (debtors; creditors; bank; assets; ledger & Suspense account) per quarter | Number | N/A | Revenue and Expenditure |  | 18 reconciliation performed (debtors; creditors; bank; assets; ledger & Suspense account) per quarter | 9 |  | 18 reconciliation performed (debtors; creditors; bank; assets; ledger & Suspense account) per quarter |  |  | 18 reconciliation performed (debtors; creditors; bank; assets; ledger & Suspense account) per quarter |  |  | 18 reconciliation performed (debtors; creditors; bank; assets; ledger & Suspense account) per quarter |  |  | 72 reconciliation performed (debtors; creditors; bank; assets; ledger & Suspense account) by 30 June 2024 |  | Quarterly | [6 empty] | Monthly Recons
Refine procurement systems and processes to respond to the demand for services | 188 | Percentage of tenders finalised within 3 months after date of advertisement per quarter | Percentage | N/A | SCM | SO 3.1.4 | 100% of tenders finalised within 3 months after date of advertisement per quarter | 0 |  | 100% of tenders finalised within 3 months after date of advertisement per quarter |  |  | 100% of tenders finalised within 3 months after date of advertisement per quarter |  |  | 100% of tenders finalised within 3 months after date of advertisement per quarter |  |  | 100% of tenders finalised within 3 months after date of advertisement by 30 June 2024 |  | Quarterly |  |  | Budget & Treasury | Not Achieved |  |  | Adverts and Intention to Award
| 189 | Number of stock taking reports submitted to EXCO per quarter | Number | N/A | SCM |  | 1 stock taking report submitted to EXCO per quarter | 0 |  | 1 stock taking report submitted to EXCO per quarter | 1 stock taking reports submitted to EXCO per quarter | 1 stock taking reports submitted to EXCO per quarter | 1 stock taking report submitted to EXCO per quarter |  |  | 1 stock taking report submitted to EXCO per quarter |  |  | 4 stock taking reports submitted to EXCO by 30 June 2024 |  | Quarterly |  |  |  | Not achieved |  |  | Copy of Stock taking reports and proof of submission
| 15 | Number of SCM quarterly reports submitted to EXCO per quarter | Number | N/A | SCM |  | 1 SCM quarterly report submitted to EXCO per quarter | 0 |  | 1 SCM quarterly report submitted to EXCO per quarter |  |  | 1 SCM quarterly report submitted to EXCO per quarter |  |  | 1 SCM quarterly report submitted to EXCO per quarter |  |  | 4 SCM quarterly reports submitted to EXCO by 30 June 2024 |  | Quarterly |  |  |  | Not achieved |  |  | Proof of submission and Copy of SCM Quarterly reports
| 175 | Percentage of the Level of Cash Backed Conditional grants | Percentage | N/A | Budget |  | N/A | Due in Quarter 4 |  | N/A |  |  | N/A |  |  | 100% Level of Cash Backed Conditional grants |  |  | 100% Level of Cash Backed Conditional grants by 30 June 2023 |  | 30 Jun 2023 |  |  |  | Due in Quarter 4 |  |  | Expenditure Reports
| 176 | Net Debtors Days collected per quarter | Days | N/A | Revenue |  | Net Debtors Days collected within 30 days per quarter | 5773 |  | Net Debtors Days collected within 30 days per quarter |  |  | Net Debtors Days collected within 30 days per quarter |  |  | Net Debtors Days collected within 30 days per quarter |  |  | Net Debtors Days collected within 30 days, by 30 June 2023 |  | Quarterly |  |  |  | Not achieved |  |  | Age Analysis
| 178 | Number sec 52 reports submitted to PT per quarter | Date | N/A | Budget | SO 3.1.3 | 1 Sec 52 report submitted to PT per quarter | 0 |  | 1 Sec 52 report submitted to PT per quarter |  |  | 1 Sec 52 report submitted to PT per quarter |  |  | 1 Sec 52 report submitted to PT per quarter |  |  | 4 Sec 52 reports submitted to PT by 30 June 2023 |  | Quarterly |  |  |  | Not achieved |  |  | Proof of submission and copy of sec 52 report
Refine procurement systems and processes to respond to the demand for services | 180 | Number of reports on use of section 36 of SCM regulations submitted to EXCO | Number | N/A | SCM | SO 3.1.4 | 1 report on use of section 36 of SCM regulations submitted to EXCO per quarter | 0 |  | 1 report on use of section 36 of SCM regulations submitted to EXCO per quarter |  |  | 1 report on use of section 36 of SCM regulations submitted to EXCO per quarter |  |  | 1 report on use of section 36 of SCM regulations submitted to EXCO per quarter |  |  | 4 reports on use of section 36 of SCM regulations submitted to EXCO by 30 June 20223 |  | Quarterly |  |  |  | Not achieved |  |  | Proof of submission and copy of Section 36 of SCM regulations report
KPA 04- GOOD GOVERNANCE & PUBLIC PARTICIPATION
Strategic Objective(SO) | KPI No. | Key Performance Indicator | Unit of Measure | Formula | Responsible Unit | IDP Strategies Objectives Ref No | Target Q1 30 Sept 2023 | Actual Q 1 | POE | Target Q2 31 Dec 2023 | Actual Q2 | POE | Target Q3 31 March 2024 | Actual Q3 | POE | Target Q4 30 June 2024 | Actual Q4 | POE | Annual Target 01 July 2023- 30 June 2024 | Annual Actual | target date / reporting frequency |  |  |  | STATUS | REASON FOR VIARIANCE | MEASURES TAKEN TO IMPROVEME PERFORMANCE | Portolio of Evidence
Effectively handling community enquiries and responding through an effective customer care service | 190 | Number of reports on billing submitted to EXCO per quarter | Number | N/A | Revenue | SO 4.1.1 | 3 reports on billing submitted to EXCO per quarter | 3 |  | 3 reports on billing submitted to EXCO per quarter | 3 reports on billing submitted to EXCO per quarter | 3 reports on billing submitted to EXCO per quarter | 3 reports on billing submitted to EXCO per quarter | 3 reports on billing submitted to EXCO per quarter | 3 reports on billing submitted to EXCO per quarter | 3 reports on billing submitted to EXCO per quarter |  |  | 12 reports on billing EXCO by 30 Jun 2024 |  | Quarterly |  |  |  | Achieved |  |  | Billing Report and proof of submission
Monitor, review and progressively improve service delivery performance through improvement of business and systems, performance auditing, risk management and oversight | 191 | Number of revenue steering committee held per quarter | Number | N/A | Revenue | SO 4.1.4 | 1 revenue steering committee held per quarter | 1 revenue steering committee held per quarter | 1 revenue steering committee held per quarter | 1 revenue steering committee held per quarter | 1 revenue steering committee held per quarter | 1 revenue steering committee held per quarter | 1 revenue steering committee held per quarter | 1 revenue steering committee held per quarter | 1 revenue steering committee held per quarter | 1 revenue steering committee held per quarter |  |  | 4 revenue steering committee held by 30 June 2024 |  | Quarterly | [6 empty] | Notice, Agenda, nd attendance register
| 192 | MSTA Sec 79 (1) Number of budget steering committee meetings held per quarter | Number | N/A | Budget |  | 1 budget steering meeting held per quarter | 1 |  | 1 budget steering meeting held per quarter |  |  | 1 budget steering meeting held per quarter |  |  | 1 budget steering meeting held per quarter |  |  | 4 budget steering committee meetings held by 30 Jun 2024 |  | Quarterly |  |  |  | Not Achieved | need more POE |  | Notice, Agenda, and attendance register
| 193 | Number of departmental meetings held per quarter | Number | N/A | CFO |  | 3 departmental meetings held per quarter |  |  | 3 departmental meetings held per quarter |  |  | 3 departmental meetings held per quarter |  |  | 3 departmental meetings held per quarter |  |  | 12 departmental meetings held per quarter |  | Quarterly | [6 empty] | Notice, Agenda, and attendance register
| 194 | Number of reports on updated investment register submitted to EXCO per quarter | Number | N/A | Budget |  | 3 reports on updated investment register submitted to EXCO per quarter |  |  | 3 reports on updated investment register submitted to EXCO per quarter |  |  | 3 reports on updated investment register submitted to EXCO per quarter | 3 reports on updated investment register submitted to EXCO per quarter | 3 reports on updated investment register submitted to EXCO per quarter | 3 reports on updated investment register submitted to EXCO per quarter |  |  | 12 reports on updated investment register submitted to EXCO by 30 June 2024 |  | Quarterly |  |  |  | Not achieved |  |  | Updated Investment Register and Proof of Submission
| 184 | Number of bid adjudication committee meetings attended per quarter | Number | N/A | SCM |  | 1 bid adjudication committee meetings attended per quarter | 1 |  | 1 bid adjudication committee meetings attended per quarter |  |  | 1 bid adjudication committee meetings attended per quarter |  |  | 1 bid adjudication committee meetings attended per quarter |  |  | 4 bid adjudication committee meetings attended by 30 June 2022 |  | Quarterly |  |  |  | Achieved | need POE |  | Attendance register, Agenda, minutes, and notice
KPA 05 - MUNICIPAL TRANSFORMATION & ORGANISATIONAL BEHAVIOUR
Strategic Objective(SO) | KPI No. | Key Performance Indicator | Unit of Measure | Formula | Responsible Unit | IDP Strategies Objectives Ref No | Target Q1 30 Sept 2023 | Actual Q 1 | POE | Target Q2 31 Dec 2023 | Actual Q2 | POE | Target Q3 31 March 2024 | Actual Q3 | POE | Target Q4 30 June 2024 | Actual Q4 | POE | Annual Target 01 July 2023- 30 June 2024 | Annual Actual | target date / reporting frequency |  |  |  | STATUS | REASON FOR VIARIANCE | MEASURES TAKEN TO IMPROVEME PERFORMANCE | Portolio of Evidence
Optimize workforce productivity enforcing a sound organizational culture | 195 | Date 2022/2023 AFS submitted to AG | Date | N/A | CFO | SO 5.1.3 | 2022/2023 AFS submitted to AG by 31 Aug 2023 | 2021-08-31 |  | N/A |  |  | N/A |  |  | N/A |  |  | 2022/2023 AFS submitted to AG by 31 Aug 2023 |  | 31 Aug 2023 |  |  |  | Achieved |  |  | Proof of submission and copy of AFS
| 196 | Date AFS audit opinion 2022/2023 achieved | Date | N/A | CFO |  | N/A | Due in Quarter 2 |  | AFS audit opinion 2022/2023 achieved by 31 December 2023 |  |  | N/A |  |  | N/A |  |  | AFS audit opinion 2022/2023 achieved by 31 December 2023 |  | 31 Dec 2023 |  |  | Budget & Treasury | Due in Quarter 2 |  |  | Audit Report
Note on C14: Mlungisi Ngcobo: Include: No of consumers who approached the municipality to make arrangements after disconnections
Note on H14: Mlungisi Ngcobo: Include: No of consumers who approached the municipality to make arrangements after disconnections
Note on K14: Mlungisi Ngcobo: Include: No of consumers who approached the municipality to make arrangements after disconnections
Note on L14: Mlungisi Ngcobo: Include: No of consumers who approached the municipality to make arrangements after disconnections
Note on M14: Mlungisi Ngcobo: Include: No of consumers who approached the municipality to make arrangements after disconnections
Note on N14: Mlungisi Ngcobo: Include: No of consumers who approached the municipality to make arrangements after disconnections
Note on O14: Mlungisi Ngcobo: Include: No of consumers who approached the municipality to make arrangements after disconnections
Note on P14: Mlungisi Ngcobo: Include: No of consumers who approached the municipality to make arrangements after disconnections
Note on Q14: Mlungisi Ngcobo: Include: No of consumers who approached the municipality to make arrangements after disconnections
Note on T14: Mlungisi Ngcobo: Include: No of consumers who approached the municipality to make arrangements after disconnections