## TOP LAYER
TOP LAYER -SERVICE DELIVERY AND BUDGET IMPLEMENTATION PLAN (SDBIP) - ZULULAND DISTRICT MUNICIPALITY - 2024/2025
KPI NO. | PROGRAM DRIVER | OUTCOME | IDP Strategic Objective Ref No. | STRATEGY | PROJECTS | LOCAL MUNICIPALITY | INDICATOR | BASELINE | ANNUAL TARGET | ACCUMULATIVE /NON-ACCUMULATIVE5 | UNIT OF MEASURE | Q1 -Target 30.9.2024 | Q2 - Target 31.12.2024 | Q3-Target 30.3.2025 | Q3 Actual | Q3 Status | REASON FOR VARIANCE | MEASURE OF IMPROVEMENT | Q4 - Target 30.6.2025 | Q4 Actual | Q4 Status | REASON FOR VARIANCE | MEASURE OF IMPROVEMENT | PORTFOLIO OF EVIDENCE
B2B PILLAR 2: BASIC SERVICE DELIVERY
KPA 1: BASIC SERVICE DELIVERY= 10 indicators
1 | HOD (PLANNING) | Access to the full package of municipal services offered to the community is efficient, affordable,economical, acceptable quality, sustainable and supports economic growth | SO 1.2.1 | Establishing and maintaining partnerships with government and private sector to accelerate provision of universal, equitable & consistent access to the municipal services that local communities are entitled to. | Water Infrastructures Supply | ALL | Number of households within ZDM to be provided with access to water within RDP standard per quarter | 722 | 800 households within ZDM to be provided with access to water within RDP standard by 30 June 2025 | Accumulative | Number | 200 households within ZDM to be provided with access to water within RDP standard per quarter | 200 households within ZDM to be provided with access to water within RDP standard per quarter | 200 households within ZDM to be provided with access to water within RDP standard per quarter |  |  |  |  | 200 households within ZDM to be provided with access to water within RDP standard per quarter |  |  |  | Q3 | List of beneficiaries and GPS co-ordinates
2 | HOD (PLANNING) |  |  |  | Water Infrastructures Supply | ALL | Number of ZDM water contracts completed annually |  | 15 ZDM contracts completed by 30 June 2025 | Non - Accumulative | Number | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 15 ZDM contracts completed by 30 June 2025 |  |  |  |  | Certificate of completion
3 | HOD (PLANNING) |  |  |  | Water Infrastructures Supply | ALL | Number of ZDM water contracts under construction annually |  | 28 ZDM water contracts under construction by 30 June 2025 | Non - Accumulative | Number | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 28 ZDM water contracts under construction by 30 June 2025 |  |  |  |  | Contract lists and appointment letters of service providers
4 | HOD (TECH) |  |  |  | Bulk Water | ALL | Percentage of kilolitres produced by ZDM water treatment plants per quarter | New indicator | 70% kilolitres produced by ZDM water treatment plants by 30 June 2025 | Accumulative | Percentage | 70% kilolitres produced by ZDM water treatment plants per quarter | 70% kilolitres produced by ZDM water treatment plants per quarter | 70% kilolitres produced by ZDM water treatment plants per quarter |  |  |  |  | 70% kilolitres produced by ZDM water treatment plants per quarter |  |  |  |  | Monthly production report
5 | HOD (TECH) |  |  |  | Water Quality Sampling | ALL | Percentage of ZDM Water determinants that pass laboratory tests per quarter | 92% | 85% ZDM Water determinants that pass laboratory tests by 30 June 2025 | Non - Accumulative | Percentage | 85% ZDM Water determinants that pass laboratory tests per quarter | 85% ZDM Water determinants that pass laboratory tests per quarter | 85% ZDM Water determinants that pass laboratory tests per quarter |  |  |  |  | 85% ZDM Water determinants that pass laboratory tests per quarter |  |  |  |  | Lab results
6 | HOD (TECH) | All categories of Municipal Infrastructure and resources are stable and maintained | SO 1.1.1 | Continuously managing all existing infrastructure capital assets to minimize the total cost of owning and operating these assets | Operations and Maintenance | ALL | The average time taken to fix spillages per quarter | 28hrs | 24Hrs average time taken to fix spillages by 30 June 2025 | Non - Accumulative | Hours | 24Hrs average time taken to fix spillages per quarter | 24Hrs average time taken to fix spillages per quarter | 24Hrs average time taken to fix spillages per quarter |  |  |  |  | 24Hrs average time taken to fix spillages per quarter |  |  |  |  | Job card summary report
7 | HOD (TECH) |  |  |  |  | ALL | The average time taken to suck septic tanks within ZDM per quarter |  | 24Hrs taken to suck septic tanks within ZDM by 30 June 2025 | Non - Accumulative | Hours | 24Hrs taken to suck septic tanks within ZDM per quarter | 24Hrs taken to suck septic tanks within ZDM per quarter | 24Hrs taken to suck septic tanks within ZDM per quarter |  |  |  |  | 24Hrs taken to suck septic tanks within ZDM per quarter |  |  |  |  | Job cards summary report
8 | HOD (FINANCE) | [5 empty] | Date verification on ZDM infrastructure assets performed |  | Verification on ZDM infrastructure assets performed by 30 June 2025 | Non - Accumulative | Date | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Verification on ZDM infrastructure assets performed by 30 June 2025 |  |  |  |  | Engineers Certificate
9 | HOD (PLANNING) | Access to the full package of municipal services offered to the community is efficient, affordable,economical, acceptable quality, sustainable and supports economic growth | SO 1.2.1 | Establishing and maintaining partnerships with government and private sector to accelerate provision of universal, equitable & consistent access to the municipal services that local communities are entitled to. | Water Infrastructures Supply | ALL | Number of assessment report of ZDM water service provider (contractors) performed per quarter |  | 4 assessment report of ZDM water service provider (contractors) performed by 30 June 2025 | Non - Accumulative | Number | 1 assessment report of ZDM water service provider (contractors) performed per quarter | 1 assessment report of ZDM water service provider (contractors) performed per quarter | 1 assessment report of ZDM water service provider (contractors) performed per quarter |  |  |  |  | 1 assessment report of ZDM water service provider (contractors) performed per quarter |  |  |  |  | Assessment Report
10 | HOD (PLANNING) | [5 empty] | Number of assessment report of ZDM water service provider (consultants) performed per quarter |  | 4 assessment report of ZDM water service provider (consultants) performed by 30 June 2025 | Non - Accumulative | Number | 1 assessment report of ZDM water service provider (consultants) performed per quarter | 1 assessment report of ZDM water service provider (consultants) performed per quarter | 1 assessment report of ZDM water service provider (consultants) performed per quarter |  |  |  |  | 1 assessment report of ZDM water service provider (consultants) performed per quarter |  |  |  |  | Assessment Report
KPI NO. | PROGRAM DRIVER | OUTCOME | IDP Strategic Objective Ref No. | STRATEGY | PROJECTS | LOCAL MUNICIPALITY | INDICATOR | BASELINE | ANNUAL TARGET | ACCUMULATIVE /NON-ACCUMULATIVE5 | UNIT OF MEASURE | Q1 -Target 30.9.2024 | Q2 - Target 31.12.2024 | Q3-Target 30.3.2025 |  |  |  |  | Q4 - Target 30.6.2025 |  | ANNUAL BUDGET |  |  | PORTFOLIO OF EVIDENCE
B2B PILLAR 5: BUILDING CAPABLE LOCAL GOVERNMENT INSTITUTIONS
KPA2: LOCAL ECONOMIC & SOCIAL DEVELOPMENT = 14 indicators
11 | HOD (COMMUNITY) | The overall economic and social conditions of the district are conducive for the creation of employment opportunities | SO 2.1.1 | Support SMMEs and create opportunities for growth | LED | ALL | Number of SMMEs / Co-operatives supported annually | New indicator | 10 SMMEs / Co-operatives supported by 30 June 2025 | Non - Accumulative | Number | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 10 of SMMEs / Co-operatives supported by 30 June 2025 |  |  |  |  | List of supported SMMEs and signed distribution form
12 | HOD (COMMUNITY) | Arts culture and heritage is preserved | SO 2.4.1 | Promoting arts, culture and heritage | Tourism | ALL | Number of tourism awareness campaigns held per quarter | 4 | 20 tourism awareness campaigns held by 30 June 2025 | Accumulative | Number | 5 tourism awareness campaigns held per quarter | 5 tourism awareness campaigns held per quarter | 5 tourism awareness campaigns held per quarter |  |  |  |  | 5 tourism awareness campaigns held per quarter |  |  |  |  | OOP and Attendance Register
13 | HOD (COMMUNITY) |  |  |  | Indonsa | ALL | Number of students trained in music within ZDM annually |  | 30 Students trained in music within ZDM by 30 June 2025 | Non - Accumulative | Number | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 30 Students trained in music within ZDM by 30 June 2025 |  |  |  |  | Graduation ceremony list
14 | HOD (COMMUNITY) |  |  |  | Indonsa | ALL | Number of students trained in drama within ZDM annually |  | 35 Students trained in drama within ZDM by 30 June 2025 | Non - Accumulative | Number | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 35 Students trained in drama within ZDM by 30 June 2025 |  |  |  |  | Graduation ceremony list
15 | HOD (COMMUNITY) |  |  |  | Indonsa | ALL | Number of students within ZDM trained in visual art annually |  | 10 students within ZDM trained in visual art by 30 June 2025 | Non - Accumulative | Number | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 10 students within ZDM trained in visual art by 30 June 2025 |  |  |  |  | Graduation ceremony list
16 | HOD (COMMUNITY) |  |  |  | Indonsa | ALL | Number of students within ZDM trained in fashion design annually |  | 35 students within ZDM trained in fashion design by 30 June 2025 | Non - Accumulative | Number | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 35 students within ZDM trained in fashion design by 30 June 2025 |  |  |  |  | Graduation ceremony list
17 | COO | Effects of poverty is minimised | SO 2.2.1 | Alleviate poverty and promote socio-economic development | Special Programmes | ALL | Number of Special Programmes implemented annually | New indicator | 2 Special Programmes implemented by 30 June 2025 | Non - Accumulative | Number | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2 Special Programmes implemented by 30 June 2025 |  |  |  |  | Programmes; Attendance registers and Pictures
18 | HOD (FINANCE) |  |  |  | Reduction of poverty | ALL | Number of implementation reports on Indigent Policy submitted to EXCO per quarter | 4 | 4 implementation reports on Indigent Policy submitted to EXCO by 30 June 2025 | Accumulative | Number | 1 implementation report on Indigent Policy submitted to EXCO per quarter | 1 implementation report on Indigent Policy submitted to EXCO per quarter | 1 implementation report on Indigent Policy submitted to EXCO per quarter |  |  |  |  | 1 implementation report on Indigent Policy submitted to EXCO per quarter |  | 0 |  |  | Copy of Indigent Policy Implementation report and proof of submission
19 | HOD (COMMUNITY) |  |  |  |  | ALL | Number of jobs created through the ZDM municipal EPWP initiatives including capital projects | 1200 | 1370 jobs created through the ZDM municipal EPWP initiatives including capital projects by 30 June 2025 | Non - Accumulative | Number | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1370 jobs created through the ZDM municipal EPWP initiatives including capital projects by 30 June 2025 |  |  |  |  | Report retrieved from the EPWP system
20 | HOD (COMMUNITY) |  | SO 2.3.1 | Regulating, monitoring and evaluating compliance of service providers to municipal health standards | Health Awareness Campaigns | ALL | Number of funeral parlours inspected within ZDM per quarter |  | 140 funeral parlours inspected within ZDM by 30 June 2025 | Accumulative | Number | 35 funeral parlours inspected within ZDM per quarter | 35 funeral parlours inspected within ZDM per quarter | 35 funeral parlours inspected within ZDM per quarter |  |  |  |  | 35 funeral parlours inspected within ZDM per quarter |  |  |  |  | Summary of Inspection Register
21 | HOD (COMMUNITY) | Promoting and maximising social and economic development |  |  |  | ALL | Number of food premises inspected within ZDM per quarter |  | 192 food premises inspected within ZDM by 30 June 2025 | Accumulative | Number | 48 food premises inspected within ZDM per quarter | 48 food premises inspected within ZDM per quarter | 48 food premises inspected within ZDM per quarter |  |  |  |  | 48 food premises inspected within ZDM per quarter |  |  |  |  | Summary of Inspection Register
22 | HOD (COMMUNITY) |  |  |  |  | ALL | Number of water samples within ZDM collected for independent laboratory testing per quarter |  | 96 water samples within ZDM collected for independent laboratory testing by 30 June 2025 | Accumulative | Number | 24 water samples within ZDM collected for independent laboratory testing per quarter | 24 water samples within ZDM collected for independent laboratory testing per quarter | 24 water samples within ZDM collected for independent laboratory testing per quarter |  |  |  |  | 24 water samples within ZDM collected for independent laboratory testing per quarter |  |  |  |  | Summary of Inspection Register
23 | HOD (COMMUNITY) |  |  |  |  | ALL | Number of food samples within ZDM collected for independent laboratory testing per quarter |  | 96 food samples within ZDM collected for independent laboratory testing by 30 June 2025 | Accumulative | Number | 24 food samples within ZDM collected for independent laboratory testing per quarter | 24 food samples within ZDM collected for independent laboratory testing per quarter | 24 food samples within ZDM collected for independent laboratory testing per quarter |  |  |  |  | 24 food samples within ZDM collected for independent laboratory testing per quarter |  |  |  |  | Summary of Inspection Register
24 | HOD (COMMUNITY) | The health of Zululand communities and citizens is improved |  |  |  | ALL | Number of ZDM Municipal Health awareness campaigns held per quarter | 8 | 20 ZDM Municipal Health awareness campaigns held by 30 June 2025 | Accumulative | Number | 5 ZDM Municipal Health awareness campaigns held per quarter | 5 ZDM Municipal Health awareness campaigns held per quarter | 5 ZDM Municipal Health awareness campaigns held per quarter |  |  |  |  | 5 ZDM Municipal Health awareness campaigns held per quarter |  |  |  |  | OOP and Attendance Register
KPI NO. | PROGRAM DRIVER | OUTCOME | IDP Strategic Objective Ref No. | STRATEGY | PROJECTS | LOCAL MUNICIPALITY | INDICATOR | BASELINE | ANNUAL TARGET | ACCUMULATIVE /NON-ACCUMULATIVE5 | UNIT OF MEASURE | Q1 -Target 30.9.2024 | Q2 - Target 31.12.2024 | Q3-Target 30.3.2025 |  |  |  |  | Q4 - Target 30.6.2025 |  | ANNUAL BUDGET |  |  | PORTFOLIO OF EVIDENCE
B2B PILLAR 4: SOUND FINANCIAL MANAGEMENT
KPA 3: MUNICIPAL FINANCIAL VIABILITY AND MANAGEMENT = 09 indicators
25 | HOD (FINANCE) | The Municipality is financially viable with sound financial management | SO 3.1.1 | Establishing and maintaining a sound and sustainable management of the fiscal and financial affairs of the municipality and its entities. | Debt Collection | ALL | Percentage of Collection Rate achieved per quarter | 60% | 60% Collection Rate achieved by 30 June 2025 | Non - Accumulative | Percentage | 60% Collection Rate achieved per quarter | 60% Collection Rate achieved per quarter | 60% Collection Rate achieved per quarter |  |  |  |  | 60% Collection Rate achieved per quarter |  |  |  |  | Copy of Collection Report
26 | HOD(CORP) |  |  |  | Training & Development | ALL | Percentage of budget spent on implementing WSP |  | 100% of budget spent on implementing WSP by 30 June 2025 | Non - Accumulative | Percentage | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 100% of budget spent on implementing WSP by 30 June 2025 |  |  |  |  | Expenditure report
27 | HOD (FINANCE) |  | SO 3.1.2 | Apply sound financial management practises to keep a positive cash balance, coverage and liquidity ratios | Financial; Administration | ALL | Date Report on Sec 13 of the MFMA submitted to AG | 31 Jul 2022 | Report on Sec 13 of the MFMA submitted to AG by 31 July 2024 | Non - Accumulative | Date | Report on Sec 13 of the MFMA submitted to AG by 31 July 2024 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | Proof of submission and copy of Sec 13 report
28 | HOD (FINANCE) |  | SO 3.1.3 | Manage, monitor and review existing financial systems to support accurate and credible reporting, budget monitoring and compliance | On going process | ALL | Number of Sec 52 reports submitted to Council and Provincial Treasury per quarter | 4 | 4 Sec 52 reports submitted to Council and Provincial Treasury by 30 June 2025 | Accumulative | Number | 1 Sec 52 report submitted to Council and Provincial Treasury per quarter | 1 Sec 52 report submitted to Council and Provincial Treasury per quarter | 1 Sec 52 report submitted to Council and Provincial Treasury per quarter |  |  |  |  | 1 Sec 52 report submitted to Council and Provincial Treasury per quarter |  |  |  |  | Council Resolution and copy of Sec 52 report
29 | HOD (PLANNING) |  |  |  | On going process | ALL | Date 2024/2025 IDP process plan including Budget timetable submitted to Council |  | 2024/2025 IDP Process Plan including Budget time table submitted Council by 31 August 2024 | Non - Accumulative | Date | 2024/2025 IDP Process Plan including Budget time table submitted Council by 31 August 2024 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | Council resolution and copy of IDP process plan including budget timetable
30 | HOD (FINANCE) |  |  |  | On going process | ALL | Date of Submission of Sec 72 Mid - Year Budget & Performance Assessment to the Mayor & Provincial Treasury |  | Submission of Sec 72 Mid Year Budget & Performance Assessment to the Mayor & Provincial Treasury by 25 January 2025 | Non - Accumulative | Date | N/A | N/A | Submission of Sec 72 Mid Year Budget & Performance Assessment to the Mayor & Provincial Treasury by 25 January 2025 |  |  |  |  | N/A |  |  |  |  | Proof of submission and copy of Sec72 Mid - Year Budget & Performance Assessment
31 | HOD (FINANCE) |  |  |  | On going process | ALL | Date adjustment Budget submitted to council |  | Adjustment Budget submitted to council by 28 Feb 2025 | Non - Accumulative | Date | N/A | N/A | Adjustment Budget submitted to council by 28 Feb 2025 |  |  |  |  | N/A |  |  |  |  | Council Resolution and copy of adjustment Budget
32 | HOD (FINANCE) |  |  |  | On going process | ALL | Date Final Budget approved by Council |  | Final Budget approved by Council by 31 May 2025 | Non - Accumulative | Date | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Final Budget approved by Council by 31 May 2025 |  |  |  |  | Council Resolution and copy of the final budget
33 | HOD (FINANCE) |  | SO 3.1.4 | Refine procurement systems and processes to respond to the demand for services | Revision of the SCM policy | ALL | Number of SCM quarterly reports submitted to EXCO per quarter | 4 | 4 SCM quarterly reports submitted to EXCO by 30 June 2025 | Accumulative | Number | 1 SCM quarterly report submitted to EXCO per quarter | 1 SCM quarterly report submitted to EXCO per quarter | 1 SCM quarterly report submitted to EXCO per quarter |  |  |  |  | 1 SCM quarterly report submitted to EXCO per quarter |  |  |  |  | Proof of submission and Copy of SCM Quarterly reports
KPI NO. | PROGRAM DRIVER | OUTCOME | IDP Strategic Objective Ref No. | STRATEGY | PROJECTS | LOCAL MUNICIPALITY | INDICATOR | BASELINE | ANNUAL TARGET | ACCUMULATIVE /NON-ACCUMULATIVE5 | UNIT OF MEASURE | Q1 -Target 30.9.2024 | Q2 - Target 31.12.2024 | Q3-Target 30.3.2025 |  |  |  |  | Q4 - Target 30.6.2025 |  | ANNUAL BUDGET |  |  | PORTFOLIO OF EVIDENCE
B2B PILLAR 3: GOOD GOVERNANCE
KPA 4: GOOD GOVERNANCE AND PUBLIC PARTICIPATION = 06 indicators
34 | COO |  | SO4.1.2 | Promoting transparent and accountable governance through regular community engagements and effective administration | LEGAL | ALL | Number of reports on legal functions submitted to MM per quarter | New indicator | 4 report on legal functions submitted to MM by 30 June 2025 | Accumulative | Number | 1 report on legal functions submitted to MM per quarter | 1 report on legal functions submitted to MM per quarter | 1 report on legal functions submitted to MM per quarter |  |  |  |  | 1 report on legal functions submitted to MM per quarter |  |  |  |  | Proof of submission and report
35 | COO |  |  |  | Communications | ALL | Number of ZDM newsletter published per quarter |  | 4 ZDM newsletter published by 30 June 2025 | Accumulative | Number | 1 ZDM newsletter published per quarter | 1 ZDM newsletter published per quarter | 1 ZDM newsletter published per quarter |  |  |  |  | 1 ZDM newsletter published per quarter |  |  |  |  | Newsletters
36 | COO |  |  |  | Budget and IDP Roadshow | ALL | Number of Community engagements held Bia annual | New indicator | 8 Community engagements held Bia annual | Accumulative | Number | N/A | 4 Community engagement held Bia annual | N/A | N/A | N/A | N/A | N/A | 4 Community engagements held Bia annual |  |  |  |  | Notice, OOP, And copy of report
37 | HOD (COMMUNITY) |  | 4.1.3 | Systematic development and or review and monitoring implementation of all municipal policies, bylaws, strategies, plans and frameworks in line with any applicable legislation | LED | ALL | Number of implementation reports on the ZDM LED strategy submitted to Community Services Portfolio Committee per quarter |  | 4 implementation reports on the ZDM LED strategy submitted to Community Serives Portfolio Committee by 30 June 2025 | Accumulative | Number | 1 implementation report on the ZDM LED strategy submitted to Community Services Portfolio Committee per quarter | 1 implementation report on the ZDM LED strategy submitted to Community Services Portfolio Committee per quarter | 1 implementation report on the ZDM LED strategy submitted to Community Services Portfolio Committee per quarter |  |  |  |  | 1 implementation report on the ZDM LED strategy submitted to Community Services Portfolio Committee per quarter |  |  |  |  | Copy of report and proof of submission
38 | COO |  | SO 4.1.4 | Monitoring, review and progressively improve service delivery performance through improvement of business processes and systems, performance auditing, risk management and oversight | Auditing | ALL | Number of reports tabled by the Audit Comm Chairperson to Council | New indicator | 2 reports tabled by the Audit Comm Chairperson to Council by 30 June 2025 | Accumulative | Number | 1 reports tabled by the Audit Comm Chairperson to Council by 30 Sept 2024 | N/A | 1 reports tabled by the Audit Comm Chairperson to Council by 31 March 2025 |  |  |  |  | N/A |  |  |  |  | Council agenda and copy of report
39 | HOD (CORP) |  |  |  | Council Support | ALL | Number of MPAC meetings coordinated per quarter |  | 4 MPAC meetings coordinated by 30 June 2025 | Accumulative | Number | 1 MPAC meeting coordinated per quarter | 1 MPAC meeting coordinated per quarter | 1 MPAC meeting coordinated per quarter |  |  |  |  | 1 MPAC meeting coordinated per quarter |  |  |  |  | Notice, Agenda and attendance register
KPI NO. | PROGRAM DRIVER | OUTCOME | IDP Strategic Objective Ref No. | STRATEGY | PROJECTS | LOCAL MUNICIPALITY | INDICATOR | BASELINE | ANNUAL TARGET | ACCUMULATIVE /NON-ACCUMULATIVE5 | UNIT OF MEASURE | Q1 -Target 30.9.2024 | Q2 - Target 31.12.2024 | Q3-Target 30.3.2025 |  |  |  |  | Q4 - Target 30.6.2025 |  | ANNUAL BUDGET |  |  | PORTFOLIO OF EVIDENCE
KPA 5: MUNICIPAL TRANSFORMATION & ORGANIZATIONAL DEVELOPMENT = 06 indicators
40 | HOD (CORP) | The municipality is adequately resourced with a skilled workforce capable of carrying out its developmental mandate. Strong career pathing is achieved | SO 5.1.1 | Investing in a workforce to meet service delivery demand through implementing a culture of continuous learning and improvement | Employee Assistance Programme | ALL | Number of EAP health awareness campaign conducted per quarter | New indicator | 4 EAP health awareness campaign conducted by 30 June 2025 | Accumulative | Number | 1 EAP health awareness campaign conducted per quarter | 1 EAP health awareness campaign conducted per quarter | 1 EAP health awareness campaign conducted per quarter |  |  |  |  | 1 EAP health awareness campaign conducted per quarter |  |  |  |  | Notice, OOP, Attendance register and Copy of Presentation
41 | HOD (CORP) |  |  |  | Training & Development | ALL | Date WSP report submitted to LGSETA |  | WSP report submitted to LGSETA by 30 June 2025 | Non-Accumulative | Date | N/A | N/A | N/A | N/A | N/A | N/A | N/A | WSP report submitted to LGSETA by 30 June 2025 |  |  |  |  | Copy of WSP Report and Proof of submission
42 | HOD (CORP) |  | SO 5.1.2 | Promoting sound labour relations through promoting effective human resource practises | Training & Development | ALL | Date employment equity reports submitted to Department of Labour |  | Employment equity reports submitted to Department of Labour by 15 Jan 2025 | Non-Accumulative | Date | N/A | N/A | Employment equity reports submitted to Department of Labour by 15 Jan 2025 |  |  |  |  | N/A |  |  |  |  | Proof of submission and copy of employment equity plan report
43 | COO |  | SO 5.1.5 | Establishing consistency and alignment between the district and locals by regular co-ordination of Intergovernmental Relations | DDM | ALL | Number of Municipal Manager Technical IGR/DDM meetings coordinated per quarter | 2023-06-04 | 4 Municipal Manager Technical IGR/DDM meetings coordinated by 30 June 2025 | Accumulative | Number | 1 Municipal Manager Technical IGR/DDM meeting coordinated per quarter | 1 Municipal Manager Technical IGR/DDM meeting coordinated per quarter | 1 Municipal Manager Technical IGR/DDM meeting coordinated per quarter |  |  |  |  | 1 Municipal Manager Technical IGR/DDM meeting coordinated per quarter |  |  |  |  | Notice, Agenda and Attendance Register
44 | HOD (FINANCE) |  | SO 5.1.3 | Optimize workforce productivity enforcing a sound organizational culture | Auditing | ALL | Date 2023/2024 AFS submitted to AG |  | 2023/2024 AFS submitted to AG by 31 Aug 2024 | Non-Accumulative | Date | 2023/2024 AFS submitted to AG by 31 Aug 2024 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | Proof of submission and copy of AFS
45 | HOD (COM) |  |  |  | EPWP | ALL | Date of submission of narrative 2023/2024 Annual Report on EPWP to Department of Public Works |  | Submission on narrative 2023/2024 Annual Report on EPWP to Department of Public Works by 15 July 2024 | Non-Accumulative | Date | Submission on narrative 2023/2024 Annual Report on EPWP to Department of Public Works by 15 July 2024 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | Proof of submission and copy of report
KPI NO. | PROGRAM DRIVER | OUTCOME | IDP Strategic Objective Ref No. | STRATEGY | PROJECTS | LOCAL MUNICIPALITY | INDICATOR | BASELINE | ANNUAL TARGET | ACCUMULATIVE /NON-ACCUMULATIVE5 | UNIT OF MEASURE | Q1 -Target 30.9.2024 | Q2 - Target 31.12.2024 | Q3-Target 30.3.2025 |  |  |  |  | Q4 - Target 30.6.2025 |  | ANNUAL BUDGET |  |  | PORTFOLIO OF EVIDENCE
Spatial Planning & Environmental Management
KPA 6: CROSS CUTTING INTERVENTIONS = 01 indicators
46 | HOD (COM) | Disasters are prevented and dealt with effectively where they occur | SO 6.1.2 | Promoting and conserving the natural environment through land use management policies, plans and frameworks. | Disaster Management | ALL | Number of lightning conductors installed in identified rural households within ZDM per quarter | 120 | 60 of lightning conductors installed in identified rural households within ZDM by 30 June 2025 | Accumulative | Number | N/A | N/A | N/A |  |  |  |  | 60 of lightning conductors installed in identified rural households within ZDM by 30 June 2025 |  |  |  |  | Certificate of compliance and Beneficiary list with GPS coordinates
|  |  | Status | Total Key Perfomance Indicators-per KPA
|  | 100% KPI met |  | KPA 1-BSD=10 Indicators | [5 empty] | MR RN HLONGWA
|  | KPI not measured |  | KPA2-LED= 14 indicators
|  | KPI Almost met 75-100% |  | KPA3-MFVM=09 indicators | [5 empty] | Municipal Manager
|  | KPI not met 75% and less |  | KPA4-GG= 06 indicators
KPA5-MTOD= 06 indicators
|  | KPI extremely well met |  | KPA6-CC-= 01 indicators
|  | Total indicators |  | 46 KPIs