## Community Serv
ZULULAND DISTRICT MUNICIPALITY 2024/2025
DEPARTMENTAL SERVICE DELIVERY AND BUDGET IMPLEMENTATION PLAN: GENERAL MANAGER COMMUNITY SERVICES
KPA 01 - BASIC SERVICE DELIVERY AND INFRASTRUCTURE
Strategic Objective(SO) | KPI No. | Key Performance Indicator | Unit of Measure | Formula | Responsible Unit | IDP Strategic Objective Ref No. | QUARTERLY TARGETS | [13 empty] | target date / reporting frequency | Budget Allocated (2020/21) | Vote No. | QUARTER ONE | STATUS | REASON FOR VIARIANCE | MEASURES TAKEN TO IMPROVEME PERFORMANCE | Portolio of Evidence
[7 empty] | Target Q1 30 Sep 2024 | Actual Q 1 | Q1 Status | Target Q2 31 Dec 2024 | Actual Q2 | POE | Target Q3 31 Mar 2025 | Actual Q3 | POE | Target Q4 30 Jun 2025 | Actual Q4 | POE | Annual Target | Annual Actual |  |  |  | ACTUAL
Strategic Objective(SO) | KPI No. | Key Performance Indicator | Unit of Measure | Formula | Responsible Unit | IDP Strategic Objective Ref No. | QUARTERLY TARGETS | [13 empty] | target date / reporting frequency | Budget Allocated (2020/21) | Vote No. | QUARTER ONE | STATUS | REASON FOR VIARIANCE | MEASURES TAKEN TO IMPROVEME PERFORMANCE | Portolio of Evidence
[7 empty] | Target Q1 30 Sep 2022 | Actual Q 2 | POE | Target Q2 31 Dec 2022 | Actual Q3 | POE | Target Q3 31 Mar 2023 | Actual Q4 | POE | Target Q4 30 Jun 2023 | Actual Q5 | POE | Annual Target | Annual Actual |  |  |  | ACTUAL
KPA 02 - LOCAL ECONOMIC & SOCIAL DEVELOPMENT
Strategic Objective(SO) | KPI No. | Key Performance Indicator | Unit of Measure | Formula | Responsible Unit | IDP Strategic Objective Ref No. | Target Q1 30 Sep 2024 | Actual Q 1 | Q1 Status | Target Q2 31 Dec 2024 |  |  | Target Q3 31 Mar 2025 |  |  | Target Q4 30 Jun 2025 |  |  | Annual Target |  | target date / reporting frequency |  |  |  | STATUS | REASON FOR VIARIANCE | MEASURES TAKEN TO IMPROVEME PERFORMANCE | Portolio of Evidence
Support SMMEs and create opportunities for growth | 5 | Number of SMMEs / Co-oparatives supported annually | Number | N/A | LED | SO 2.1.1 | N/A | N/A | Due in Q4 | N/A |  |  | N/A |  |  | 10 of SMMEs / Co-oparatives supported by 30 June 2025 |  |  | 10 SMMEs / Co-oparatives supported by 30 June 2025 |  | 2025-06-30 | [6 empty] | List of supported SMMEs and signed distribution form
Establishing strategic linkages | 95 | Number of ZDM LED forum meetings held per quarter | Number | N/A | LED | SO 2.1.3 | 1 ZDM LED forum meeting held per quarter |  |  | 1 ZDM LED forum meeting held per quarter |  |  | 1 ZDM LED forum meeting held per quarter |  |  | 1 ZDM LED forum meeting held per quarter |  |  | 4 ZDM LED forum meetings held by 30 June 2025 |  | Quarterly | [6 empty] | Notice, Agenda, and attendance register
Supporting the well-being of vulnerable groups through short and long term initiatives | 9 | Number of jobs created through the ZDM municipal EPWP initiatives including capital projects | Number | N/A | EPWP | SO 2.2.5 | N/A | N/A | Due in Q4 | N/A |  |  | N/A |  |  | 1370 jobs created through the ZDM municipal EPWP initiatives including capital projects |  |  | 1370 jobs created through the ZDM municipal EPWP initiatives including capital projects by 30 June 2025 |  | 2025-06-30 |  |  |  | Due in Quarter 4 |  |  | Report retrieved from the EPWP system
| 96 | Number of jobs maintained through ZDM EPWP integrated grant projects | Number | N/A | EPWP |  | N/A | N/A | Due in Q4 | N/A |  |  | N/A |  |  | 600 of jobs maintained through the EPWP integrated grant projects |  |  | 600 jobs maintained through ZDM EPWP integrated grant projects by 30 June 2025 |  | 2025-06-30 |  |  |  | Due in Quarter 4 |  |  | List of participants retrieved from HR system
Regulating, monitoring and evaluating compliance of service providers to municipal health standards | 10 | Number of ZDM Municipal Health awareness campaigns per quarter | Number | N/A | Municipal Health | SO 2.3.1 | 5 Municipal Health awareness campaign per quarter |  |  | 5 Municipal Health awareness campaign per quarter |  |  | 5 Municipal Health awareness campaign per quarter |  |  | 5 Municipal Health awareness campaign per quarter |  |  | 20 Municipal Health awareness campaigns by 30 June 2025 |  | Quarterly |  |  |  | Achieved |  |  | OOP and Attendance Register
| 97 | Number of funeral parlours inspected within ZDM per quarter | Number | N/A | Municipal Health |  | 35 funeral parlours inspected within ZDM per quarter |  |  | 35 funeral parlours inspected within ZDM per quarter | 10 funeral parlours inspected within ZDM per quarter | 11 funeral parlours inspected within ZDM per quarter | 35 funeral parlours inspected within ZDM per quarter | 13 funeral parlours inspected within ZDM per quarter | 14 funeral parlours inspected within ZDM per quarter | 35 funeral parlours inspected within ZDM per quarter |  |  | 140 funeral parlours inspected within ZDM by 30 June 2025 |  | quarterly | [6 empty] | Summary of Inspection Register
| 98 | Number of food premises inspected within ZDM per quarter | Number | N/A | Municipal Health |  | 48 food premises inspected within ZDM per quarter |  |  | 48 food premises inspected within ZDM per quarter | 13 food premises inspected within ZDM per quarter | 14 food premises inspected within ZDM per quarter | 48 food premises inspected within ZDM per quarter | 16 food premises inspected within ZDM per quarter | 17 food premises inspected within ZDM per quarter | 48 food premises inspected within ZDM per quarter |  |  | 192 food premises inspected within ZDM by 30 June 2025 |  | quarterly | [6 empty] | Summary of Inspection Register
| 99 | Number of water samples within ZDM collected for independent laboratory testing per quarter | Number | N/A | Municipal Health |  | 24 water samples within ZDM collected for independent laboratory testing per quarter |  |  | 24 water samples within ZDM collected for independent laboratory testing per quarter | 6 water samples within ZDM collected for independent laboratory testing per quarter | 7 water samples within ZDM collected for independent laboratory testing per quarter | 24 water samples within ZDM collected for independent laboratory testing per quarter | 9 water samples within ZDM collected for independent laboratory testing per quarter | 10 water samples within ZDM collected for independent laboratory testing per quarter | 24 water samples within ZDM collected for independent laboratory testing per quarter |  |  | 96 water samples within ZDM collected for independent laboratory testing by 30 June 2025 |  | quartely | [6 empty] | Copy of Lab results
| 100 | Number of food samples within ZDM collected for independent laboratory testing per quarter | Number | N/A | Municipal Health |  | 24 food samples within ZDM collected for independent laboratory testing per quarter |  |  | 24 food samples within ZDM collected for independent laboratory testing per quarter | 6 food samples within ZDM collected for independent laboratory testing per quarter | 7 food samples within ZDM collected for independent laboratory testing per quarter | 24 food samples within ZDM collected for independent laboratory testing per quarter | 9 food samples within ZDM collected for independent laboratory testing per quarter | 10 food samples within ZDM collected for independent laboratory testing per quarter | 24 food samples within ZDM collected for independent laboratory testing per quarter |  |  | 96 food samples within ZDM collected for independent laboratory testing by 30 June 2025 |  | quartely | [6 empty] | Copy of Lab results
Promoting arts, culture and heritage | 6 | Number of tourism awareness campaigns held per quarter | Number | N/A | Tourism |  | 1 tourism awareness campaigns held per quarter |  |  | 1 tourism awareness campaigns held per quarter | 5 tourism awareness campaigns held per quarter | 6 tourism awareness campaigns held per quarter | 1 tourism awareness campaigns held per quarter | 8 tourism awareness campaigns held per quarter | 9 tourism awareness campaigns held per quarter | 1 tourism awareness campaigns held per quarter | 2 tourism awareness campaigns held per quarter | 3 tourism awareness campaigns held per quarter | 4 tourism awareness campaigns held by 30 June 2025 |  | Quarterly | [6 empty] | OOP and Attendance Register
| 101 | Number of quarterly reports on the implementation of Tourism & Markerting Strategy submitted to Community Services Portfolio Committee | Number | N/A | Tourism | SO2.4.1 | 1 quarterly reports on the implementation of Tourism & Markerting Strategy submitted to Community Services Portfolio Committee |  |  | 1 quarterly reports on the implementation of Tourism & Markerting Strategy submitted to Community Services Portfolio Commiitee | 5 quarterly reports on the implementation of Tourism & Markerting Strategy submitted to Community Services Portfolio Commiitee | 6 quarterly reports on the implementation of Tourism & Markerting Strategy submitted to Community Services Portfolio Commiitee | 1 quarterly reports on the implementation of Tourism & Markerting Strategy submitted to Community Services Portfolio Commiitee | 8 quarterly reports on the implementation of Tourism & Markerting Strategy submitted to Community Services Portfolio Commiitee | 9 quarterly reports on the implementation of Tourism & Markerting Strategy submitted to Community Services Portfolio Commiitee | 1 quarterly reports on the implementation of Tourism & Markerting Strategy submitted to Community Services Portfolio Commiitee | 11 quarterly reports on the implementation of Tourism & Markerting Strategy submitted to Community Services Portfolio Commiitee | 12 quarterly reports on the implementation of Tourism & Markerting Strategy submitted to Community Services Portfolio Commiitee | 4 quarterly reports on the implementation of Tourism & Markerting Strategy submitted to Community Services Portfolio Commiitee by 30 June 2025 |  | Quarterly | [6 empty] | Copy of implementation reports on Tourism & Markerting Strategy and proof of submission
| 102 | Number of students trained in music within ZDM annually | Number | N/A | Indonsa |  | N/A | N/A | Due in Q4 | N/A |  |  | N/A |  |  | 7 Students trained in music within ZDM by 30 June 2025 |  |  | 7 Students trained in music within ZDM by 30 June 2025 |  | 2025-06-30 | [6 empty] | Graduation ceremony list
| 103 | Number of students trained in drama within ZDM annually | Number | N/A | Indonsa |  | N/A | N/A | Due in Q4 | N/A |  |  | N/A |  |  | 20 Students trained in drama within ZDM by 30 June 2025 |  |  | 20 Students trained in drama within ZDM by 30 June 2025 |  | 2025-06-30 |  |  |  | Due in Quarter 4 |  |  | Graduation ceremony list
| 104 | Number of students within ZDM trained in visual art annually | Number | N/A | Indonsa |  | N/A | N/A | Due in Q4 | N/A |  |  | N/A |  |  | 7 students within ZDM trained in visual art by 30 June 2025 |  |  | 7 students within ZDM trained in visual art by 30 June 2025 |  | 2025-06-30 |  |  |  | Due in Quarter 4 |  |  | Graduation ceremony list
| 105 | Number of students within ZDM trained in fashion design annually | Number | N/A | Indonsa |  | N/A | N/A | Due in Q4 | N/A |  |  | N/A |  |  | 20 students within ZDM trained in fashion design by 30 June 2025 |  |  | 20 students within ZDM trained in fashion design by 30 June 2025 |  | 2025-06-30 |  |  |  | Due in Quarter 4 |  |  | Graduation ceremony list
| 106 | Date artists recorded at Indonsa art and craft centre recording studio | Number | N/A | Indonsa |  | N/A | N/A | Due in Q4 | N/A |  |  | N/A |  |  | Artists recorded at Indonsa art and craft centre recording studio by 30 June 2025 |  |  | Artists recorded at Indonsa art and craft centre recording studio by 30 June 2025 |  | 2025-06-30 |  |  |  | Due in Quarter 4 |  |  | Copy of demo recorded
Strategic Objective(SO) | KPI No. | Key Performance Indicator | Unit of Measure | Formula | Responsible Unit | IDP Strategic Objective Ref No. | Target Q1 30 Sep 2024 | Actual Q 1 | Q1 Status | Target Q2 31 Dec 2024 |  |  | Target Q3 31 Mar 2025 |  |  | Target Q4 30 Jun 2025 |  |  | Annual Target |  | target date / reporting frequency |  |  |  | STATUS | REASON FOR VIARIANCE | MEASURES TAKEN TO IMPROVEME PERFORMANCE | Portolio of Evidence
Apply sound financial management practises to keep a positive cash balance, coverage and liquidity ratios | 107 | Percentage for Indonsa art and craft centre grant spent | Percentage | N/A | Indonsa | SO 3.1.2 | N/A | N/A | Due in Q4 | N/A |  |  | N/A |  |  | 100% for Indonsa art and craft centre grant spent per quarter |  |  | 100% for Indonsa art and craft centre grant spent by 30 June 2025 |  | 2025-06-30 |  |  |  | Due in Quarter 4 |  |  | Expenditure report
| 108 | Percentage spent on the EPWP grant per quarter | Percentage | N/A | EPWP |  | 25% spent on the EPWP grant per quarter |  |  | 25% spent on the EPWP grant per quarter |  |  | 25% spent on the EPWP grant per quarter |  |  | 25% spent on the EPWP grant per quarter |  |  | 100% spent on the EPWP grant by 30 June 2025 |  | Quarterly |  |  |  | Achieved |  |  | Expenditure report
KPA 04 - GOOD GOVERNANCE AND PUBLIC PARTICIPATION
Strategic Objective(SO) | KPI No. | Key Performance Indicator | Unit of Measure | Formula | Responsible Unit | IDP Strategic Objective Ref No. | Target Q1 30 Sep 2024 | Actual Q 1 | Q1 Status | Target Q2 31 Dec 2024 |  |  | Target Q3 31 Mar 2025 |  |  | Target Q4 30 Jun 2025 |  |  | Annual Target |  | target date / reporting frequency |  |  |  | STATUS | REASON FOR VIARIANCE | MEASURES TAKEN TO IMPROVEME PERFORMANCE | Portolio of Evidence
Promoting transparent and accountable governance through regular community engagements and effective administration | 109 | Number of school visits on Tourism Markerting per quarter | Number | N/A | Tourism | SO 4.1.2 | 5 school visits on Tourism Markerting per quarter |  |  | 5 school visits on Tourism Markerting per quarter | 9 school visits per quarter | 10 school visits per quarter | 5 school visits on Tourism Markerting per quarter | 12 school visits per quarter | 13 school visits per quarter | 5 school visits on Tourism Markerting per quarter | 15 school visits per quarter | 16 school visits per quarter | 20 school visits on Tourism Markerting by 30 June 2025 |  | Quarterly | [6 empty] | Attendance register
Systematic development and or review and monitoring implementation of all municipal policies, bylaws, strategies, plans and frameworks in line with any applicable legislation | 110 | Number of implementation reports on the ZDM LED strategy submitted to Community Services Portfolio Committee per quarter | Number | N/A | LED | SO 4.1.3 | 1 implementation report on the ZDM LED strategy submitted to Community Services Portfolio Committee per quarter |  |  | 1 implementation report on the ZDM LED strategy submitted to Community Services Portfolio Committee per quarter |  |  | 1 implementation report on the ZDM LED strategy submitted to Community Services Portfolio Committee per quarter |  |  | 1 implementation report on the ZDM LED strategy submitted to Community Services Portfolio Committee per quarter |  |  | 4 implementation reports on the ZDM LED strategy submitted to Community Serives Portfolio Committee by 30 June 2025 |  | Quarterly | [6 empty] | Copy of report and proof of submission
| 111 | Number of progress reports on Indonsa Arts & Craft Centre business strategy submitted to Community Services Portfolio Committee per quarter | Number | N/A | Indonsa |  | 1 progress report on Indonsa Arts & Craft Centre business strategy submitted to Community Services Portfolio Committee per quarter |  |  | 1 progress report on Indonsa Arts & Craft Centre business strategy submitted to Community Services Portfolio Committee per quarter |  |  | 1 progress report on Indonsa Arts & Craft Centre business strategy submitted to Community Services Portfolio Committee per quarter |  |  | 1 progress report on Indonsa Arts & Craft Centre business strategy submitted to Community Services Portfolio Committee per quarter |  |  | 4 progress reports on Indonsa Arts & Craft Centre business strategy submitted to Community Services Portfolio Committee by 30 June 2025 |  | Quarterly | [6 empty] | Copy of progress reports on Indonsa Arts & Crafts Centre business strategy and proof of submission
KPA 05 - MUNICIPAL TRANSFORMATION AND ORGANIZATIONAL DEVELOPMENT
Strategic Objective(SO) | KPI No. | Key Performance Indicator | Unit of Measure | Formula | Responsible Unit | IDP Strategic Objective Ref No. | Target Q1 30 Sep 2024 | Actual Q 1 | POE | Target Q2 31 Dec 2024 |  |  | Target Q3 31 Mar 2025 |  |  | Target Q4 30 Jun 2025 |  |  | Annual Target |  | target date / reporting frequency |  |  |  | STATUS | REASON FOR VIARIANCE | MEASURES TAKEN TO IMPROVEME PERFORMANCE | Portolio of Evidence
Promoting sound labour relations through promoting effective human resource practises | 112 | Number of departmental meetings coordinated per quarter | Number | N/A | HOD | SO 5.1.2 | 3 departmental meetings coordinated per quarter | 3 |  | 3 departmental meetings coordinated per quarter |  |  | 3 departmental meetings coordinated per quarter |  |  | 3 departmental meetings coordinated per quarter |  |  | 12 departmental meetings coordinated by 30 June 2024 |  | Quarterly |  |  |  | Achieved |  |  | Notice, Agenda, and Attendance Register
Optimise workforce productivity by enforcing a sound organizational culture | 113 | Date of submission of narrative 2023/2024 Annual Report on EPWP to Department of Public Works | Date | N/A | EPWP | SO 5.1.3 | Submission on narrative 2023/2024 Annual Report on EPWP to Department of Public Works by 15 July 2024 | Q4 |  | N/A |  |  | N/A |  |  | N/A |  |  | Submission on narrative 2023/2024 Annual Report on EPWP to Department of Public Works by 15 July 2024 |  | 15-Jul-24 |  |  | Community Services | Q4 |  |  | Proof of submission and copy of report
| 114 | Number of District monthly statistics report submissions to Provincial Department of Health per quarter | Number | N/A | Municipal Health |  | 10 District monthly statistics report submissions to Provincial Department of Health per quarter |  |  | 10 District monthly statistics report submissions to Provincial Department of Health per quarter |  |  | 10 District monthly statistics report submissions to Provincial Department of Health per quarter |  |  | 10 District monthly statistics report submissions to Provincial Department of Health per quarter |  |  | 40 District monthly statistics report submissions to Provincial Department of Health by 30 June 2025 |  | Quarterly | [6 empty] | Proof of Submission and soft copy of district monthly statistics report
| 115 | Number of Quarterly evaluation reports on Integrated grant EPWP submitted to Department of Public Works per quarter | Number | N/A | EPWP |  | 1 Quarterly evaluation report on Integrated grant EPWP submitted to Department of Public Works per quarter |  |  | 1 Quarterly evaluation report on Integrated grant EPWP submitted to Department of Public Works per quarter |  |  | 1 Quarterly evaluation report on Integrated grant EPWP submitted to Department of Public Works per quarter |  |  | 1 Quarterly evaluation report on Integrated grant EPWP submitted to Department of Public Works per quarter |  |  | 4 Quarterly evaluation reports on Integrated grant EPWP submitted to Department of Public Works by 30 June 2025 |  | Quarterly | [6 empty] | Proof of submission and Quarterly evaluation reports
| 116 | Number of integrated grant Expenditure reports submitted to the Department of Public Works per quarter | Number | N/A | EPWP |  | 3 integrated grant Expenditure reports submitted to the Department of Public Works per quarter | 3 |  | 3 integrated grant Expenditure reports submitted to the Department of Public Works per quarter |  |  | 3 integrated grant Expenditure reports submitted to the Department of Public Works per quarter |  |  | 3 integrated grant Expenditure reports submitted to the Department of Public Works per quarter |  |  | 12 integrated grant Expenditure reports submitted to the Department of Public Works by 30 June 2025 |  | Quarterly |  |  |  | Achieved |  |  | Acknowledgment of receipts and copies of expenditure reports
| 117 | Number of progress reports compiled and submitted to the Community Portfolio Committee on implementation of ZDM EPWP per quarter | Number | N/A | EPWP |  | 1 progress report compiled and submitted to the Community Portfolio Committee on implementation of ZDM EPWP per quarter | 1 |  | 1 progress report compiled and submitted to the Community Portfolio Committee on implementation of ZDM EPWP per quarter |  |  | 1 progress report compiled and submitted to the Community Portfolio Committee on implementation of ZDM EPWP per quarter |  |  | 1 progress report compiled and submitted to the Community Portfolio Committee on implementation of ZDM EPWP per quarter |  |  | 4 progress reports compiled and submitted to the Community Portfolio Committee on implementation of ZDM EPWP by 30 June 2025 |  | Quarterly |  |  |  | Achieved |  |  | Copy of Report and proof of submission
Establishing consistency and alignment between the district and locals by regular co-ordination of Integovernmental Relations | 118 | Number of sports meetings held per quarter | Number | N/A | Sports | SO 5.1.5 | 1 sports meeting held per quarter |  |  | 1 sports meeting held per quarter | 5 sports meeting held per quarter | 6 sports meeting held per quarter | 1 sports meeting held per quarter | 8 sports meeting held per quarter | 9 sports meeting held per quarter | 1 sports meeting held per quarter |  |  | 4 spots meetings held by 30 June 2025 |  | Quarterly | [6 empty] | Notice, Agenda, and Attendance Register
| 119 | Number of ZDM EPWP forum meetings conducted per quarter | Number | N/A | EPWP |  | 1 ZDM EPWP forum meeting conducted per quarter |  |  | 1 ZDM EPWP forum meeting conducted per quarter |  |  | 1 ZDM EPWP forum meeting conducted per quarter |  |  | 1 ZDM EPWP forum meeting conducted per quarter |  |  | 4 ZDM EPWP forum meetings conducted by 30 June 2025 |  | Quarterly |  |  |  | Not Achieved |  |  | Notice, Agenda, and Attendance Register
| 120 | Number of ZDM Tourism Forum meetings held within ZDM per quarter | Number | N/A | Tourism |  | 1 ZDM Tourism Forum meeting held within ZDM per quarter |  |  | 1 ZDM Tourism Forum meeting held within ZDM per quarter |  |  | 1 ZDM Tourism Forum meeting held within ZDM per quarter |  |  | 1 ZDM Tourism Forum meeting held within ZDM per quarter |  |  | 4 ZDM Tourism Forum meetings held within ZDM by 30 June 2025 |  | Quarterly |  |  |  | Achieved |  |  | Notice, Agenda, and Attendance register
| 121 | Number of accommodation inspections per quarter | Number | N/A | Tourism |  | 5 Accommodation inspection per quarter |  |  | 5 Accommodation inspection per quarter | 5 Accommodation inspection per quarter | 6 Accommodation inspection per quarter | 5 Accommodation inspection per quarter | 8 Accommodation inspection per quarter | 9 Accommodation inspection per quarter | 5 Accommodation inspection per quarter | 2 Accommodation inspection per quarter | 3 Accommodation inspection per quarter | 20 Accommodation inspection by 30 June 2025 |  | Quarterly | [6 empty] | Attendance register, and inspection form
| 122 | Number of tourism exhibitions per quarter | Number | N/A | Tourism |  | 1 tourism exhibition held per quarter |  |  | 1 tourism exhibition held per quarter | 5 tourism exhibition held per quarter | 6 tourism exhibition held per quarter | 1 tourism exhibition held per quarter | 8 tourism exhibition held per quarter | 9 tourism exhibition held per quarter | 1 tourism exhibition held per quarter | 11 tourism exhibition held per quarter | 12 tourism exhibition held per quarter | 4 tourism exhibition held by 30 June 2025 |  | Quarterly | [6 empty] | Pictures and attendance register
Note on C6: Mlungisi Ngcobo: Look at target within studs??