## Planning
ZULULAND DISTRICT MUNICIPALITY 2025/2026
DEPARTMENTAL SERVICE DELIVERY AND BUDGET IMPLEMENTATION PLAN: GENERAL MANAGER PLANNING
KPA 1 - BASIC SERVICE DELIVERY AND INFRASTRUCTURE
Strategic Objective(SO) | KPI No. | Key Performance Indicator | Unit of Measure | Formula | Responsible Unit | IDP Strategic Objective Ref No. | QUARTERLY TARGETS | [13 empty] | target date / reporting frequency | Budget Allocated (2021/2022) | Q2 Status | REASON FOR VIARIANCE | MEASURES TAKEN TO IMPROVE PERFORMANCE | Portolio of Evidence
[7 empty] | Target Q1 30 Sep 2025 | Actual Q 1 | Q1 Status | Target Q2 31 Dec 2025 | Actual Q2 | POE | Target Q3 31 March 2026 | Actual Q3 | Status Q3 | Target Q4 30 Jun 2026 | Actual Q4 | POE | Annual Target | Annual Actual
Continuously managing all developed infrastructure capital assets to minimize the total cost of owning and operating these assets while delivering the desired service levels & protecting the natural environment ( Effective Asset Management, internal&community capacity building, collecting revenue, tarrifs, monitoring & evaluation, environmental management)
Establishing and maintaining partnerships with government and private sector to accelerate provision of universal, equitable & consistent access to the municipal services that local communities are entitled to. | 1 | Number of households within ZDM to be provided with access to water within RDP standard per quarter | Number | N/A | PMU | SO 1.2.1 | 200 households within ZDM to be provided with access to water within RDP standard per quarter | 0 | Not Achieved | 200 households within ZDM to be provided with access to water within RDP standard per quarter | 327 households within ZDM to be provided with access to water within RDP standard per quarter | 327 households within ZDM to be provided with access to water within RDP standard per quarter | 200 households within ZDM to be provided with access to water within RDP standard per quarter |  |  | 200 households within ZDM to be provided with access to water within RDP standard per quarter |  |  | 800 households within ZDM to be provided with access to water within RDP standard by 30 June 2026 |  | Quarterly |  |  |  |  | List of beneficiaries and GPS coordinates
| 2 | Number of households within ZDM to be provided with access to Sanitation within RDP standard per quarter | Number |  | PMU |  | 50 households within ZDM to be provided with access to Sanitation within RDP standard per quarter | 51 households within ZDM to be provided with access to Sanitation within RDP standard per quarter | 52 households within ZDM to be provided with access to Sanitation within RDP standard per quarter | 50 households within ZDM to be provided with access to Sanitation within RDP standard per quarter | 54 households within ZDM to be provided with access to Sanitation within RDP standard per quarter | 55 households within ZDM to be provided with access to Sanitation within RDP standard per quarter | 50 households within ZDM to be provided with access to Sanitation within RDP standard per quarter | 57 households within ZDM to be provided with access to Sanitation within RDP standard per quarter | 58 households within ZDM to be provided with access to Sanitation within RDP standard per quarter | 50 households within ZDM to be provided with access to Sanitation within RDP standard per quarter | 60 households within ZDM to be provided with access to Sanitation within RDP standard per quarter | 61 households within ZDM to be provided with access to Sanitation within RDP standard per quarter | 200 households within ZDM to be provided with access to Sanitation within RDP standard by 30 June 2026 |  | Quarterly |  |  |  |  | List of beneficiaries and GPS coordinates
| 3 | Number of ZDM water contracts completed annually | Number | N/A | PMU |  | N/A | Due in Q4 |  | N/A | N/A | N/A | N/A | N/A | N/A | 12 ZDM contracts completed annually |  |  | 12 ZDM contracts completed annually by 30 June 2026 |  | 2026-06-30 |  |  |  |  | Certificate of completion
| 4 | Number of ZDM sanitation contracts under construction per quarter | Number | N/A | PMU |  | 2 ZDM sanitation contracts under construction per quarter | 2 | Achieved | 2 ZDM sanitation contracts under construction per quarter |  |  | 2 ZDM sanitation contracts under construction per quarter |  |  | 2 ZDM sanitation contracts under construction per quarter |  |  | 2 ZDM sanitation contracts under construction by 30 June 2024 |  | Quarterly |  |  |  |  | Contract lists or progress reports and appointment letters of service providers
| 4 | Number of ZDM water contracts under construction annually | Number | N/A | PMU |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 23 ZDM water contracts under construction annually |  |  | 23 ZDM water contracts under construction by 30 June 2026 |  | 2026-06-30 |  |  |  |  | Contract lists and appointment letters of service providers
| 10 | Number of assessment report of ZDM water service provider (contractors) performed per quarter | Number |  | PMU |  | 1 assessment report of ZDM water service provider (contractors) performed per quarter |  |  | 1 assessment report of ZDM water service provider (contractors) performed per quarter | I assessment report of ZDM water service provider (contractors) performed per quarter | I assessment report of ZDM water service provider (contractors) performed per quarter | 1 assessment report of ZDM water service provider (contractors) performed per quarter |  |  | 1 assessment report of ZDM water service provider (contractors) performed per quarter |  |  | 4 assessment report of ZDM water service provider (contractors) performed by 30 June 2026 |  | Quarterly |  |  |  |  | Assessment Report
| 9 | Number of households within ZDM to be provided with sanitation facilities within RDP standard per quarter | Number | N/A | PMU |  | 678 households within ZDM to be provided with sanitation facilities within RDP standard per quarter | 209 | Not Achieved | 564 households within ZDM to be provided with sanitation facilities within RDP standard per quarter |  |  | 71 households within ZDM to be provided with sanitation facilities within RDP standard per quarter |  |  | 71 households within ZDM to be provided with sanitation facilities within RDP standard per quarter |  |  | 1384 households within ZDM to be provided with sanitation facilities within RDP standard by 30 June 2024 |  | Quarterly |  |  |  |  | List of beneficiaries and GPS co-ordinates
| 11 | Number of assessment report of ZDM water service provider (consultants) performed per quarter | Number | N/A | WSA |  | 1 assessment report of ZDM water service provider (consultants) performed per quarter | 0 | Not Achieved | 1 assessment report of ZDM water service provider (consultants) performed per quarter | 1 assessment report of ZDM water service provider (consultants) performed per quarter | 1 assessment report of ZDM water service provider (consultants) performed per quarter | 1 assessment report of ZDM water service provider (consultants) performed per quarter |  |  | 1 assessment report of ZDM water service provider (consultants) performed per quarter |  |  | 4 assessment reports of ZDM water service provider (consultants) performed by 30 June 2026 |  | Quarterly | Internal |  |  |  | Assessment Report
KPA 03- MUNICIPAL FINANCIAL VIABILITY AND MANAGEMENT
Strategic Objective(SO) | KPI No. | Key Performance Indicator | Unit of Measure | Formula | Responsible Unit | IDP Strategic Objective Ref No. | Target Q1 30 Sep 2025 | Actual Q 1 | Q1 Status | Taret Q2 31 Dec 2025 | Actual Q2 | POE | Target Q3 31 Mar 2026 | Actual Q 3 | Status Q3 | Target Q4 30 Jun 2026 | Actual Q4 | POE | Annual Target | Annual Actual | Target date/ reporting frequency | Budget Allocated (2021/2022) | Q2 Status | REASON FOR VIARIANCE | MEASURES TAKEN TO IMPROVE PERFORMANCE | Portolio of Evidence
Manage, monitor and review existing financial systems to support accurate and credible reporting, budget monitoring and compliance | 30 | Date 2025/2026 IDP process plan including Budget timetable submitted to Council | Date | N/A | Planning & Budget & Treasury | SO 3.1.3 | 2025/2026 IDP process plan including budget timetable submitted to Council by 31 Aug 2025 | 2024-08-29 | Achieved | N/A | Reported in Q1 |  | N/A | N/A | N/A | N/A |  |  | 2025/2026 IDP process plan including budget timetable submitted to Council by 31 Aug 2025 |  | 2025-08-31 | Internal |  |  |  | Council resolution and copy of IDP process plan including budget timetable
| 150 | Percentage of MIG spent per quarter | Percentage | N/A | PMU |  | 25% of MIG spent per quarter |  |  | 50% of MIG spent per quarter |  |  | 75% of MIG spent per quarter |  |  | 100% of MIG spent per quarter |  |  | 100% of MIG spent by 30 June 2026 |  | Quarterly |  |  |  |  | Expenditure Report
| 151 | Percentage of RBIG spent per quarter | Percentage | N/A | PMU |  | 30% of RBIG spent per quarter |  |  | 60% of RBIG spent per quarter |  |  | 85% of RBIG spent per quarter |  |  | 100% of RBIG spent per quarter |  |  | 100% of RBIG spent by 30 June 2026 |  | Quarterly |  |  |  |  | Expenditure Report
| 152 | Percentage of WSIG spent per quarter | Percentage | N/A | PMU |  | 30% of WSIG spent per quarter |  |  | 60% of WSIG spent per quarter |  |  | 85% of WSIG spent per quarter |  |  | 100% of WSIG spent per quarter |  |  | 100% of WSIG spent by 30 June 2026 |  | Quarterly |  |  |  |  | Expenditure Report
| 153 | Percentage spent on Municipal Rural Road Asset management | Percentage | N/A | Planning Admin |  | N/A | Due in Quarter 2 | Due in Quarter 2 | 50% spent on Municipal Rural Road Asset management |  |  | 70% spent on Municipal Rural Road Asset management |  |  | 100% spent on Municipal Rural Road Asset management |  |  | 100% spent on Municipal Rural Road Asset management by 30 June 2026 |  | Quarterly |  |  |  |  | Expenditure report
KPA 04 - GOOD GOVERNANCE AND PUBLIC PARTICIPATION
Strategic Objective(SO) | KPI No. | Key Performance Indicator | Unit of Measure | Formula | Responsible Unit | IDP Strategic Objective Ref No. | Target Q1 30 Sep 2025 | Actual Q 1 | Q1 Status | Target Q2 31 Dec 2025 | Actual Q2 | POE | Target Q3 31 Mar 2026 | Actual Q 3 | Status Q3 | Target Q4 30 Jun 2026 | Actual Q4 | POE | Annual Target | Annual Actual | Target date/ reporting frequency | Budget Allocated (2021/2022) | Q2 Status | REASON FOR VIARIANCE | MEASURES TAKEN TO IMPROVE PERFORMANCE | Portolio of Evidence
Systematic development and or review and monitoring implementation of all municipal policies, bylaws, strategies, plans and frameworks in line with any applicable legislation | 154 | Date WSIG and RBIG Annual Implementation Plan submitted to Department of Water and Sanitation | Date |  | PMU | SO 4.1.3 | N/A | Due in Quarter 4 | Due in Quarter 4 | N/A | Due in Quarter 4 | Due in Quarter 4 | N/A |  |  | WSIG and RBIG Annual Implementation Plan submitted to Department of Water and Sanitation by 30 June 2026 |  |  | WSIG and RBIG Annual Implementation Plan submitted to Department of Water and Sanitation by 30 June 2026 |  | 2026-06-15 | Internal | Due in Quarter 4 |  |  | Proof of Submission and copy of WSIG and RBIG Annual Implementation Plan report
| 155 | Date PMU Business Plan submitted to KZN-COGTA | Date |  | PMU |  | N/A | Due in Quarter 4 | Due in Quarter 4 | N/A | Due in Quarter 4 | Due in Quarter 4 | N/A |  |  | PMU Business Plan submitted to KZN-COGTA by 30 April 2026 |  |  | PMU Business Plan submitted to KZN-COGTA by 30 April 2026 |  | 2026-04-30 | Internal | Due in Quarter 4 |  |  | Proof of Submission and copy of PMU Business Plan report
| 156 | Date Three Year Proforma Implementation Plan submitted to KZN-COGTA | Date |  | PMU |  | N/A | Due in Quarter 3 | Due in Quarter 3 | N/A | Due in Quarter 3 |  | Three Year Proforma Implementation Plan submitted to KZN-COGTA by 30 January 2026 |  |  | N/A |  |  | Three Year Proforma Implementation Plan submitted to KZN-COGTA by 30 January 2026 |  | 2026-01-30 | Internal | Due in Quarter 3 |  |  | Proof of Submission and copy of three year proforma Implementation plan
| 157 | Date Water Loss, Water Conservation/ Demand management strategy reviewed by Council | Date | N/A | WSA |  | N/A |  | Not Achieved | N/A |  |  | N/A | N/A | N/A | Water Loss, Water Conservation/ Demand management strategy approved by Council by 30 May 2025 |  |  | Water Loss, Water Conservation/ Demand management strategy approved by Council by 30 May 2025 |  | 2025-05-30 |  |  | N/A | N/A | Council Resolution and Water Loss, Water Conservation/ Demand management strategy
| 158 | Number of Technical review meetings held per quarter | Number |  | PMU |  | 3 Technical review meetings held per quarter |  |  | 3 Technical review meetings held per quarter |  |  | 3 Technical review meetings held per quarter |  |  | 3 Technical review meetings held per quarter |  |  | 12 Technical review meetings held by 30 June 2026 |  | Quarterly |  |  |  |  | Notice, Agenda; and attendance register
| 159 | Number of ZDM GIS & Environmental Management Technical Forum held per quarter | Number | N/A | GIS |  | 1 ZDM GIS & Environmental Management Technical Forum per quarter |  |  | 1 ZDM GIS & Environmental Management Technical Forum per quarter |  |  | 1 ZDM GIS & Environmental Management Technical Forum per quarter |  |  | 1 ZDM GIS & Environmental Management Technical Forum per quarter |  |  | 4 ZDM GIS & Environmental Management Technical Forums by 30 June 2026 |  | Quarterly | Internal |  |  |  | Notice, Agenda; and attendance register
| 160 | Number of Departmental meetings held per quarter | Number | N/A | HOD |  | 3 Departmental meetings held per quarter |  |  | 3 Departmental meetings held per quarter |  |  | 3 Departmental meetings held per quarter |  |  | 3 Departmental meetings held per quarter |  |  | 12 Departmental meetings held by 30 June 2026 |  | Quarterly | Internal |  |  |  | Notice, Agenda; and attendance register
| 161 | Number of campaigns on Environmental Health & Safety awareness held per quarter | Number |  | WSA |  | 1 Environmental Health & Safety awareness held per quarter | 2 Environmental Health & Safety awareness held per quarter | 3 Environmental Health & Safety awareness held per quarter | 1 Environmental Health & Safety awareness held per quarter | 5 Environmental Health & Safety awareness held per quarter | 6 Environmental Health & Safety awareness held per quarter | 1 Environmental Health & Safety awareness held per quarter | 8 Environmental Health & Safety awareness held per quarter | 9 Environmental Health & Safety awareness held per quarter | 1 Environmental Health & Safety awareness held per quarter | 11 Environmental Health & Safety awareness held per quarter | 12 Environmental Health & Safety awareness held per quarter | 4 Environmental Health & Safety awareness held by 30 June 2026 |  | Quarterly |  |  |  |  | Notice, Pamphlet and attendance register
| 162 | Number of Water Conservation and Water Demand Management campaigns held per quaeter | Number | N/A | WSA |  | 1 Water Conservation and Water Demand Management campaign held per quarter | 2 Water Conservation and Water Demand Management campaign held per quarter | 3 Water Conservation and Water Demand Management campaign held per quarter | 1 Water Conservation and Water Demand Management campaign held per quarter | 5 Water Conservation and Water Demand Management campaign held per quarter | 6 Water Conservation and Water Demand Management campaign held per quarter | 1 Water Conservation and Water Demand Management campaign held per quarter | 8 Water Conservation and Water Demand Management campaign held per quarter | 9 Water Conservation and Water Demand Management campaign held per quarter | 1 Water Conservation and Water Demand Management campaign held per quarter | 11 Water Conservation and Water Demand Management campaign held per quarter | 12 Water Conservation and Water Demand Management campaign held per quarter | 4 Water Conservation and Water Demand Management campaign held by 30 June 2026 |  | Quarterly | Internal |  |  |  | Notice, Pamphlet and attendance register
KPA 05- MUNICIPAL TRANSFORMATION AND ORGANIZATIONAL DEVELOPMENT
Strategic Objective(SO) | KPI No. | Key Performance Indicator | Unit of Measure | Formula | Responsible Unit | IDP Strategic Objective Ref No. | Target Q1 30 Sep 2025 | Actual Q 1 | Q1 Status | Target Q2 31 Dec 2025 | Actual Q2 | POE | Target Q3 31 Mar 2026 | Actual Q 3 | POE | Target Q4 30 Jun 2026 | Actual Q4 | POE | Annual Target | Annual Actual | Target date/ reporting frequency | Budget Allocated (2021/2022) | Q2 Status | REASON FOR VIARIANCE | MEASURES TAKEN TO IMPROVE PERFORMANCE | Portolio of Evidence
Investing in a workforce to meet service delievery demand through implementing a culture of continous learning and improvement | 163 | Number of WSP Meeting held per quarter | Number |  | WSA | SO 5.1.1 | 3 WSP Meetings held per quarter |  |  | 3 WSP Meetings held per quarter | 3 WSP Meetings held per quarter | 3 WSP Meetings held per quarter | 3 WSP Meetings held per quarter |  |  | 3 WSP Meetings held per quarter |  |  | 12 WSP Meetings held by 30 June 2026 |  | Quarterly |  |  |  |  | Notice, Agenda; and attendance register
| 164 | Date WSDP Reviewed by Council | Date |  | WSA |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | WSDP Reviewed by 30 June 2026 |  |  | WSDP Reviewed by 30 June 2026 |  | 2026-06-30 |  |  |  |  | Council Resolution and Reviewed WSDP
Optimise workforce productivity by enforcing a sound organizational culture | 165 | Number of MIG Claims uploads onto MIG MIS and submission of the MIG Expenditure and Commitments Schedule [MECS] to KZN-COGTA per quarter | Number | N/A | PMU | SO 5.1.3 | 3 MIG Claims uploads onto MIG MIS and submission of the MIG Expenditure and Commitments Schedule [MECS] to KZN-COGTA per quarter |  |  | 3 MIG Claims uploads onto MIG MIS and submission of the MIG Expenditure and Commitments Schedule [MECS] to KZN-COGTA per quarter |  |  | 3 MIG Claims uploads onto MIG MIS and submission of the MIG Expenditure and Commitments Schedule [MECS] to KZN-COGTA per quarter |  |  | 3 MIG Claims uploads onto MIG MIS and submission of the MIG Expenditure and Commitments Schedule [MECS] to KZN-COGTA per quarter |  |  | 12 MIG Claims uploads onto MIG MIS and submission of the MIG Expenditure and Commitments Schedule [MECS] to KZN-COGTA by 30 June 2026 |  | Quarterly | Internal |  |  |  | Print screen of system upload
| 166 | Number of WSIG and RBIG QPE Reports submitted to Department of Water & Sanitation per quarter | Number | N/A | PMU |  | 1 WSIG and RBIG QPE Report submitted to DWS per quarter (Previous Quarter) |  |  | 1 WSIG and RBIG QPE Report submitted to DWS per quarter (Previous Quarter) | 1 WSIG and RBIG QPE Report submitted to DWS per quarter (Previous Quarter) | 1 WSIG and RBIG QPE Report submitted to DWS per quarter (Previous Quarter) | 1 WSIG and RBIG QPE Report submitted to DWS per quarter (Previous Quarter) |  |  | 1 WSIG and RBIG QPE Report submitted to DWS per quarter (Previous Quarter) |  |  | 4 WSIG and RBIG QPE Report submitted to DWS by 30 June 2026 |  | Quarterly | Internal |  |  |  | Proof of Submission and copy WSIG and RBIG QPE Report
| 167 | Date MIG Annual Performance Evaluation Report submitted to KZN-COGTA | Date | N/A | PMU |  | MIG Annual Performance Evaluation Report submitted to KZN-COGTA by 30 Sept 2025 |  |  | N/A | Reported in Q1 | N/A | N/A | N/A | N/A | N/A |  |  | MIG Annual Performance Evaluation Report submitted to KZN-COGTA by 30 Sept 2025 |  | 2025-09-30 |  | Reported in Q1 |  |  | Proof of Submission and copy of MIG Annual Performance Evaluation Report
| 168 | Number of MIG Expenditure Proof of Payments uploaded to KZN-COGTA on MIG MIS per quarter | Number | N/A | PMU |  | 3 MIG Expenditure Proof of Payments uploaded to KZN-COGTA on MIG MIS per quarter |  |  | 3 MIG Expenditure Proof of Payments uploaded to KZN-COGTA on MIG MIS per quarter |  |  | 3 MIG Expenditure Proof of Payments uploaded to KZN-COGTA on MIG MIS per quarter |  |  | 3 MIG Expenditure Proof of Payments uploaded to KZN-COGTA on MIG MIS per quarter |  |  | 12 MIG Expenditure Proof of Payments uploaded to KZN-COGTA on MIG MIS by 30 June 2026 |  | Quarterly | Internal |  |  |  | Proof of Submission and proof of payments
| 169 | Number of WSIG and RBIG Monthly Reports (5B) submitted to Department of Water & Sanitation per quarter | Number | N/A | PMU |  | 3 WSIG and RBIG Monthly Reports (5B) submitted to Department of Water & Sanitation per quarter |  |  | 3 WSIG and RBIG Monthly Reports (5B) submitted to Department of Water & Sanitation per quarter |  |  | 3 WSIG and RBIG Monthly Reports (5B) submitted to Department of Water & Sanitation per quarter |  |  | 3 WSIG and RBIG Monthly Reports (5B) submitted to Department of Water & Sanitation per quarter |  |  | 12 WSIG and RBIG Monthly Reports (5B) submitted to Department of Water & Sanitation by 30 June 2026 |  | Quarterly | Internal |  |  |  | Proof of Submission and copy WSIG and RBIG monthly report
| 170 | Date 2025/2026 GIS report submitted to council | Date |  | GIS |  | N/A |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 2025/2026 GIS report submitted to counciL BY 30 June 2026 |  |  | 2025/2026 GIS report submitted to counciL BY 30 June 2026 |  | 2026-06-30 |  |  |  |  | Council resolution and Copy of GIS report
| 171 | Date Final 2026/2027 IDP submitted to council for adoption | Date | N/A | Planning Admin |  | N/A |  |  | N/A | Due in Q4 |  | N/A | N/A | N/A | Final 2026/2027 IDP submitted to council for adoption by 31-May-2026 |  |  | Final 2026/2027 IDP submitted to council for adoption by 31-May-2026 |  | 2026-05-31 |  | Due in Q4 |  |  | Council Resolution and copy of final IDP
| 172 | Date ZDM 2025/2026 Annual Report adopted by Council | Date | N/A | IDP |  | N/A |  |  | N/A | Due in Q4 |  | Annual Report adopted by Council by 31 Jan 2026 |  |  | N/A |  |  | Annual Report adopted by Council by 31 Jan 2026 |  | 2026-01-31 | Internal | Due in Q4 |  |  | Council Resolution and copy of annual report
KPA 06 - SPATIAL PLANNING AND ENVIRONMENTAL MANAGEMENT
Strategic Objective(SO) | KPI No. | Key Performance Indicator | Unit of Measure | Formula | Responsible Unit | IDP Strategic Objective Ref No. | Target Q1 30 Sep 2025 | Actual Q 1 | Q1 Status | Target Q2 31 Dec 2025 | Actual Q2 | POE | Target Q3 31 Mar 2026 | Actual Q 3 | POE | Target Q4 30 Jun 2026 | Actual Q4 | POE | Annual Target | Annual Actual | Target date/ reporting frequency | Budget Allocated (2021/2022) | Q2 Status | REASON FOR VIARIANCE | MEASURES TAKEN TO IMPROVE PERFORMANCE | Portolio of Evidence
Promoting and conserving the natural environment through land use management policies, plans and frameworks | 173 | Number of consolidated reports produced on property valuation roll from ZDM Local Municipalities per quarter | Number | N/A | GIS | SO 6.1.2 | 1 consolidated report produced on property valuation roll from ZDM Local Municipalities per quarter |  |  | 1 consolidated report produced on property valuation roll from ZDM Local Municipalities per quarter |  |  | 1 consolidated report produced on property valuation roll from ZDM Local Municipalities per quarter |  |  | 1 consolidated report produced on property valuation roll from ZDM Local Municipalities per quarter |  |  | 4 consolidated reports produced on property valuation roll from ZDM Local Municipalities by 30 June 2026 |  | Quarterly | Internal |  |  |  | consolidated reports on property valuation roll
Note on C6: Mlungisi Ngcobo: Look at target within stds??

## Departmental summary Q1 (hidden)
SUMMARY REPORT FOR QUARTER 1 OF 2022/2023 : REPORT PER KPAs
| Achieved | Not achieved | Total indicators per KPA
KPA 1 - BASIC SERVICE DELIVERY AND INFRASTRUCTURE | 4 | 2 | 6
KPA 2 - MUNICIPAL TRANSFORMATION AND ORGANIZATIONAL DEVELOPMENT | N/A | N/A | N/A
KPA 3 - MUNICIPAL FINANCIAL VIABILITY AND MANAGEMENT | 3 | 1 | 4
KPA 4 - GOOD GOVERNANCE AND PUBLIC PARTICIPATION | 3 | 1 | 4
KPA 05 - LOCAL ECONOMIC DEVELOPMENT | 6 | 0 | 6
KPA 06- SPATIAL PLANNING AND ENVIRONMENTAK MANAGEMENT | 1 | 0 | 1
TOTAL: | 17 | 4 | 21
Percentage: | 81% | 19%